## Sheet1
project_id | project_name | wbs_value | task_id | parent_id | task_name | percent_done | start_date | end_date | duration | duration_unit | bl_start | bl_finish | crew_size | location_name | company_name | company_color | pull_plan | calendar_name | constraint_type | constraint_date | deadline_date | deadline_variance | p6_activity_id | notes | ordered_parent_index | p6_wbs_level | p6_wbs_guid | p6_wbs_parent_guid | date_and_time
240001 | Test Project | 1.12 | 41905203 | 41904234 | Construction | 4.4104 | 2023-09-07 08:00 | 2023-10-12 17:00 | 26 | day | 2020-01-27 07:00 | 2025-05-30 17:00 | [12 empty] | 11 | 2 | iRqoq5YdVEasR9RY3sZSmg | 220015 | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1 | 41904239 | 41905203 | Enabling After NTC (Construction Management Plans- CMP) | 28 |  |  |  | day | 2020-01-27 07:00 | 2023-06-15 17:00 | [12 empty] | 0 | 3 | sycKPI8q4EaFiuMDlAky2A | iRqoq5YdVEasR9RY3sZSmg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1 | 41904261 | 41904239 | Enabling - Atlantic Ave Work Zone | 14 |  |  |  | day | 2020-01-27 07:00 | 2022-05-26 17:00 | [12 empty] | 0 | 4 | 3ojFbL3LdU2aC6Mkt+YxYg | sycKPI8q4EaFiuMDlAky2A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1 | 41904429 | 41904261 | CMP-1 Atlantic Avenue Staging Area (Standard Hours) |  |  |  |  | day | 2020-01-27 07:00 | 2021-10-19 17:00 | [12 empty] | 0 | 5 | u18AfljIfku3la9yTdYU/A | 3ojFbL3LdU2aC6Mkt+YxYg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.1 | 41904672 | 41904429 | CMP-1A |  |  |  |  | day | 2020-01-27 07:00 | 2020-06-26 17:00 | [12 empty] | 0 | 6 | ELuab9RfckmxYB/isbyNuA | u18AfljIfku3la9yTdYU/A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.1.1 | 41904994 | 41904672 | Work Plan- CMP 1A |  |  |  |  | day | [14 empty] | 0 | 7 | uNsux8dmJ0u4MXoSSvSvrg | ELuab9RfckmxYB/isbyNuA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.1.2 | 41904838 | 41904672 | Staging Area | 38 |  |  |  | day | 2020-01-27 07:00 | 2020-02-25 17:00 | [12 empty] | 1 | 7 | NE4aL2QCXUOLi9+jmXLd9A | ELuab9RfckmxYB/isbyNuA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.1.3 | 41904837 | 41904672 | ADA Ramp | 18 |  |  |  | day | 2020-05-26 07:00 | 2020-06-26 17:00 | [12 empty] | 2 | 7 | cRxJKBr/uUaK6oLc058KdQ | ELuab9RfckmxYB/isbyNuA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2 | 41904673 | 41904429 | CMP-1B |  |  |  |  | day | 2020-04-01 07:00 | 2020-11-13 17:00 | [12 empty] | 1 | 6 | NWGKHvepbkOeW8mmelmtZw | u18AfljIfku3la9yTdYU/A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.1 | 41904995 | 41904673 | Work Plan- CMP 1B | 10 |  |  |  | day | [14 empty] | 0 | 7 | sipfLbFIKE+xyuazJlffTw | NWGKHvepbkOeW8mmelmtZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.2 | 41904839 | 41904673 | Staging Area |  |  |  |  | day | 2020-05-26 07:00 | 2020-07-31 17:00 | [12 empty] | 1 | 7 | POJNVqml4UGJvyPpMzbQVA | NWGKHvepbkOeW8mmelmtZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.3 | 41904840 | 41904673 | Headhouse | 23 |  |  |  | day | 2020-04-01 07:00 | 2020-07-30 17:00 | [12 empty] | 2 | 7 | D7U6hTLnZU69OsO10QSAOw | NWGKHvepbkOeW8mmelmtZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.3.1 | 41905151 | 41904840 | Police Bubble Removal | 35 |  |  |  | day | [14 empty] | 0 | 8 | ycLVUrZ9wEOy6zuIDfOvdA | D7U6hTLnZU69OsO10QSAOw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.3.1.1 | 41905174 | 41905151 | COR #XX -Police Bubble | 39 |  |  |  | day | [14 empty] | 0 | 9 | 1zjHYQIekkKbbtysQswhIQ | ycLVUrZ9wEOy6zuIDfOvdA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.3.1.1.1 | 41905182 | 41905174 | 00 0000 - [260000-XX] |  |  |  |  | day | [14 empty] | 0 | 10 | x959EXUWdE2P5oKoGjDB+g | 1zjHYQIekkKbbtysQswhIQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.3.2 | 41905152 | 41904840 | Keolis Bubble Removal |  |  |  |  | day | 2020-04-01 07:00 | 2020-07-30 17:00 | [12 empty] | 1 | 8 | 69MKZowTOUuGTrsjgWROFw | D7U6hTLnZU69OsO10QSAOw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4 | 41905013 | 41904673 | Protective Canopy / Demo Existing Canopy [Night Work] | 21 |  |  |  | day | 2020-06-25 07:00 | 2020-11-13 17:00 | [12 empty] | 3 | 7 | UDCDKpv8+kWDJ5YygjZp5w | NWGKHvepbkOeW8mmelmtZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.1 | 41905153 | 41905013 | Option 1 |  |  |  |  | day | 2020-06-25 07:00 | 2020-11-13 17:00 | [12 empty] | 0 | 8 | HxA3zw5vFkionp85eAeQgA | UDCDKpv8+kWDJ5YygjZp5w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.1.1 | 41905177 | 41905153 | G - J.75 | 23 |  |  |  | day | 2020-07-06 07:00 | 2020-09-30 17:00 | [12 empty] | 0 | 9 | v0iyhHWfQ0C0Q4rogrfXyw | HxA3zw5vFkionp85eAeQgA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.1.2 | 41905178 | 41905153 | H - Bike Rack | 43 |  |  |  | day | 2020-06-25 07:00 | 2020-08-07 17:00 | [12 empty] | 1 | 9 | dv5uBfofWUyfhCQ2mOKCYA | HxA3zw5vFkionp85eAeQgA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.1.3 | 41905179 | 41905153 | G-F | 29 |  |  |  | day | 2020-07-23 07:00 | 2020-09-30 17:00 | [12 empty] | 2 | 9 | RV52ocmy406Qo3kBnoQSwA | HxA3zw5vFkionp85eAeQgA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.1.4 | 41905180 | 41905153 | F-D | 37 |  |  |  | day | 2020-07-29 07:00 | 2020-11-04 17:00 | [12 empty] | 3 | 9 | K5Z5q/SsB0WbrAoSReadLA | HxA3zw5vFkionp85eAeQgA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.1.5 | 41905181 | 41905153 | D-B | 1 |  |  |  | day | 2020-07-31 07:00 | 2020-11-13 17:00 | [12 empty] | 4 | 9 | DmqgqXJ7/UGEKelw2yD6JA | HxA3zw5vFkionp85eAeQgA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.2 | 41905154 | 41905013 | Original |  |  |  |  | day | [14 empty] | 1 | 8 | DHLT5DLj/keEhOrJoccYHw | UDCDKpv8+kWDJ5YygjZp5w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.2.1 | 41905175 | 41905154 | Bike Rack | 32 |  |  |  | day | [14 empty] | 0 | 9 | 3Qir0kx0AUa3mSni1ZTh9Q | DHLT5DLj/keEhOrJoccYHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.2.2 | 41905176 | 41905154 | H Line Atlantic | 11 |  |  |  | day | [14 empty] | 1 | 9 | W5JXOvtK+UOgKPQoFrrWbg | DHLT5DLj/keEhOrJoccYHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.2.3 | 41905173 | 41905154 | H Line to D Line | 21 |  |  |  | day | [14 empty] | 2 | 9 | 9TtH7xqvZUC5sXhPzvPu4A | DHLT5DLj/keEhOrJoccYHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.2.4 | 41905172 | 41905154 | H - F | 43 |  |  |  | day | [14 empty] | 3 | 9 | 8N1PbtRguEW4sHwB3APLVg | DHLT5DLj/keEhOrJoccYHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.2.5 | 41905171 | 41905154 | F - D | 24 |  |  |  | day | [14 empty] | 4 | 9 | 3ebYUYFWFkGr8Dcu3sn3SQ | DHLT5DLj/keEhOrJoccYHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.2.4.3 | 41905147 | 41905013 | C (Enables Headhouse Mods) | 48 |  |  |  | day | [14 empty] | 2 | 8 | kSr4rV+5+UaDKF08LIiJ6Q | UDCDKpv8+kWDJ5YygjZp5w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.3 | 41904748 | 41904429 | Pile Cap Modifications(Along col line 31) | 26 |  |  |  | day | 2020-06-05 07:00 | 2021-10-19 17:00 | [12 empty] | 2 | 6 | hvaREs1M/0qunUEBgC9pBg | u18AfljIfku3la9yTdYU/A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.3.1 | 41905021 | 41904748 | Demo WP | 41 |  |  |  | day | [14 empty] | 0 | 7 | AwU5WEWst0+uaB886oSiAQ | hvaREs1M/0qunUEBgC9pBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.3.2 | 41905249 | 41904748 | FRP |  |  |  |  | day | 2020-12-07 07:00 | 2021-10-19 17:00 | [12 empty] | 1 | 7 | pTzzCMKkq0qUuvAYzM+pIQ | hvaREs1M/0qunUEBgC9pBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.3.2.1 | 41905253 | 41905249 | J29.7 |  |  |  |  | day | 2021-01-14 07:00 | 2021-01-29 17:00 | [12 empty] | 0 | 8 | VUL9VXaicEWK4h4IRuimvw | pTzzCMKkq0qUuvAYzM+pIQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.1.3.2.2 | 41905256 | 41905249 | Remaining |  |  |  |  | day | 2021-02-01 07:00 | 2021-10-19 17:00 | [12 empty] | 1 | 8 | cdcjvLe3G0K6UyYGbSKWOw | pTzzCMKkq0qUuvAYzM+pIQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2 | 41904433 | 41904261 | CMP-7 CA/T Egress Tunnel Mods (M-F 8:00pm to 4:30am) | 46 |  |  |  | day | 2020-03-04 07:00 | 2022-05-26 17:00 | [12 empty] | 1 | 5 |  | 3ojFbL3LdU2aC6Mkt+YxYg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1 | 41904700 | 41904433 | CMP-7 A&B - CA/T Egress Tunnel Modifications |  |  |  |  | day | 2020-06-29 07:00 | 2022-05-26 17:00 | [12 empty] | 0 | 6 | Qm9nohHuFU2QwFxEq/eDvg |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.1 | 41905084 | 41904700 | 01 - Bulletin 13 - Silverline Electrical Room Ventilation Scope | 2 |  |  |  | day | 2020-09-17 07:00 | 2021-12-09 17:00 | [12 empty] | 0 | 7 | 47tJQKwaPkOr+O4vJUSMRg | Qm9nohHuFU2QwFxEq/eDvg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.1.1 | 41905431 | 41905084 | Utility Relocation | 36 |  |  |  | day | 2021-09-09 07:00 | 2021-10-29 17:00 | [12 empty] | 0 | 8 | UdaarTrKq0abMDhvqcoxoA | 47tJQKwaPkOr+O4vJUSMRg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.1.2 | 41905432 | 41905084 | Wiresaw Penetrations | 6 |  |  |  | day | 2021-09-25 07:00 | 2021-11-05 17:00 | [12 empty] | 1 | 8 | g1hGeBqkgEO1hxbTp83uTg | 47tJQKwaPkOr+O4vJUSMRg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.1.3 | 41905433 | 41905084 | Duct Removal/Installation | 20 |  |  |  | day | 2021-10-05 07:00 | 2021-12-09 17:00 | [12 empty] | 2 | 8 | pkzfFDtP3UugIRYOTlddPA | 47tJQKwaPkOr+O4vJUSMRg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.1.4 | 41905434 | 41905084 | Infill Existing Vent Penetrations | 8 |  |  |  | day | 2021-11-02 07:00 | 2021-11-09 17:00 | [12 empty] | 3 | 8 | 37OcOOtzjUOyAaVLb7/Qmg | 47tJQKwaPkOr+O4vJUSMRg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.2 | 41905087 | 41904700 | 02 - CMP-7 A - Relocate Door at CA/T Egress | 38 |  |  |  | day | [14 empty] | 1 | 7 | cCyGxFIRKkS662yixfDhgQ | Qm9nohHuFU2QwFxEq/eDvg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.3 | 41905085 | 41904700 | 03 - CAT Egress - Temp Stair Riser Extension |  |  |  |  | day | 2020-07-31 07:00 | 2022-05-26 17:00 | [12 empty] | 2 | 7 | hPHn5WigFUOG5urSclxkRQ | Qm9nohHuFU2QwFxEq/eDvg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.3.1 | 41905464 | 41905085 | new | 3 |  |  |  | day | [14 empty] | 0 | 8 | yO1IgWVzdE6LuP25NemocA | hPHn5WigFUOG5urSclxkRQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.3.2 | 41905465 | 41905085 | old |  |  |  |  | day | [14 empty] | 1 | 8 | WXHo9hXHBES7ScVN8YXPyw | hPHn5WigFUOG5urSclxkRQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.4 | 41905460 | 41904700 | 04 - Vent Demo and DMP/North Foundation |  |  |  |  | day | 2021-11-17 07:00 | 2021-12-15 17:00 | [12 empty] | 3 | 7 | C9TUNZLG/0mLPD4tEDcQtg | Qm9nohHuFU2QwFxEq/eDvg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.5 | 41905461 | 41904700 | 05 - Sanitary Line | 49 |  |  |  | day | [14 empty] | 4 | 7 |  | Qm9nohHuFU2QwFxEq/eDvg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.6 | 41905086 | 41904700 | SMH2 Offset | 8 |  |  |  | day | 2020-06-29 07:00 | 2020-10-30 17:00 | [12 empty] | 5 | 7 | g/+r4gJey0a6E1YbSuV0yA | Qm9nohHuFU2QwFxEq/eDvg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.1.7 | 41905088 | 41904700 | New Structural and Backfill | 25 |  |  |  | day | [14 empty] | 6 | 7 | XIynG6Bq6E6krhVjpoXdyQ | Qm9nohHuFU2QwFxEq/eDvg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.2 | 41904620 | 41904433 | CMP-7 C - Substructure (Standard Work Hours 7:00 am to 3:30 pm) | 1 |  |  |  | day | [14 empty] | 1 | 6 | isJPQsnQUEC7ppHPcSgCzg |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.3 | 41904736 | 41904433 | CMP-7 D - Silverline Tunnel Roof - Structural |  |  |  |  | day | 2020-03-04 07:00 | 2021-01-31 17:00 | [12 empty] | 2 | 6 | otS1P85kF0ufxqOKSzwphw |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.3.1 | 41905027 | 41904736 | Demolition | 27 |  |  |  | day | 2020-05-26 07:00 | 2020-09-11 17:00 | [12 empty] | 0 | 7 | u5GdELw/AEWM2R4O2PAsjA | otS1P85kF0ufxqOKSzwphw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.3.1.1 | 41905155 | 41905027 | Under-Platform A |  |  |  |  | day | [14 empty] | 0 | 8 | uqNAAFWtk0qcoR18jw9knA | u5GdELw/AEWM2R4O2PAsjA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.1.2.3.2 | 41905026 | 41904736 | New Structural and Backfill |  |  |  |  | day | 2020-09-28 07:00 | 2021-01-31 17:00 | [12 empty] | 1 | 7 | fGYbpPuXCkObkktm18fQ+w | otS1P85kF0ufxqOKSzwphw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2 | 41904260 | 41904239 | Enabling - Over Tracks |  |  |  |  | day | 2020-02-24 07:00 | 2023-06-15 17:00 | [12 empty] | 1 | 4 | jrqJ1+mj5UWE2ezgvMLB8A | sycKPI8q4EaFiuMDlAky2A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.1 | 41904448 | 41904260 | Track Closures | 7 |  |  |  | day | 2020-06-27 07:00 | 2021-04-29 17:00 | [12 empty] | 0 | 5 | OC4bVS02bkiOROnachhz4Q | jrqJ1+mj5UWE2ezgvMLB8A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.1.1 | 41904780 | 41904448 | CMP 05 | 46 |  |  |  | day | 2020-06-27 07:00 | 2021-04-29 17:00 | [12 empty] | 0 | 6 | TR3LxcQoME+6f8c/yf2lFw | OC4bVS02bkiOROnachhz4Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.1.2 | 41904787 | 41904448 | CMP 09 | 34 |  |  |  | day | [14 empty] | 1 | 6 | kXPrNtJRmUWQTYquHc4xlw | OC4bVS02bkiOROnachhz4Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2 | 41904502 | 41904260 | CMP-6 - Emergency Egress | 13 |  |  |  | day | 2021-06-14 07:00 | 2023-06-15 17:00 | [12 empty] | 1 | 5 | emZfp3Cr806C8ZnbWl6ASA | jrqJ1+mj5UWE2ezgvMLB8A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.1 | 41905197 | 41904502 | Enabling - Amtrak Scope |  |  |  |  | day | [14 empty] | 0 | 6 | h7575kM1XU6ncVuHSn9bxw | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.2 | 41905198 | 41904502 | Pave - Base / Binder Coat #1&2 - Weekend Shift |  |  |  |  | day | 2021-06-14 07:00 | 2021-09-24 17:00 | [12 empty] | 1 | 6 | KAKbXlE+mU2tYR4dm1EwbA | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.3 | 41905297 | 41904502 | Pave - Base / Binder Coat #2 - Weekend Shift |  |  |  |  | day | [14 empty] | 2 | 6 | bUYKE7yTOE6WEO1JQGd3aQ | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.4 | 41905199 | 41904502 | Pave - Top Coat #3 - Weekend Shift | 39 |  |  |  | day | 2021-10-11 07:00 | 2021-11-20 17:00 | [12 empty] | 3 | 6 | xnoPG+TWQEuDlfAa9PLS/A | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.5 | 41905200 | 41904502 | Gates 1 2 4 - Standard 5d Work Week | 3 |  |  |  | day | 2022-08-29 07:00 | 2023-05-19 17:00 | [12 empty] | 4 | 6 | bLcb9cHyBU2cOk0JmOfQBQ | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.6 | 41905201 | 41904502 | Misc | 1 |  |  |  | day | 2021-12-29 07:00 | 2023-06-15 17:00 | [12 empty] | 5 | 6 | eArKYbStSkWP6tUBxao3Mw | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.7 | 41904773 | 41904502 | CMP 6E | 5 |  |  |  | day | [14 empty] | 6 | 6 | 14Sr15+AdEWC75A+R5cJ1Q | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.8 | 41904774 | 41904502 | CMP 6D | 41 |  |  |  | day | [14 empty] | 7 | 6 | BMIbZIDt1kS8oFLV8Rv/Jw | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.9 | 41904775 | 41904502 | CMP 6C |  |  |  |  | day | [14 empty] | 8 | 6 | YHM8Fxz66EyunurUgnvBpw | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.10 | 41904776 | 41904502 | CMP 6B |  |  |  |  | day | [14 empty] | 9 | 6 | 7weZdntM5UG79rKlOtuIfg | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.11 | 41904777 | 41904502 | CMP 6A |  |  |  |  | day | [14 empty] | 10 | 6 | cd495sTP40azJkEyzE/z7Q | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.12 | 41904781 | 41904502 | CMP 6END |  |  |  |  | day | [14 empty] | 11 | 6 | iC0attygp0uxgGomw9Hksw | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.13 | 41904778 | 41904502 | Gates and Platform | 43 |  |  |  | day | [14 empty] | 12 | 6 | C2sD999iJkCGv53bvojXeA | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.14 | 41904779 | 41904502 | WP | 33 |  |  |  | day | [14 empty] | 13 | 6 | GlT8mNKbQ0iWfd7OvDsm+Q | emZfp3Cr806C8ZnbWl6ASA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.2.14.1 | 41905024 | 41904779 | Submittals | 9 |  |  |  | day | [14 empty] | 0 | 7 | 3tZ7R0iLd02NqRdvGidUCw | GlT8mNKbQ0iWfd7OvDsm+Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3 | 41904500 | 41904260 | Column Preparation (Decap, Survey, Prepare Steel) | 35 |  |  |  | day | 2020-02-24 07:00 | 2021-09-27 17:00 | [12 empty] | 2 | 5 | gwNvCrysrka7Nge0EKiBxA | jrqJ1+mj5UWE2ezgvMLB8A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.1 | 41904763 | 41904500 | 2024-01-02 | 13 |  |  |  | day | 2020-02-24 07:00 | 2020-03-11 17:00 | [12 empty] | 0 | 6 | KIXmarWQEEiw7NLeD3ffqw | gwNvCrysrka7Nge0EKiBxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.2 | 41904758 | 41904500 | 2024-11-13 | 30 |  |  |  | day | 2020-03-11 07:00 | 2020-03-12 17:00 | [12 empty] | 1 | 6 | gYJiTpmZH0eCe72KOE6Dmg | gwNvCrysrka7Nge0EKiBxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.3 | 41904759 | 41904500 | 2024-03-04 | 47 |  |  |  | day | 2020-02-26 07:00 | 2020-03-13 17:00 | [12 empty] | 2 | 6 | lw6eDWeX3kuEuV0AJF6FSg | gwNvCrysrka7Nge0EKiBxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.4 | 41904761 | 41904500 | 2024-07-08 |  |  |  |  | day | 2020-03-02 07:00 | 2020-03-03 17:00 | [12 empty] | 3 | 6 | hu2bmjBN7ki2WGZKP2nRfQ | gwNvCrysrka7Nge0EKiBxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.5 | 41904760 | 41904500 | 2024-05-06 |  |  |  |  | day | 2020-03-01 07:00 | 2020-03-02 17:00 | [12 empty] | 4 | 6 | XpyQ6qgv10iBRCXdt7qYSA | gwNvCrysrka7Nge0EKiBxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.6 | 41904762 | 41904500 | 2024-09-10 | 13 |  |  |  | day | 2020-03-03 07:00 | 2020-03-04 17:00 | [12 empty] | 5 | 6 | chLn9sC+2k2PxBnm8jL6ig | gwNvCrysrka7Nge0EKiBxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.7 | 41905257 | 41904500 | F and C Line - Rework Existing Steel | 22 |  |  |  | day | 2021-04-07 07:00 | 2021-09-27 17:00 | [12 empty] | 6 | 6 | JHXSw/ZQoEyNpkdVrvS94Q | gwNvCrysrka7Nge0EKiBxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.7.1 | 41905258 | 41905257 | F Line |  |  |  |  | day | 2021-04-07 07:00 | 2021-09-27 17:00 | [12 empty] | 0 | 7 | 7hLDzqle6E6xBlGSoZCSkQ | JHXSw/ZQoEyNpkdVrvS94Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.7.1.1 | 41905260 | 41905258 | Bus Terminal +49' |  |  |  |  | day | 2021-04-07 07:00 | 2021-09-27 17:00 | [12 empty] | 0 | 8 | nzRh3K6un0eLNJPeXNbX5w | 7hLDzqle6E6xBlGSoZCSkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.7.1.1.1 | 41905427 | 41905260 | Raduis Steel Conflict |  |  |  |  | day | 2021-06-28 07:00 | 2021-08-20 17:00 | [12 empty] | 0 | 9 |  | nzRh3K6un0eLNJPeXNbX5w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.7.1.2 | 41905261 | 41905258 | P1 +74.5' | 44 |  |  |  | day | [14 empty] | 1 | 8 | 7yEf5ILpGEus/uT72klb/g | 7hLDzqle6E6xBlGSoZCSkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.7.2 | 41905259 | 41905257 | C Line | 17 |  |  |  | day | 2021-08-30 07:00 | 2021-09-21 17:00 | [12 empty] | 1 | 7 | XqGQBceTMU2NSbpXM3p/aQ | JHXSw/ZQoEyNpkdVrvS94Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.7.2.1 | 41905262 | 41905259 | Bus Terminal +49' | 46 |  |  |  | day | 2021-08-30 07:00 | 2021-09-16 17:00 | [12 empty] | 0 | 8 | hxcn7KbxlkOGYIpK4AsM+A | XqGQBceTMU2NSbpXM3p/aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.3.7.2.2 | 41905263 | 41905259 | P1 +74.5' |  |  |  |  | day | 2021-09-13 07:00 | 2021-09-21 17:00 | [12 empty] | 1 | 8 | /xzHr87Ps0q0X1WQKFal4A | XqGQBceTMU2NSbpXM3p/aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4 | 41904379 | 41904260 | CMP-5 - Track Work | 25 |  |  |  | day | 2020-05-26 07:00 | 2021-05-21 17:00 | [12 empty] | 3 | 5 | 05Yf4gGylUmhjIBfOsyhWg | jrqJ1+mj5UWE2ezgvMLB8A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.1 | 41904703 | 41904379 | Headhouse Modifications - CMP-5G | 24 |  |  |  | day | 2020-10-08 07:00 | 2021-01-29 17:00 | [12 empty] | 0 | 6 | QxdIF+Pa40GkkOhQ5ffj/Q | 05Yf4gGylUmhjIBfOsyhWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.1.1 | 41904887 | 41904703 | Storm Drainage Under Headhouse Platform | 44 |  |  |  | day | [14 empty] | 0 | 7 | Olmozd8K1E6TFNj0Vi+rag | QxdIF+Pa40GkkOhQ5ffj/Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.1.2 | 41904812 | 41904703 | CMP-5B - Headhouse Doors/Entrance (Work Hours Mon-Fri 8:00 pm to 4:30 am) |  |  |  |  | day | 2020-10-08 07:00 | 2021-01-29 17:00 | [12 empty] | 1 | 7 | 37KHPdoeCkWdy/zUXyCZng | QxdIF+Pa40GkkOhQ5ffj/Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.1.2.1 | 41905252 | 41904812 | Change Design | 28 |  |  |  | day | 2021-01-11 07:00 | 2021-01-29 17:00 | [12 empty] | 0 | 8 | 8lpn/X5VMUOHHv+nXRsTHg | 37KHPdoeCkWdy/zUXyCZng | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.1.3 | 41904872 | 41904703 | CMP-5G - Headhouse Interior | 14 |  |  |  | day | [14 empty] | 2 | 7 | KeJorPrxyk2uJyZ5t9Z96Q | QxdIF+Pa40GkkOhQ5ffj/Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.2 | 41904605 | 41904379 | Tracks 1&2 / Column Line G |  |  |  |  | day | 2020-05-26 07:00 | 2021-04-06 17:00 | [12 empty] | 1 | 6 | f7oyh7KMnkWP+ZFZGxCVSQ | 05Yf4gGylUmhjIBfOsyhWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.2.1 | 41904841 | 41904605 | 1+ 2 - Signal Relocations and Track & Foundation Removal | 0 |  |  |  | day | 2020-05-26 07:00 | 2020-06-28 17:00 | [12 empty] | 0 | 7 | zVNqZZ6VKEeJXOC6htyRWQ | f7oyh7KMnkWP+ZFZGxCVSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.2.2 | 41905019 | 41904605 | 1+ 2 - OCS Relocation | 24 |  |  |  | day | 2020-06-09 07:00 | 2020-07-12 17:00 | [12 empty] | 1 | 7 | QMhSElznRk2UCVGDNd+eGw | f7oyh7KMnkWP+ZFZGxCVSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.2.3 | 41905073 | 41904605 | 1+ 2 - Pre-Foundation Scope - Demo, MEPs | 6 |  |  |  | day | 2020-07-21 07:00 | 2020-08-28 17:00 | [12 empty] | 2 | 7 | q2P1+TujKECzVZxfQX12og | f7oyh7KMnkWP+ZFZGxCVSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.2.4 | 41905008 | 41904605 | 1+ 2 - Pile Upgrade (G29 & G30.3 Modifications) | 8 |  |  |  | day | 2020-09-14 07:00 | 2021-01-26 17:00 | [12 empty] | 3 | 7 | xIFhUsVefUux6T0kVQ1mig | f7oyh7KMnkWP+ZFZGxCVSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.2.5 | 41905074 | 41904605 | 1+ 2 - Post-Foundation Scope - Demo, MEPs | 23 |  |  |  | day | 2021-02-22 07:00 | 2021-03-09 17:00 | [12 empty] | 4 | 7 | DPj9D0wZ7EinODxoZG90nA | f7oyh7KMnkWP+ZFZGxCVSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.2.6 | 41905195 | 41904605 | 2024-01-02 | 0 |  |  |  | day | 2020-12-14 07:00 | 2020-12-14 17:00 | [12 empty] | 5 | 7 | y9uWOLys1066dRP6cCJDKQ | f7oyh7KMnkWP+ZFZGxCVSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.2.7 | 41905009 | 41904605 | 1+ 2 - Track Infill | 43 |  |  |  | day | 2021-03-29 07:00 | 2021-04-06 17:00 | [12 empty] | 6 | 7 | vfIMkDs8e0KyLhz7ZLLK8g | f7oyh7KMnkWP+ZFZGxCVSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.3 | 41904609 | 41904379 | Tracks 3&4 / Column Line F | 7 |  |  |  | day | 2020-06-02 07:00 | 2021-03-12 17:00 | [12 empty] | 2 | 6 | SLSBoIdTyEeuSWYtvUzPWg | 05Yf4gGylUmhjIBfOsyhWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.3.1 | 41904844 | 41904609 | 3 + 4 - Signal Relocations and Track & Foundation Removal | 23 |  |  |  | day | 2020-06-02 07:00 | 2020-07-19 17:00 | [12 empty] | 0 | 7 | NPU00KWjwEec6JFrIvuRIg | SLSBoIdTyEeuSWYtvUzPWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.3.2 | 41905032 | 41904609 | 3 + 4 - OCS Relocation |  |  |  |  | day | 2020-07-19 07:00 | 2020-07-26 17:00 | [12 empty] | 1 | 7 | q+XAgfgh00ClDyNfl2lzag | SLSBoIdTyEeuSWYtvUzPWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.3.3 | 41905076 | 41904609 | 3 + 4 - Pre-Foundation Scope - Demo, MEPs | 16 |  |  |  | day | 2020-08-24 07:00 | 2020-09-09 17:00 | [12 empty] | 2 | 7 | hVGfWyLSOU+YHQ2PbqW16Q | SLSBoIdTyEeuSWYtvUzPWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.3.4 | 41905036 | 41904609 | 3 + 4 - Platform Foundations/Walls | 7 |  |  |  | day | 2020-10-09 07:00 | 2021-01-20 17:00 | [12 empty] | 3 | 7 | Tov4Of4/OES0k7Q1VKnoig | SLSBoIdTyEeuSWYtvUzPWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.3.5 | 41905077 | 41904609 | 3 + 4 - Post-Foundation Scope - Demo, MEPs |  |  |  |  | day | 2021-01-11 07:00 | 2021-03-09 17:00 | [12 empty] | 4 | 7 | rmKAqEqoiUakSIxlWeIBHQ | SLSBoIdTyEeuSWYtvUzPWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.3.6 | 41904845 | 41904609 | 3 + 4 - Track Infill and Canopy Scope | 34 |  |  |  | day | 2021-03-08 07:00 | 2021-03-12 17:00 | [12 empty] | 5 | 7 | gNfvc7XqXEeSq1bXy/CAvA | SLSBoIdTyEeuSWYtvUzPWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.4 | 41904610 | 41904379 | Tracks 5&6 / Column Line E | 32 |  |  |  | day | 2020-07-15 07:00 | 2021-03-11 17:00 | [12 empty] | 3 | 6 | V3f/TUezlUazBY0g3xpOMg | 05Yf4gGylUmhjIBfOsyhWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.4.1 | 41904846 | 41904610 | 5 + 6 - Signal Relocations and Track & Foundation Removal | 4 |  |  |  | day | 2020-07-15 07:00 | 2020-08-02 17:00 | [12 empty] | 0 | 7 | J2wAuWWbokaZOZNIAnzEpA | V3f/TUezlUazBY0g3xpOMg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.4.2 | 41905033 | 41904610 | 5 + 6 - OCS Relocation | 41 |  |  |  | day | 2020-08-02 07:00 | 2020-08-09 17:00 | [12 empty] | 1 | 7 | Mlm2GTWJmkKlkRpHxLZrbQ | V3f/TUezlUazBY0g3xpOMg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.4.3 | 41905078 | 41904610 | 5 + 6 - Pre-Foundation Scope - Demo, MEPs |  |  |  |  | day | 2020-08-24 07:00 | 2020-09-18 17:00 | [12 empty] | 2 | 7 | ero2IyQqQk2V0n4m8FyEQg | V3f/TUezlUazBY0g3xpOMg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.4.4 | 41905194 | 41904610 | 2024-05-06 | 40 |  |  |  | day | 2020-08-17 07:00 | 2021-01-20 17:00 | [12 empty] | 3 | 7 | Lp+wUOT2N0iKEFn1Bha60Q | V3f/TUezlUazBY0g3xpOMg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.4.5 | 41904873 | 41904610 | 5 + 6 - Platform Foundations/Walls and Elevator Pit | 27 |  |  |  | day | 2020-10-27 07:00 | 2020-12-10 17:00 | [12 empty] | 4 | 7 | 0c11GWPAa0mpemlWkdq0Rg | V3f/TUezlUazBY0g3xpOMg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.4.6 | 41905079 | 41904610 | 5 + 6 - Post-Foundation Scope - Demo, MEPs |  |  |  |  | day | 2021-02-01 07:00 | 2021-03-08 17:00 | [12 empty] | 5 | 7 | 7SfHMlqjWU2Uk+JIA9Md8g | V3f/TUezlUazBY0g3xpOMg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.4.7 | 41904847 | 41904610 | 5 + 6 - Track Infill and Canopy Scope | 8 |  |  |  | day | 2021-02-17 07:00 | 2021-03-11 17:00 | [12 empty] | 6 | 7 | dFTd9S935UWilXlD1yZmYA | V3f/TUezlUazBY0g3xpOMg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.5 | 41904611 | 41904379 | Tracks 7&8 / Column Line D |  |  |  |  | day | 2020-07-27 07:00 | 2021-03-08 17:00 | [12 empty] | 4 | 6 | RhsosNFDCUm8ybwHe0bWDw | 05Yf4gGylUmhjIBfOsyhWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.5.1 | 41904848 | 41904611 | 7 + 8 - Signal Relocations and Track & Foundation Removal |  |  |  |  | day | 2020-07-27 07:00 | 2020-10-04 17:00 | [12 empty] | 0 | 7 | zBjuEYNKTkumXOGMeLJG9A | RhsosNFDCUm8ybwHe0bWDw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.5.2 | 41905034 | 41904611 | 7 + 8 - OCS Relocation | 33 |  |  |  | day | 2020-10-04 07:00 | 2020-10-11 17:00 | [12 empty] | 1 | 7 | wSsGDL4tfE+bhReWd8B9vA | RhsosNFDCUm8ybwHe0bWDw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.5.3 | 41905080 | 41904611 | 7 + 8 - Pre-Foundation Scope - Demo, MEPs | 32 |  |  |  | day | 2020-10-13 07:00 | 2020-10-21 17:00 | [12 empty] | 2 | 7 | w5e2ZRwkH0KuiiQyjUenNg | RhsosNFDCUm8ybwHe0bWDw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.5.4 | 41905037 | 41904611 | 7 + 8 - Platform Foundations/Walls | 47 |  |  |  | day | 2020-10-22 07:00 | 2020-12-10 17:00 | [12 empty] | 3 | 7 | AmHJltqv3U2t/bXl7QMcsg | RhsosNFDCUm8ybwHe0bWDw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.5.5 | 41905081 | 41904611 | 7 + 8 - Post-Foundation Scope - Demo, MEPs | 22 |  |  |  | day | 2021-01-28 07:00 | 2021-03-08 17:00 | [12 empty] | 4 | 7 | 9fEg2Mi/DUeJJh4knuQDrA | RhsosNFDCUm8ybwHe0bWDw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.5.6 | 41904849 | 41904611 | 7 + 8 - Track Infill and Canopy Scope | 23 |  |  |  | day | 2021-02-16 07:00 | 2021-03-06 17:00 | [12 empty] | 5 | 7 | e3GClTAIFU+SIZ031keN8g | RhsosNFDCUm8ybwHe0bWDw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.6 | 41904612 | 41904379 | Tracks 9&10 / Column Line C | 36 |  |  |  | day | 2020-07-31 07:00 | 2021-03-08 17:00 | [12 empty] | 5 | 6 | WLrfgDPxS0GXJz2d1B+mkQ | 05Yf4gGylUmhjIBfOsyhWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.6.1 | 41904850 | 41904612 | 9 + 10 - Signal Relocations and Track & Foundation Removal | 34 |  |  |  | day | 2020-07-31 07:00 | 2020-10-18 17:00 | [12 empty] | 0 | 7 | Y/117v/Twk69fsjcUqmPqQ | WLrfgDPxS0GXJz2d1B+mkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.6.2 | 41905035 | 41904612 | 9 + 10 - OCS Relocation | 43 |  |  |  | day | 2020-10-18 07:00 | 2020-10-25 17:00 | [12 empty] | 1 | 7 | OQd1VWMuSU2K6Nn5gDvU3w | WLrfgDPxS0GXJz2d1B+mkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.6.3 | 41905082 | 41904612 | 9 + 10 - Pre-Foundation Scope - Demo, MEPs | 39 |  |  |  | day | 2020-10-26 07:00 | 2020-11-06 17:00 | [12 empty] | 2 | 7 | jbfkXSecVEGwCVhWWcOaQQ | WLrfgDPxS0GXJz2d1B+mkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.6.4 | 41905038 | 41904612 | 9 + 10 - Platform Foundations/Walls | 21 |  |  |  | day | [14 empty] | 3 | 7 | TnZuYWIWxU+Ge+LXJMUrPQ | WLrfgDPxS0GXJz2d1B+mkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.6.5 | 41905083 | 41904612 | 9 + 10 - Post-Foundation Scope - Demo, MEPs | 26 |  |  |  | day | 2020-11-16 07:00 | 2021-03-08 17:00 | [12 empty] | 4 | 7 | NiImIpxNVkKZ3yB1CvUuWw | WLrfgDPxS0GXJz2d1B+mkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.6.6 | 41904851 | 41904612 | 9 + 10 - GMP- 5F - Track Infill and Canopy Scope |  |  |  |  | day | 2021-02-08 07:00 | 2021-03-06 17:00 | [12 empty] | 5 | 7 | zDfw1l7Fmkmkygb5IpWCpw | WLrfgDPxS0GXJz2d1B+mkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.7 | 41904606 | 41904379 | Tracks 11-13 / Column Line B | 0 |  |  |  | day | 2020-08-17 07:00 | 2021-05-21 17:00 | [12 empty] | 6 | 6 | 6o9JMUecAECjlewTAbPn7Q | 05Yf4gGylUmhjIBfOsyhWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.7.1 | 41904842 | 41904606 | Signal Relocations and Track & Foundation Removal |  |  |  |  | day | 2020-08-17 07:00 | 2020-11-13 17:00 | [12 empty] | 0 | 7 | 3UqGmFjXSEyhpgT6OyLg0Q | 6o9JMUecAECjlewTAbPn7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.7.2 | 41905031 | 41904606 | OCS Relocation | 36 |  |  |  | day | 2020-12-10 07:00 | 2020-12-11 17:00 | [12 empty] | 1 | 7 | TC73NBiX7ke/vB++vnnbEQ | 6o9JMUecAECjlewTAbPn7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.7.3 | 41904843 | 41904606 | CMP-5B - Track Infill and Canopy Scope | 46 |  |  |  | day | 2021-01-23 07:00 | 2021-05-16 17:00 | [12 empty] | 2 | 7 | r6GLZWPzTUehgTj1X69QsA | 6o9JMUecAECjlewTAbPn7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.7.3.1 | 41905244 | 41904843 | Hoteling | 13 |  |  |  | day | 2021-01-23 07:00 | 2021-05-16 17:00 | [12 empty] | 0 | 8 | LM4wJi2Y/Ey7IQngFptwMg | r6GLZWPzTUehgTj1X69QsA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.7.3.1.1 | 41905246 | 41905244 | 11+12 | 2 |  |  |  | day | 2021-01-23 07:00 | 2021-05-16 17:00 | [12 empty] | 0 | 9 | p3/mx9YBcEmax8Kt1AOx+g | LM4wJi2Y/Ey7IQngFptwMg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.7.3.1.2 | 41905247 | 41905244 | 13 | 0 |  |  |  | day | 2021-01-23 07:00 | 2021-03-15 17:00 | [12 empty] | 1 | 9 | ITEfEQdkOEuwdp7dqziqTA | LM4wJi2Y/Ey7IQngFptwMg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.7.3.2 | 41905245 | 41904843 | Other | 4 |  |  |  | day | 2021-04-20 07:00 | 2021-04-29 17:00 | [12 empty] | 1 | 8 | XRawqMg6ZUqh0YBRRWTTEg | r6GLZWPzTUehgTj1X69QsA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.7.4 | 41904871 | 41904606 | CMP-5E - Relocate Dispatch Trailer | 25 |  |  |  | day | 2021-05-21 07:00 | 2021-05-21 17:00 | [12 empty] | 3 | 7 | IcODZ/kKtUmRJFcv13Manw | 6o9JMUecAECjlewTAbPn7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.8 | 41905248 | 41904379 | Fire Protection - Track Work | 13 |  |  |  | day | 2020-11-02 07:00 | 2021-02-09 17:00 | [12 empty] | 7 | 6 | GFlkLCq4aEmqoVuB9KgWcg | 05Yf4gGylUmhjIBfOsyhWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.9 | 41904613 | 41904379 | CMP-5H - Demise Tower Work Zone - Enabling Phase H |  |  |  |  | day | 2021-01-25 07:00 | 2021-03-19 17:00 | [12 empty] | 8 | 6 | 2St79o6+mkG9CQaqRKklOw | 05Yf4gGylUmhjIBfOsyhWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.9.1 | 41905254 | 41904613 | 36 Line Barrier |  |  |  |  | day | 2021-01-25 07:00 | 2021-03-19 17:00 | [12 empty] | 0 | 7 | en9pChP4akmr1bHXnJKHvQ | 2St79o6+mkG9CQaqRKklOw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.4.9.2 | 41905255 | 41904613 | Barrier A | 8 |  |  |  | day | 2021-03-04 07:00 | 2021-03-12 17:00 | [12 empty] | 1 | 7 | 6oIs9Gk9BkW9dvMVa3h4Ww | 2St79o6+mkG9CQaqRKklOw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5 | 41904444 | 41904260 | CMP-12A - Selective Terminal Facade Demo (M-F 8:00pm to 4:30am) | 14 |  |  |  | day | 2020-07-27 07:00 | 2020-09-29 17:00 | [12 empty] | 4 | 5 | dX6xWU8xcE+km0QzFIKSNQ | jrqJ1+mj5UWE2ezgvMLB8A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5.1 | 41904795 | 41904444 | J.5 - H Line - Crane - Atlantic | 14 |  |  |  | day | 2020-08-24 07:00 | 2020-08-28 17:00 | [12 empty] | 0 | 6 | PQGoFJgTX0iXg3W4ytscyQ | dX6xWU8xcE+km0QzFIKSNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5.2 | 41904788 | 41904444 | H - F.5 Line - Basket 1 - Tracks 1+2 | 25 |  |  |  | day | 2020-07-27 07:00 | 2020-08-24 17:00 | [12 empty] | 1 | 6 | dIcEfAa+QUOqhFY/NxQJQw | dX6xWU8xcE+km0QzFIKSNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5.3 | 41904789 | 41904444 | F.5 - E.5 Line - Basket 2 - Tracks 3+4 |  |  |  |  | day | 2020-07-30 07:00 | 2020-08-25 17:00 | [12 empty] | 2 | 6 | 1AlW98GSdEyFcX/G9Fsbww | dX6xWU8xcE+km0QzFIKSNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5.4 | 41904790 | 41904444 | E.5 - D.5 Line - Basket 3 - Tracks 5+6 |  |  |  |  | day | 2020-08-05 07:00 | 2020-08-26 17:00 | [12 empty] | 3 | 6 | tMkZlc6mrEahvyNeUerKFA | dX6xWU8xcE+km0QzFIKSNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5.5 | 41904791 | 41904444 | D.5 - C.5 Line - Basket 4 - Tracks 7+8 |  |  |  |  | day | 2020-08-10 07:00 | 2020-08-27 17:00 | [12 empty] | 4 | 6 | 2yQFyMDjgUGd/isCUwcGRQ | dX6xWU8xcE+km0QzFIKSNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5.6 | 41904792 | 41904444 | C.5 - B.5 Line - Basket 5 - Tracks 9+10 |  |  |  |  | day | 2020-08-13 07:00 | 2020-09-01 17:00 | [12 empty] | 5 | 6 | m9Mq0Ce1k0yIu58ynq590A | dX6xWU8xcE+km0QzFIKSNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5.7 | 41904794 | 41904444 | B.5 - A.6 Line - Basket 6 - Tracks 11+12 | 48 |  |  |  | day | 2020-09-02 07:00 | 2020-09-03 17:00 | [12 empty] | 6 | 6 | qBm7PcrISEyoP47y3UWy5w | dX6xWU8xcE+km0QzFIKSNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5.8 | 41904796 | 41904444 | 18.5 - 19 Line - Basket 7 - Dorchester | 31 |  |  |  | day | 2020-09-02 07:00 | 2020-09-10 17:00 | [12 empty] | 7 | 6 | BcWnSdDv2Uq3PgEE+5Gbng | dX6xWU8xcE+km0QzFIKSNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5.9 | 41904799 | 41904444 | 17.5 - 18.5 Line - Crane - Dorchester | 3 |  |  |  | day | 2020-09-08 07:00 | 2020-09-17 17:00 | [12 empty] | 8 | 6 | 2Lr/BkDVa0So9p/JRbYVfQ | dX6xWU8xcE+km0QzFIKSNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5.10 | 41904797 | 41904444 | 17 - 17.5 Line - Basket 8 - Dorchester | 29 |  |  |  | day | 2020-09-18 07:00 | 2020-09-29 17:00 | [12 empty] | 9 | 6 | 7NjKrMv6KEG0WD8YNYYDdQ | dX6xWU8xcE+km0QzFIKSNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.2.5.11 | 41904798 | 41904444 | 16 - 17 Line - Basket 9 - Dorchester |  |  |  |  | day | [14 empty] | 10 | 6 | vXGfbE/HZkuSHr+qhWubtQ | dX6xWU8xcE+km0QzFIKSNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3 | 41904285 | 41904239 | Enabling - Dorchester Ave - Pre Tower Work Zone | 22 |  |  |  | day | 2020-01-27 07:00 | 2023-02-22 17:00 | [12 empty] | 2 | 4 | 7+QQ1RxugkaDubTUDmTlvQ | sycKPI8q4EaFiuMDlAky2A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.1 | 41904431 | 41904285 | CMP-3 Dorchester Ave Staging Area (Standard Hours) | 38 |  |  |  | day | 2020-03-01 07:00 | 2020-03-09 17:00 | [12 empty] | 0 | 5 | eqc8JfCnokC7VwLTu3PRHA | 7+QQ1RxugkaDubTUDmTlvQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.1.1 | 41904678 | 41904431 | CMP-3A | 44 |  |  |  | day | 2020-03-02 07:00 | 2020-03-06 17:00 | [12 empty] | 0 | 6 | 1Dks5DryNEmB2Oh6DhCntw | eqc8JfCnokC7VwLTu3PRHA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.1.1.1 | 41904996 | 41904678 | Work Plan- CMP 3A | 14 |  |  |  | day | [14 empty] | 0 | 7 | 2j1iK6HvXUSM/tSjH8AtBA | 1Dks5DryNEmB2Oh6DhCntw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.1.1.2 | 41905006 | 41904678 | Construction- CMP 3A | 42 |  |  |  | day | 2020-03-02 07:00 | 2020-03-06 17:00 | [12 empty] | 1 | 7 | HcTK+1w1tkSFfp/vfy1zag | 1Dks5DryNEmB2Oh6DhCntw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.1.2 | 41904679 | 41904431 | CMP-3B | 28 |  |  |  | day | [14 empty] | 1 | 6 | ZUJGsg2OF0GNIW8QymHLlw | eqc8JfCnokC7VwLTu3PRHA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.1.2.1 | 41904997 | 41904679 | Work Plan- CMP 3B | 35 |  |  |  | day | [14 empty] | 0 | 7 | Fg3Kfq5Y+k6/yoi5ZcngZw | ZUJGsg2OF0GNIW8QymHLlw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.1.2.2 | 41905007 | 41904679 | Construction- CMP 3B | 12 |  |  |  | day | [14 empty] | 1 | 7 | 8bzZGbienEGXOkXY8BDDOg | ZUJGsg2OF0GNIW8QymHLlw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2 | 41904378 | 41904285 | CMP-8 Dorchester Ave Work Zone (Standard Hours) |  |  |  |  | day | 2020-01-27 07:00 | 2023-02-22 17:00 | [12 empty] | 1 | 5 | dGrivra9v0GjXpBJg5AqsQ | 7+QQ1RxugkaDubTUDmTlvQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.1 | 41904698 | 41904378 | CMP-8A&B |  |  |  |  | day | 2020-01-27 07:00 | 2021-11-05 17:00 | [12 empty] | 0 | 6 | tHDYEPMIC0uyPZkvJTfMNA | dGrivra9v0GjXpBJg5AqsQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.1.1 | 41905022 | 41904698 | Demo Canopy | 21 |  |  |  | day | 2020-05-22 07:00 | 2020-07-03 17:00 | [12 empty] | 0 | 7 | CW9ij9apcUSBpmIQ0ZdBcQ | tHDYEPMIC0uyPZkvJTfMNA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.1.2 | 41905023 | 41904698 | Demo / Piles Prep | 27 |  |  |  | day | 2020-07-06 07:00 | 2021-05-25 17:00 | [12 empty] | 1 | 7 | phU9ABz6MESKWfB2ZsJzzw | tHDYEPMIC0uyPZkvJTfMNA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.1.3 | 41905387 | 41904698 | USPS - Easement Closure |  |  |  |  | day | 2021-06-28 07:00 | 2021-11-05 17:00 | [12 empty] | 2 | 7 | R/aO5hGl0ECgvEKJLMiORg | tHDYEPMIC0uyPZkvJTfMNA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2 | 41904699 | 41904378 | CMP-8C - Loading Dock |  |  |  |  | day | 2020-05-18 07:00 | 2023-02-22 17:00 | [12 empty] | 1 | 6 | XAZF6+8NTk6p3qNUj5HsCg | dGrivra9v0GjXpBJg5AqsQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.1 | 41905055 | 41904699 | Test Pits - AA-30 Tank | 44 |  |  |  | day | 2020-05-18 07:00 | 2020-07-01 17:00 | [12 empty] | 0 | 7 | wELC7mQ6HkeE5N2i3ipzLg | XAZF6+8NTk6p3qNUj5HsCg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.2 | 41905056 | 41904699 | Test Pits - A.3-31 | 5 |  |  |  | day | 2020-07-02 07:00 | 2020-07-10 17:00 | [12 empty] | 1 | 7 | VzAPyjOA3UupJcWlePsIwg | XAZF6+8NTk6p3qNUj5HsCg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.3 | 41905028 | 41904699 | AA-30 | 27 |  |  |  | day | 2020-08-17 07:00 | 2020-10-02 17:00 | [12 empty] | 2 | 7 | CItdPCChAke6OgbF4rhBBA | XAZF6+8NTk6p3qNUj5HsCg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.4 | 41905058 | 41904699 | A.3-31 |  |  |  |  | day | 2020-09-01 07:00 | 2020-10-30 17:00 | [12 empty] | 3 | 7 | t7fSZHGdlkKIOci71j7RxQ | XAZF6+8NTk6p3qNUj5HsCg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.5 | 41905029 | 41904699 | B-31 | 43 |  |  |  | day | 2020-06-16 07:00 | 2021-03-19 17:00 | [12 empty] | 4 | 7 | QG73i9OK5ku7K1laYtuRPA | XAZF6+8NTk6p3qNUj5HsCg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.6 | 41905030 | 41904699 | Service Building | 43 |  |  |  | day | 2020-10-23 07:00 | 2023-02-22 17:00 | [12 empty] | 5 | 7 | SV1QuE4eUEuYyDnFIbJ26g | XAZF6+8NTk6p3qNUj5HsCg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.6.1 | 41906218 | 41905030 | Structure | 19 |  |  |  | day | 2021-12-15 07:00 | 2022-02-18 17:00 | [12 empty] | 0 | 8 | KvPJPRCzeUSuhLpF6oAiWw | SV1QuE4eUEuYyDnFIbJ26g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.6.2 | 41906216 | 41905030 | Service Building Upperwork / Roof |  |  |  |  | day | 2022-03-15 07:00 | 2023-02-22 17:00 | [12 empty] | 1 | 8 | fsDWD0Bd6kGt3eqI6NZMZg | SV1QuE4eUEuYyDnFIbJ26g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.6.3 | 41906217 | 41905030 | Exterior |  |  |  |  | day | 2022-04-06 07:00 | 2022-06-06 17:00 | [12 empty] | 2 | 8 | fuCpsag5Z0anOnf47EFw4Q | SV1QuE4eUEuYyDnFIbJ26g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.6.4 | 41906219 | 41905030 | Interiors |  |  |  |  | day | 2021-09-03 07:00 | 2022-08-19 17:00 | [12 empty] | 3 | 8 | CH5UG8pJ0EK6qo6aA9HIVA | SV1QuE4eUEuYyDnFIbJ26g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.6.4.1 | 41906221 | 41906219 | A-30 Comeback | 24 |  |  |  | day | 2022-02-16 07:00 | 2022-05-11 17:00 | [12 empty] | 0 | 9 | mkFOGbDLI0i/cznvlJx9Zw | CH5UG8pJ0EK6qo6aA9HIVA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.3.2.2.6.4.2 | 41906220 | 41906219 | -- | 38 |  |  |  | day | 2021-09-03 07:00 | 2022-08-19 17:00 | [12 empty] | 1 | 9 | FGeZfDtt6k259w0ERFYDYg | CH5UG8pJ0EK6qo6aA9HIVA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4 | 41904286 | 41904239 | Enabling - Summer St - Pre Tower Work Zone |  |  |  |  | day | 2020-02-18 07:00 | 2021-12-02 17:00 | [12 empty] | 3 | 4 | PEJFfaQl2km9KnChWLp6SA | sycKPI8q4EaFiuMDlAky2A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1 | 41904430 | 41904286 | CMP-2 Summer St Staging Area (Standard Hours) |  |  |  |  | day | 2020-02-18 07:00 | 2021-12-02 17:00 | [12 empty] | 0 | 5 | UCdId0C7a06vQvtS8twwdg | PEJFfaQl2km9KnChWLp6SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.1 | 41904768 | 41904430 | CMP 2A - Curb Cuts |  |  |  |  | day | 2020-03-01 07:00 | 2020-03-06 17:00 | [12 empty] | 0 | 6 | hUainzXwQEGYj4D88UHmnA | UCdId0C7a06vQvtS8twwdg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.2 | 41904769 | 41904430 | CMP 2B - ADA Ramp | 12 |  |  |  | day | 2020-06-01 07:00 | 2020-07-21 17:00 | [12 empty] | 1 | 6 | icD1wSKP3Eq1rySGQwkIrg | UCdId0C7a06vQvtS8twwdg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.3 | 41904770 | 41904430 | CMP 2C - 12' Wall |  |  |  |  | day | 2020-02-18 07:00 | 2020-06-25 17:00 | [12 empty] | 2 | 6 | bQntbSeRVUyzs0aU+SbXfQ | UCdId0C7a06vQvtS8twwdg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.4 | 41904771 | 41904430 | CMP 2D - Ramp and Temp Sign | 2 |  |  |  | day | 2020-06-01 07:00 | 2020-08-14 17:00 | [12 empty] | 3 | 6 | Lx9f6uwR3024yqNYo9F9zQ | UCdId0C7a06vQvtS8twwdg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.4.1 | 41905051 | 41904771 | Permanent Ramp | 38 |  |  |  | day | 2020-06-08 07:00 | 2020-08-14 17:00 | [12 empty] | 0 | 7 | VKDiI2FTaUamSyZLZ2EaMQ | Lx9f6uwR3024yqNYo9F9zQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.4.2 | 41905052 | 41904771 | 245 Sign | 5 |  |  |  | day | 2020-06-01 07:00 | 2020-07-20 17:00 | [12 empty] | 1 | 7 | 7jRmDBlJU0asuOJp0uYmVA | Lx9f6uwR3024yqNYo9F9zQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.5 | 41904772 | 41904430 | CMP 2E - Fidelity Plaza |  |  |  |  | day | 2020-03-02 07:00 | 2021-12-02 17:00 | [12 empty] | 4 | 6 | 8cggoZFP5kWKLJgeoZt2hQ | UCdId0C7a06vQvtS8twwdg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.6 | 41904674 | 41904430 | CMP-2A | 26 |  |  |  | day | [14 empty] | 5 | 6 | Z2nvocGzkkajPXe1qtu0Kw | UCdId0C7a06vQvtS8twwdg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.6.1 | 41904998 | 41904674 | Work Plan- CMP 2A | 8 |  |  |  | day | [14 empty] | 0 | 7 | S+RtbRzZ+kihOUuRJObnrg | Z2nvocGzkkajPXe1qtu0Kw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.6.2 | 41905002 | 41904674 | Construction- CMP 2A | 36 |  |  |  | day | [14 empty] | 1 | 7 | kEuQaVPu7UO3xk5V5rLcvA | Z2nvocGzkkajPXe1qtu0Kw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.7 | 41904675 | 41904430 | CMP-2B |  |  |  |  | day | [14 empty] | 6 | 6 | OtO0neICzUaacs3Y2Gx78A | UCdId0C7a06vQvtS8twwdg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.7.1 | 41904999 | 41904675 | Work Plan- CMP 2B | 41 |  |  |  | day | [14 empty] | 0 | 7 | nfwqhJiWjkeYMXXcFGMY6Q | OtO0neICzUaacs3Y2Gx78A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.7.2 | 41905003 | 41904675 | Construction- CMP 2B | 43 |  |  |  | day | [14 empty] | 1 | 7 | k6JaDCZmh0uQ4I8kpP5mKA | OtO0neICzUaacs3Y2Gx78A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.8 | 41904676 | 41904430 | CMP-2C | 23 |  |  |  | day | [14 empty] | 7 | 6 | dum4xcFCLESQ95KeLZoKtA | UCdId0C7a06vQvtS8twwdg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.8.1 | 41905000 | 41904676 | Work Plan- CMP 2C | 14 |  |  |  | day | [14 empty] | 0 | 7 | LuzSlrzpxE2kyfO5Ju7LJw | dum4xcFCLESQ95KeLZoKtA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.8.2 | 41905004 | 41904676 | Construction- CMP 2C | 31 |  |  |  | day | [14 empty] | 1 | 7 | EA3N7w+cy02f97L0qEqLRw | dum4xcFCLESQ95KeLZoKtA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.9 | 41904677 | 41904430 | CMP-2D | 31 |  |  |  | day | [14 empty] | 8 | 6 | R+WQg4oaSUSOD6b3UHNa4w | UCdId0C7a06vQvtS8twwdg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.9.1 | 41905001 | 41904677 | Work Plan- CMP 2D | 23 |  |  |  | day | [14 empty] | 0 | 7 | GKD/2/YjAEaNPfYSHjKv2Q | R+WQg4oaSUSOD6b3UHNa4w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.1.9.2 | 41905005 | 41904677 | Construction- CMP 2D | 40 |  |  |  | day | [14 empty] | 1 | 7 | K8pEZZuLUU21mNG+a0E1mQ | R+WQg4oaSUSOD6b3UHNa4w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.2 | 41904432 | 41904286 | CMP-4 Tunnel Prep (Standard Hours) |  |  |  |  | day | 2020-09-10 07:00 | 2021-03-15 17:00 | [12 empty] | 1 | 5 | M0Tx6hse4kWOR30PFGtXGw | PEJFfaQl2km9KnChWLp6SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.2.1 | 41904680 | 41904432 | CMP-4 - Glory Hole (MEPs in Service Corridor Shown in Basement Schedule Section) |  |  |  |  | day | 2020-09-10 07:00 | 2021-01-04 17:00 | [12 empty] | 0 | 6 | iggJFmPO2kmZj7T6oY/vvA | M0Tx6hse4kWOR30PFGtXGw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.4.2.2 | 41904681 | 41904432 | CMP-4B - Service Corridor Temp Bridge | 11 |  |  |  | day | [14 empty] | 1 | 6 | vyp9vU3Tu02aTHOfgC15nQ | M0Tx6hse4kWOR30PFGtXGw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5 | 41904264 | 41904239 | Enabling - Tower Work Zone | 38 |  |  |  | day | 2020-02-26 07:00 | 2021-03-29 17:00 | [12 empty] | 4 | 4 | 7KAemoRVEkOTQDftp8qghQ | sycKPI8q4EaFiuMDlAky2A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.1 | 41904396 | 41904264 | Exisiting Platform (El +18.25') (Standard Hours) | 1 |  |  |  | day | 2020-09-08 07:00 | 2020-12-15 17:00 | [12 empty] | 0 | 5 | XuNvyoMxL06E3kTu8XES4Q | 7KAemoRVEkOTQDftp8qghQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.1.1 | 41904738 | 41904396 | For Construction Use | 2 |  |  |  | day | 2020-09-18 07:00 | 2020-12-15 17:00 | [12 empty] | 0 | 6 | ex9gIPUOaEOnXP0sOJFIDg | XuNvyoMxL06E3kTu8XES4Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.1.2 | 41904739 | 41904396 | Temp Generator for CTEC @ Dorcester Ave Staging |  |  |  |  | day | 2020-09-08 07:00 | 2020-11-13 17:00 | [12 empty] | 1 | 6 | DAPNv68Dmk2pbpmL+WHouQ | XuNvyoMxL06E3kTu8XES4Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.1.3 | 41904757 | 41904396 | 15kV Bus Terminal Power Feed | 36 |  |  |  | day | [14 empty] | 2 | 6 | u7XEvaXyD0aC1Jb3MQfLcQ | XuNvyoMxL06E3kTu8XES4Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2 | 41904397 | 41904264 | Existing Basement Headhouse (El +3.25') (Standard Hours) | 48 |  |  |  | day | 2020-02-26 07:00 | 2021-03-29 17:00 | [12 empty] | 1 | 5 | kF85TFpe3kClwM9BjJGHgQ | 7KAemoRVEkOTQDftp8qghQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1 | 41904793 | 41904397 | Basement Enabling | 16 |  |  |  | day | 2020-06-29 07:00 | 2020-10-05 17:00 | [12 empty] | 0 | 6 | 1DUnq0CC7Em5rWmC8Ai1sQ | kF85TFpe3kClwM9BjJGHgQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.1 | 41905059 | 41904793 | Submittals | 48 |  |  |  | day | 2020-06-29 07:00 | 2020-07-24 17:00 | [12 empty] | 0 | 7 | MQvbA8Kw20uP0HnMQNSCFQ | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.1.1 | 41905156 | 41905059 | Coordination Drawings | 1 |  |  |  | day | 2020-06-29 07:00 | 2020-06-29 17:00 | [12 empty] | 0 | 8 | swk0o60RoUKPY3F4zPj6jw | MQvbA8Kw20uP0HnMQNSCFQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.1.2 | 41905157 | 41905059 | MEP Submittals | 1 |  |  |  | day | 2020-06-29 07:00 | 2020-07-24 17:00 | [12 empty] | 1 | 8 | seRRboSj706GIwCTIK27jQ | MQvbA8Kw20uP0HnMQNSCFQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.2 | 41905060 | 41904793 | 01 - Amtrak Compressor Relocation (RFI 105, 330) | 27 |  |  |  | day | 2020-06-29 07:00 | 2020-09-18 17:00 | [12 empty] | 1 | 7 | 506CAm83bUWWR87sPuxjMA | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.2.1 | 41905158 | 41905060 | [220010-24] | 22 |  |  |  | day | 2020-06-29 07:00 | 2020-08-25 17:00 | [12 empty] | 0 | 8 | ggSKo/kRwkum2F6xBvD2+A | 506CAm83bUWWR87sPuxjMA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.3 | 41905061 | 41904793 | 02 - Demo West Wall of Compressor Room |  |  |  |  | day | 2020-08-19 07:00 | 2020-08-27 17:00 | [12 empty] | 2 | 7 | ICeWc17Zzk6cv2aoHdVTsA | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.4 | 41905062 | 41904793 | 03 - Demo AHU-5 and Associated Duct (RFI 115) | 31 |  |  |  | day | 2020-06-29 07:00 | 2020-08-11 17:00 | [12 empty] | 3 | 7 | 1r166GzW7k2Zbt+szV+ugg | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.5 | 41905063 | 41904793 | 04 - Demo WS Heat Pump in AV Room (RFI 331) | 32 |  |  |  | day | 2020-06-29 07:00 | 2020-07-06 17:00 | [12 empty] | 4 | 7 | svrAZLVYm0KBMzdrHinDVA | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.6 | 41905064 | 41904793 | 05 - Remediate Compressor Room Floor (RFI 135, 136, 105, ) |  |  |  |  | day | 2020-07-27 07:00 | 2020-09-18 17:00 | [12 empty] | 5 | 7 | oGnVqGpruEqLiOK91iabSQ | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.7 | 41905065 | 41904793 | 06 - Demo/Re-configure Fan F-36 (OA) |  |  |  |  | day | 2020-08-03 07:00 | 2020-09-01 17:00 | [12 empty] | 6 | 7 | h0zea8LdP0ahPb9T+nVwTA | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.8 | 41905066 | 41904793 | 07 - Relocate 8" HHWS/R Mains & Branches and Heating Coil RH-7 (RFI 139 8" Only) |  |  |  |  | day | 2020-08-03 07:00 | 2020-08-28 17:00 | [12 empty] | 7 | 7 | vmpki+S2kUG+dFVkXMCsQg | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.9 | 41905067 | 41904793 | 08 - Reconfig Gnd Floor SA at Concrete Trough Plenum (AHU-4) | 43 |  |  |  | day | 2020-07-27 07:00 | 2020-09-21 17:00 | [12 empty] | 8 | 7 | fHvJHXqizUO3PPjwmNCTWQ | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.10 | 41905068 | 41904793 | 09 - Demo Fan F-6 Duct and Add New Fan F-6A (RFI 332 ) | 25 |  |  |  | day | 2020-06-29 07:00 | 2020-08-07 17:00 | [12 empty] | 9 | 7 | mQ9ChNI+Z0yMITo5VgrI4g | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.11 | 41905069 | 41904793 | 10 - Modify AHU-9 RA Duct |  |  |  |  | day | 2020-06-29 07:00 | 2020-09-10 17:00 | [12 empty] | 10 | 7 | KIv5RH1LKUyXLH7w7m60iA | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.12 | 41905070 | 41904793 | 11 -Temp Relocate 8" Platform Dry Standpipe Main (RFI 113.1) |  |  |  |  | day | 2020-06-29 07:00 | 2020-09-02 17:00 | [12 empty] | 11 | 7 | Z8IQY+yR0EOsAX8CabVh7A | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.13 | 41905071 | 41904793 | 12 - Relocate/Demo Plumbing in Compressor Room | 31 |  |  |  | day | 2020-08-05 07:00 | 2020-08-31 17:00 | [12 empty] | 12 | 7 | t6eUjWtDx0m8d/gvs6WCIw | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.14 | 41905072 | 41904793 | 13 - Relocate Fuel Oil Serving Boilers | 3 |  |  |  | day | 2020-06-29 07:00 | 2020-10-05 17:00 | [12 empty] | 13 | 7 | BeQCFckCHUukgQYNhJQ4yw | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.1.15 | 41905075 | 41904793 | 14 - Headhouse to Tracks 1-8 - Conduit Run #2 - PCB towards Atlantic | 10 |  |  |  | day | [14 empty] | 14 | 7 | S1TUkMC3AEKJNuePjumbmw | 1DUnq0CC7Em5rWmC8Ai1sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.2 | 41904783 | 41904397 | Existing PCB and PCC Room | 16 |  |  |  | day | 2020-06-08 07:00 | 2021-03-29 17:00 | [12 empty] | 1 | 6 | AMZTAsS6ZUaVyzckAVDkbg | kF85TFpe3kClwM9BjJGHgQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.2.1 | 41905057 | 41904783 | DMP Operation | 37 |  |  |  | day | 2020-06-08 07:00 | 2020-07-10 17:00 | [12 empty] | 0 | 7 | 7Sh1EX3c70ui+NO1OjtFsg | AMZTAsS6ZUaVyzckAVDkbg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.3 | 41904607 | 41904397 | Existing Compressor Room | 23 |  |  |  | day | 2020-08-03 07:00 | 2021-03-26 17:00 | [12 empty] | 2 | 6 | YXiNShqzg0OlVEvSeh57zg | kF85TFpe3kClwM9BjJGHgQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.3.1 | 41905044 | 41904607 | PCC & PCB Switchgear Room | 4 |  |  |  | day | 2020-09-01 07:00 | 2021-03-26 17:00 | [12 empty] | 0 | 7 | IEHswyOECkaR4xsba4GXIg | YXiNShqzg0OlVEvSeh57zg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.3.1.1 | 41905148 | 41905044 | Air Compression Requirements | 33 |  |  |  | day | [14 empty] | 0 | 8 | tpf2+bWorkGMLqF1PXo9og | IEHswyOECkaR4xsba4GXIg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.3.1.2 | 41905149 | 41905044 | Enabling/Demolition |  |  |  |  | day | [14 empty] | 1 | 8 | MgF+vC3DVU+fuKu6rfEfeQ | IEHswyOECkaR4xsba4GXIg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.3.1.3 | 41905150 | 41905044 | New Gear / Room Construction |  |  |  |  | day | 2020-09-01 07:00 | 2021-03-26 17:00 | [12 empty] | 2 | 8 | dYz3WLzkVk+i1keqBvLgIw | IEHswyOECkaR4xsba4GXIg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.3.2 | 41905045 | 41904607 | Conduit Run #2 - PCB towards Atlantic | 10 |  |  |  | day | 2020-08-03 07:00 | 2020-09-18 17:00 | [12 empty] | 1 | 7 | d/COcejyPECT15/BwedZhg | YXiNShqzg0OlVEvSeh57zg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.3.3 | 41905046 | 41904607 | Conduit Run #1 - PCB towards Dorchester | 47 |  |  |  | day | 2020-09-11 07:00 | 2020-09-25 17:00 | [12 empty] | 2 | 7 | SjwPpcIpqE2KUPm2Tk8Wvg | YXiNShqzg0OlVEvSeh57zg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.3.4 | 41905049 | 41904607 | Condiut Run #3 - PCB to PSG | 15 |  |  |  | day | 2020-08-03 07:00 | 2020-09-14 17:00 | [12 empty] | 3 | 7 | TPwDW7MQO0eFSqcRuosZmg | YXiNShqzg0OlVEvSeh57zg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.3.5 | 41905047 | 41904607 | RFI 105.2 | 32 |  |  |  | day | [14 empty] | 4 | 7 | tAu/fcHIQE+aKP6nvZ1+3w | YXiNShqzg0OlVEvSeh57zg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.4 | 41904619 | 41904397 | Existing Main Electrical Room | 8 |  |  |  | day | 2020-02-26 07:00 | 2020-11-14 17:00 | [12 empty] | 3 | 6 | XU1bzU+qaUOHgMQT24QXrg | kF85TFpe3kClwM9BjJGHgQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.4.1 | 41905048 | 41904619 | New Emergency Electrical Room | 5 |  |  |  | day | 2020-02-26 07:00 | 2020-11-14 17:00 | [12 empty] | 0 | 7 | /ks1bHB4JkKCkwb34GZQBA | XU1bzU+qaUOHgMQT24QXrg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.5 | 41904754 | 41904397 | Existing PA room | 15 |  |  |  | day | 2020-08-31 07:00 | 2021-03-26 17:00 | [12 empty] | 4 | 6 | 7Op9Gw78IUGZwMAzP04NVg | kF85TFpe3kClwM9BjJGHgQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.1.5.2.6 | 41904618 | 41904397 | New Service Corridor | 28 |  |  |  | day | 2020-09-28 07:00 | 2021-01-04 17:00 | [12 empty] | 5 | 6 | q7yM4YXKe0qfDkD04CHDdQ | kF85TFpe3kClwM9BjJGHgQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2 | 41904241 | 41905203 | Podium/Bus Terminal/Parking (Standard Hours) | 47.8927 | 2023-09-07 08:00 | 2023-10-04 17:00 | 20 | day | 2021-01-19 07:00 | 2025-05-30 17:00 | [12 empty] | 1 | 3 | Tk7ZcUqLokiVH5BGj9QkhQ | iRqoq5YdVEasR9RY3sZSmg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.1 | 41906797 | 41904241 | VMU - Precast / Plaster Mock-up | 19 |  |  |  | day | 2022-08-08 07:00 | 2023-04-25 17:00 | [12 empty] | 0 | 4 | ZNZRfvcXN0eCBz4Q4YIfEA | Tk7ZcUqLokiVH5BGj9QkhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.2 | 41904290 | 41904241 | Podium- Cranes & Hoist |  |  |  |  | day | 2021-01-19 07:00 | 2023-02-26 17:00 | [12 empty] | 1 | 4 | kVypc62zWUyf0LyxJsdpqw | Tk7ZcUqLokiVH5BGj9QkhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.2.1 | 41904496 | 41904290 | Podium- Cranes | 18 |  |  |  | day | 2021-01-19 07:00 | 2023-02-26 17:00 | [12 empty] | 0 | 5 | XHuaY8BJyUSpGXAoD5ixjQ | kVypc62zWUyf0LyxJsdpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.2.1.1 | 41904701 | 41904496 | Crane #1 - Atlantic 1600 |  |  |  |  | day | 2021-01-19 07:00 | 2022-05-26 17:00 | [12 empty] | 0 | 6 | /PH874vB9EW40ZlFYEzyyg | XHuaY8BJyUSpGXAoD5ixjQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.2.1.2 | 41904707 | 41904496 | Crane #3 - Atlantic Assist Comeback | 2 |  |  |  | day | 2022-11-05 07:00 | 2023-02-26 17:00 | [12 empty] | 1 | 6 | NxHarSh5IkaiWesX2tssXA | XHuaY8BJyUSpGXAoD5ixjQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.2.1.2.1 | 41905444 | 41904707 | Mobilization 1 |  |  |  |  | day | [14 empty] | 0 | 7 | pXBPxeidykCuhk0L1UpbLw | NxHarSh5IkaiWesX2tssXA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.2.1.2.2 | 41905445 | 41904707 | Mobilization 2 | 19 |  |  |  | day | 2022-11-05 07:00 | 2023-02-26 17:00 | [12 empty] | 1 | 7 | oTwew0n+W0qkqFYBixFPzA | NxHarSh5IkaiWesX2tssXA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.2.1.3 | 41904702 | 41904496 | Crane #2 - Dorchester 1300 | 31 |  |  |  | day | 2021-10-16 07:00 | 2022-06-20 17:00 | [12 empty] | 2 | 6 | Q739JfkD6kqvcSCFLJQstw | XHuaY8BJyUSpGXAoD5ixjQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.2.1.4 | 41904708 | 41904496 | Crane #4 - Dorchester Assist Comeback | 6 |  |  |  | day | 2022-07-18 07:00 | 2022-08-15 17:00 | [12 empty] | 3 | 6 | PQeVgPblYk6IHHblX0ChuQ | XHuaY8BJyUSpGXAoD5ixjQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.2.2 | 41904454 | 41904290 | Podium Hoist | 40 |  |  |  | day | [14 empty] | 1 | 5 | WmRiAFWc6EOE97sNlCaWTg | kVypc62zWUyf0LyxJsdpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.2.2.1 | 41904709 | 41904454 | Hoist #2 (Podium @ Atlantic)- Ground through Level 10 | 32 |  |  |  | day | [14 empty] | 0 | 6 | n/yWZIE40k+jZjdSL+Tl/g | WmRiAFWc6EOE97sNlCaWTg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3 | 41904251 | 41904241 | Podium Structure | 39 |  |  |  | day | 2021-02-02 07:00 | 2024-05-31 17:00 | [12 empty] | 2 | 4 | AQasnsoJA0aMZnck2jOpZw | Tk7ZcUqLokiVH5BGj9QkhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.1 | 41904414 | 41904251 | Summary Structure (Includes CMP-09) | 38 |  |  |  | day | 2021-02-02 07:00 | 2024-03-25 17:00 | [12 empty] | 0 | 5 | 7bgx3/m/zU6MwzO5Wb+jrA | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.2 | 42792755 | 41904251 | Structural (Comeback) - Atlantic - Elevators | 17 |  |  |  | day | 2023-08-10 07:00 | 2024-05-31 17:00 | [12 empty] | 1 | 5 | N4wMa51efkmFp/zTD+6zPw | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3 | 41904380 | 41904251 | CMP-9 - Plenum Structural Steel (M-F 8:00pm to 4:30am) | 39 |  |  |  | day | 2021-02-02 07:00 | 2022-03-11 17:00 | [12 empty] | 2 | 5 | N+HtYtea0kOQWb6noCTJUA | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.1 | 41905264 | 41904380 | 01W - CMP-9A Col. Lines H, G, & F (Tracks 01-04) | 0 |  |  |  | day | 2021-02-02 07:00 | 2021-10-23 17:00 | [12 empty] | 0 | 6 | WfxTNi4NEk+FO0jn8kKXjw | N+HtYtea0kOQWb6noCTJUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.1.1 | 41905265 | 41905264 | Detail H-31 Truss | 10 |  |  |  | day | 2021-02-02 07:00 | 2021-03-22 17:00 | [12 empty] | 0 | 7 | EtkRROsDyUWqDNnVjAOTNA | WfxTNi4NEk+FO0jn8kKXjw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.1.2 | 41905266 | 41905264 | Remaining | 27 |  |  |  | day | 2021-03-01 07:00 | 2021-10-23 17:00 | [12 empty] | 1 | 7 | ccK+Brq55U+xOOUF4P73sg | WfxTNi4NEk+FO0jn8kKXjw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.1.2.1 | 41905316 | 41905266 | 01W - South F20 Comeback | 24 |  |  |  | day | 2021-05-03 07:00 | 2021-10-23 17:00 | [12 empty] | 0 | 8 | fhOUiz2OGkuzUusy5rNSpg | ccK+Brq55U+xOOUF4P73sg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.1.2.2 | 41905317 | 41905266 | (New WBS) | 49 |  |  |  | day | [14 empty] | 1 | 8 | GFAOQftC3EKCfVoCqMwyww | ccK+Brq55U+xOOUF4P73sg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.2 | 41904595 | 41904380 | 02W - Ramp Infill | 22 |  |  |  | day | 2021-04-26 07:00 | 2021-06-29 17:00 | [12 empty] | 1 | 6 | p5xL/QsbREqU7mVt4oaTDQ | N+HtYtea0kOQWb6noCTJUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.3 | 41904596 | 41904380 | 03W - CMP-9B Col. Lines F & E (Tracks 03-06) |  |  |  |  | day | 2021-04-09 07:00 | 2021-10-23 17:00 | [12 empty] | 2 | 6 | g7wGdm4k2kC7V0mVaRZT+g | N+HtYtea0kOQWb6noCTJUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.3.1 | 41905501 | 41904596 | 03W - South F20 Comeback | 29 |  |  |  | day | 2021-10-11 07:00 | 2021-10-23 17:00 | [12 empty] | 0 | 7 | 8YR+NisU2kmAzZM4nftmCA | g7wGdm4k2kC7V0mVaRZT+g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.4 | 41904597 | 41904380 | 04W - CMP-9C Col. Lines E & D (Tracks 05-08 / 05-13) | 41 |  |  |  | day | 2021-07-10 07:00 | 2021-11-18 17:00 | [12 empty] | 3 | 6 | i5JMYiEakUOVu8tOHLjSfA | N+HtYtea0kOQWb6noCTJUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.4.1 | 41905502 | 41904597 | 04W - North LBE Comeback | 34 |  |  |  | day | 2021-11-03 07:00 | 2021-11-18 17:00 | [12 empty] | 0 | 7 | NfktjWBaMUWQCFFBFMAo4g | i5JMYiEakUOVu8tOHLjSfA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.5 | 41904598 | 41904380 | 06W - CMP-9E Col. Lines D & C (Tracks 07-10 / 07-13) |  |  |  |  | day | 2021-08-26 07:00 | 2022-01-28 17:00 | [12 empty] | 4 | 6 | T0/oYde3tEeiO1dxSKGgLA | N+HtYtea0kOQWb6noCTJUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.5.1 | 41905503 | 41904598 | 06W - North LBE Comeback |  |  |  |  | day | 2021-11-02 07:00 | 2022-01-28 17:00 | [12 empty] | 0 | 7 | lmPFTiHHYE2W3KK6bPWVgg | T0/oYde3tEeiO1dxSKGgLA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.5.2 | 41905504 | 41904598 | 06W - South Comeback | 25 |  |  |  | day | 2021-10-25 07:00 | 2021-11-30 17:00 | [12 empty] | 1 | 7 | yMqGwgeLGEW7FccLnN3YHQ | T0/oYde3tEeiO1dxSKGgLA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.6 | 41904599 | 41904380 | 01E - CMP-9F Col. Lines C & B (Tracks 09-12 / 09-13) | 47 |  |  |  | day | 2021-10-18 07:00 | 2021-12-15 17:00 | [12 empty] | 5 | 6 | 9bCw5fhTOEalj0DOwnPsRA | N+HtYtea0kOQWb6noCTJUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.7 | 41905636 | 41904380 | 01E - South | 48 |  |  |  | day | 2021-11-23 07:00 | 2021-12-16 17:00 | [12 empty] | 6 | 6 | 96oBHZI0bUeu22j8Jl4hlQ | N+HtYtea0kOQWb6noCTJUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.8 | 41905637 | 41904380 | 01E - North CI 29-32 |  |  |  |  | day | 2021-11-26 07:00 | 2021-12-29 17:00 | [12 empty] | 7 | 6 | 3JJZBh/Np0S8tswCPXZtxw | N+HtYtea0kOQWb6noCTJUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.9 | 41904600 | 41904380 | 02E - CMP-9H Col. Lines B & A.3 (Tracks 11-13) | 0 |  |  |  | day | 2021-12-03 07:00 | 2022-03-11 17:00 | [12 empty] | 8 | 6 | NDWNiiFOj0qqibp8KBhn+A | N+HtYtea0kOQWb6noCTJUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.9.1 | 41905440 | 41904600 | --- |  |  |  |  | day | 2022-03-11 07:00 | 2022-03-11 17:00 | [12 empty] | 0 | 7 | Vk+zg8olF0iSbqOSSuz73g | NDWNiiFOj0qqibp8KBhn+A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.10 | 41905638 | 41904380 | 02E - North | 11 |  |  |  | day | 2022-02-28 07:00 | 2022-03-11 17:00 | [12 empty] | 9 | 6 | JhT+TSCJXEWuF4QiH05ynA | N+HtYtea0kOQWb6noCTJUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.3.11 | 41905665 | 41904380 | Baggage Claim Demo - (Enables 1E completion) | 4 |  |  |  | day | 2021-12-13 07:00 | 2021-12-15 17:00 | [12 empty] | 10 | 6 | V2eoAOP1pU2jkaB/k0N8yA | N+HtYtea0kOQWb6noCTJUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4 | 41904400 | 41904251 | Structural P1 (EL +74.5') |  |  |  |  | day | 2021-08-19 07:00 | 2022-07-01 17:00 | [12 empty] | 3 | 5 | WT06mN+ZGEeEcOCVTOj0LQ | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.1 | 41905601 | 41904400 | G/19 & F/20 - DEMO (waiting on BT POUR 10/29) | 31 |  |  |  | day | 2021-11-05 07:00 | 2021-12-03 17:00 | [12 empty] | 0 | 6 | zNrER5YLn0qOjpL0Xa5NKQ | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.2 | 41905322 | 41904400 | 05W - F-E - 1600 | 8 |  |  |  | day | 2021-08-19 07:00 | 2022-04-08 17:00 | [12 empty] | 1 | 6 | UNrqiueZhUe9oTsLYLaG4Q | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.2.1 | 41905506 | 41905322 | 05W - South Comeback |  |  |  |  | day | 2021-12-13 07:00 | 2022-04-08 17:00 | [12 empty] | 0 | 7 | humAdUj4hECK5avuFmQQHg | UNrqiueZhUe9oTsLYLaG4Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.3 | 41905323 | 41904400 | 07W - E-D - 1600 | 34 |  |  |  | day | 2021-09-20 07:00 | 2022-04-15 17:00 | [12 empty] | 2 | 6 | c+0NtNcHREefXREUUyBS0Q | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.3.1 | 41905505 | 41905323 | 07W - North LBE Comeback | 18 |  |  |  | day | 2021-11-22 07:00 | 2022-03-21 17:00 | [12 empty] | 0 | 7 | xl1sB1OR30SK2bJmqxAqcQ | c+0NtNcHREefXREUUyBS0Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.4 | 41905345 | 41904400 | 08W - F-H Wings 31-29 & 23-19 - 1600 - 8W NORTH |  |  |  |  | day | 2021-09-27 07:00 | 2022-03-11 17:00 | [12 empty] | 3 | 6 | 7wZrXxVJgUO/rbfWKqC8MA | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.4.1 | 41905435 | 41905345 | --- | 15 |  |  |  | day | [14 empty] | 0 | 7 | 07ePG7ZNykqkRLQi4Lg6+A | 7wZrXxVJgUO/rbfWKqC8MA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.4.2 | 41905507 | 41905345 | 08W - South Comeback | 2 |  |  |  | day | 2021-12-14 07:00 | 2022-03-08 17:00 | [12 empty] | 1 | 7 | Gz0IqVKZF0KXYIEzknImxQ | 7wZrXxVJgUO/rbfWKqC8MA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.4.3 | 41905727 | 41905345 | 08W - North Comeback | 19 |  |  |  | day | 2021-12-14 07:00 | 2022-03-11 17:00 | [12 empty] | 2 | 7 | dzhVmGZ6dkqLuhAfzhulQA | 7wZrXxVJgUO/rbfWKqC8MA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.5 | 41905602 | 41904400 | C/19 & C/20 DEMO (Waiting on BT POUR#03) [DRIVES 3E & 4E] | 23 |  |  |  | day | [14 empty] | 4 | 6 | LpCz37rcY0S/9gmT6hoAQA | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.6 | 41905603 | 41904400 | B/19 DEMO (Waiting on BT POUR#03) [DRIVES 4E & 5E] | 32 |  |  |  | day | [14 empty] | 5 | 6 | FzbOPKlPZE+eSAcxu590xg | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.7 | 41905324 | 41904400 | 03E - D-C - 1300 |  |  |  |  | day | 2021-11-09 07:00 | 2022-03-25 17:00 | [12 empty] | 6 | 6 | aT4pVIJrtkiOA5QkI00bwg | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.8 | 41905639 | 41904400 | 03E - South |  |  |  |  | day | 2022-01-05 07:00 | 2022-03-10 17:00 | [12 empty] | 7 | 6 | 2JxU4QgvuUWxT0lfypGb7A | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.9 | 41905325 | 41904400 | 04E - C-B - 1300 |  |  |  |  | day | 2022-03-01 07:00 | 2022-03-15 17:00 | [12 empty] | 8 | 6 | Al42QjBUTEu904SSpRvdXA | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.10 | 41905640 | 41904400 | 04E - South | 7 |  |  |  | day | 2022-02-08 07:00 | 2022-03-15 17:00 | [12 empty] | 9 | 6 | As+LMtudHUC7O3PhAZ5c8A | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.11 | 41905641 | 41904400 | 04E - North |  |  |  |  | day | 2022-01-05 07:00 | 2022-03-11 17:00 | [12 empty] | 10 | 6 | LmiRekwnw0a1yeUJ3d5LKw | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.12 | 41905604 | 41904400 | A.6/19 DEMO (Waiting on BT POUR#XX) [DRIVES 5E & 15E] | 37 |  |  |  | day | 2021-12-13 07:00 | 2022-02-17 17:00 | [12 empty] | 11 | 6 | qGPomlfbvE+QlfsObAHrow | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.13 | 41905326 | 41904400 | 05E - B-A.3 Wings - 1300 | 39 |  |  |  | day | 2022-01-10 07:00 | 2022-06-09 17:00 | [12 empty] | 12 | 6 | qUVL2QBEkEOgrVbAJjamMQ | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.4.14 | 41905439 | 41904400 | 05E - South | 19 |  |  |  | day | 2022-03-29 07:00 | 2022-07-01 17:00 | [12 empty] | 13 | 6 | KA+B4yLRoUWyqs+tOENqGQ | WT06mN+ZGEeEcOCVTOj0LQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.5 | 41904401 | 41904251 | Structural P2 (EL +84.5') & P3 (EL +94.5') | 34 |  |  |  | day | 2021-10-13 07:00 | 2022-04-12 17:00 | [12 empty] | 4 | 5 | ZXWTU9mZYUODXE/iJ1s70Q | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.5.1 | 41905327 | 41904401 | 10W - F-E - 1600 |  |  |  |  | day | 2021-10-13 07:00 | 2022-04-12 17:00 | [12 empty] | 0 | 6 | aOXtKchf2U6o7D57s1H0KA | ZXWTU9mZYUODXE/iJ1s70Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.5.1.1 | 41905508 | 41905327 | 10W - South Comeback | 24 |  |  |  | day | 2021-11-22 07:00 | 2022-04-01 17:00 | [12 empty] | 0 | 7 | 3Z2NVNHF00i6JmP+jtTVZQ | aOXtKchf2U6o7D57s1H0KA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.5.2 | 41905328 | 41904401 | 09W - E-D - 1600 | 34 |  |  |  | day | 2021-12-03 07:00 | 2022-04-12 17:00 | [12 empty] | 1 | 6 | roM/tz+si0eRcv/ggjFaIg | ZXWTU9mZYUODXE/iJ1s70Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.5.3 | 41905329 | 41904401 | 06E - D-C - 1300 |  |  |  |  | day | 2021-12-17 07:00 | 2022-04-08 17:00 | [12 empty] | 2 | 6 | oIY5nFIz5UuRupkLMvF6HA | ZXWTU9mZYUODXE/iJ1s70Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.5.4 | 41905330 | 41904401 | 07E - C-B - 1300 |  |  |  |  | day | 2022-01-18 07:00 | 2022-04-08 17:00 | [12 empty] | 3 | 6 | gy8Lu3DhfEmtzj/cJgQu9Q | ZXWTU9mZYUODXE/iJ1s70Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.6 | 41904402 | 41904251 | Structural P3 (EL +94.5') | 17 |  |  |  | day | [14 empty] | 5 | 5 | uVgrofzfXEGoEnf9EuShqg | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.7 | 41904403 | 41904251 | Structural P4 (EL +109') & P5 (EL +122') |  |  |  |  | day | 2021-12-06 07:00 | 2022-06-21 17:00 | [12 empty] | 6 | 5 | bsIphetoGE+F7X/7lY05fA | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.7.1 | 41905333 | 41904403 | 13W - F-E - 1600 | 17 |  |  |  | day | 2021-12-06 07:00 | 2022-05-27 17:00 | [12 empty] | 0 | 6 | V58m53eZ9E6JYLfvnvygUg | bsIphetoGE+F7X/7lY05fA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.7.2 | 41905334 | 41904403 | 12W - E-D - 1600 | 1 |  |  |  | day | 2022-04-04 07:00 | 2022-06-03 17:00 | [12 empty] | 1 | 6 | XHQC1z6xAEunv8uc3PflEw | bsIphetoGE+F7X/7lY05fA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.7.3 | 41905335 | 41904403 | 09E - D-C - 1300 |  |  |  |  | day | 2022-02-23 07:00 | 2022-06-21 17:00 | [12 empty] | 2 | 6 | sFWVOkptlE+Vk6S9Td/80Q | bsIphetoGE+F7X/7lY05fA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.7.4 | 41905336 | 41904403 | 10E - C-B - 1300 |  |  |  |  | day | 2022-04-11 07:00 | 2022-06-17 17:00 | [12 empty] | 3 | 6 | WYLq1jhypkKGcevETyCD3w | bsIphetoGE+F7X/7lY05fA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.7.4.1 | 41905441 | 41905336 | --- |  |  |  |  | day | [14 empty] | 0 | 7 | lzpZyQO/S0OM0x2Tm97GAg | WYLq1jhypkKGcevETyCD3w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.7.5 | 41905340 | 41904403 | 11E - B-A.3 Wings - 1300 | 35 |  |  |  | day | [14 empty] | 4 | 6 | TarWpIL3I0+JLcDLBD31CQ | bsIphetoGE+F7X/7lY05fA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.8 | 41904404 | 41904251 | Structural P5 (EL +122') (L10) |  |  |  |  | day | [14 empty] | 7 | 5 | GRAC41qo/kiD7W8adhsV4g | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.9 | 41904405 | 41904251 | Structural L11 (EL +135') (Residential Sky Street) | 3 |  |  |  | day | 2021-12-21 07:00 | 2022-06-20 17:00 | [12 empty] | 8 | 5 | XdBUeZ0S/UaSdJMw8x5tww | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.9.1 | 41905341 | 41904405 | 15W - F-D - 1600 | 32 |  |  |  | day | 2021-12-21 07:00 | 2022-06-06 17:00 | [12 empty] | 0 | 6 | d18LXlqzFUqPGeJArCPKug | XdBUeZ0S/UaSdJMw8x5tww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.9.2 | 41905342 | 41904405 | 11E - D-B - 1300 | 13 |  |  |  | day | 2022-04-21 07:00 | 2022-06-20 17:00 | [12 empty] | 1 | 6 | 6IMhYqPshkKny8WbpEvl7w | XdBUeZ0S/UaSdJMw8x5tww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.9.2.1 | 41905442 | 41905342 | --- | 20 |  |  |  | day | [14 empty] | 0 | 7 | BP1q80AzZU66prpMD8o7OA | 6IMhYqPshkKny8WbpEvl7w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10 | 41904406 | 41904251 | Structural (Ground to L12) F-H - 1600 Relocated/Modified - Atlantic Mob1 | 47 |  |  |  | day | 2022-01-28 07:00 | 2022-06-10 17:00 | [12 empty] | 9 | 5 | zFMFUIA4e0yoJFf9UAlKBg | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.1 | 41905349 | 41904406 | 17W - H-F - Assist Crane #3 - Atlantic Ave - Mob1 | 19 |  |  |  | day | 2022-04-15 07:00 | 2022-05-20 17:00 | [12 empty] | 0 | 6 | BLermK6UG0SFEJpLW1MoeA | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.2 | 41905350 | 41904406 | 18W - H-F - Assist Crane #3 - Atlantic Ave - Mob1 | 7 |  |  |  | day | 2022-04-20 07:00 | 2022-05-20 17:00 | [12 empty] | 1 | 6 | XGTEb22I90O8Ai2ZGTcu2A | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.3 | 41905351 | 41904406 | 19W - H-F - Assist Crane #3 - Atlantic Ave - Mob1 | 6 |  |  |  | day | 2022-04-22 07:00 | 2022-05-25 17:00 | [12 empty] | 2 | 6 | Fn0095qCd0yr7R/bv+BU1w | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.4 | 41905346 | 41904406 | 11W- F-H Wings South - 1600 |  |  |  |  | day | 2022-02-28 07:00 | 2022-04-12 17:00 | [12 empty] | 3 | 6 | 2ShZHWAB+UGYtRwc+4K/fQ | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.4.1 | 41905436 | 41905346 | --- | 16 |  |  |  | day | [14 empty] | 0 | 7 | I1kFs1HDAkebLzmzZQ10xg | 2ShZHWAB+UGYtRwc+4K/fQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.5 | 41905352 | 41904406 | 20W - H-F - Assist Crane #3 - Atlantic Ave - Mob1 |  |  |  |  | day | 2022-04-27 07:00 | 2022-06-06 17:00 | [12 empty] | 4 | 6 | +0p2T1ii3EaIIusMsTdrFA | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.5.1 | 41905509 | 41905352 | 08W - South Comeback |  |  |  |  | day | [14 empty] | 0 | 7 | uYHYC28YWkCIk9KmVRlSbQ | +0p2T1ii3EaIIusMsTdrFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.6 | 41905510 | 41904406 | 11W- F-H Wings North - 1600-1 | 11 |  |  |  | day | 2022-01-28 07:00 | 2022-04-12 17:00 | [12 empty] | 5 | 6 | iNF5IBW+8UCPH7ZX+Bep2g | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.6.1 | 41905511 | 41905510 | --- |  |  |  |  | day | [14 empty] | 0 | 7 | x2qsKrhGi0Kl1K1JSFnvYA | iNF5IBW+8UCPH7ZX+Bep2g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.7 | 41905347 | 41904406 | 14W- F-H Wings 31-29 & 23-19 - 1600 | 21 |  |  |  | day | 2022-04-05 07:00 | 2022-06-02 17:00 | [12 empty] | 6 | 6 | YN3DSdTmWk+esuFmPK6vuA | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.7.1 | 41905437 | 41905347 | --- |  |  |  |  | day | [14 empty] | 0 | 7 | F7ZnxWLO/kiVkJaItt/TfQ | YN3DSdTmWk+esuFmPK6vuA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.8 | 41905353 | 41904406 | 21W - H-F - Assist Crane #3 - Atlantic Ave - Mob1 | 29 |  |  |  | day | 2022-04-30 07:00 | 2022-06-03 17:00 | [12 empty] | 7 | 6 | BMpHmxvfH0KShb7Nad28/g | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.9 | 41905512 | 41904406 | 14W- F-H Wings North | 37 |  |  |  | day | 2022-03-25 07:00 | 2022-05-13 17:00 | [12 empty] | 8 | 6 | Krct21Uf3UCPoJYF/77YFg | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.9.1 | 41905513 | 41905512 | --- | 37 |  |  |  | day | [14 empty] | 0 | 7 | 6WlsIPmGkUG/AymFSb/yEg | Krct21Uf3UCPoJYF/77YFg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.10 | 41905348 | 41904406 | 16W - F-H Wings South |  |  |  |  | day | 2022-04-04 07:00 | 2022-05-11 17:00 | [12 empty] | 9 | 6 | j7QCdxS9DE+2q0RqQl0fqw | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.10.1 | 41905438 | 41905348 | --- |  |  |  |  | day | [14 empty] | 0 | 7 | QKWLVCEd0U+396BB2lXAxg | j7QCdxS9DE+2q0RqQl0fqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.11 | 41905428 | 41904406 | 22W - H-F - Assist Crane #3 - Atlantic Ave - Mob1 | 26 |  |  |  | day | 2022-05-16 07:00 | 2022-06-08 17:00 | [12 empty] | 10 | 6 | lAcqq0dKyk+Nejord5/jiQ | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.12 | 41905514 | 41904406 | 16W - F-H Wings North | 26 |  |  |  | day | 2022-03-29 07:00 | 2022-06-10 17:00 | [12 empty] | 11 | 6 | h1g5oGLHkESvt0QTFMPrnw | zFMFUIA4e0yoJFf9UAlKBg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.10.12.1 | 41905515 | 41905514 | --- | 33 |  |  |  | day | [14 empty] | 0 | 7 | iz7QzTUtVE+NuTpJzUw1uQ | h1g5oGLHkESvt0QTFMPrnw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11 | 41905443 | 41904251 | Podium Foundations - Atlantic | 20 |  |  |  | day | 2021-05-18 07:00 | 2022-11-14 17:00 | [12 empty] | 10 | 5 | hcyVx3rWmEmrYQKKb4eH4g | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.1 | 41905516 | 41905443 | GSA | 29 |  |  |  | day | 2021-05-18 07:00 | 2022-02-25 17:00 | [12 empty] | 0 | 6 | Dc9SJm1s+kSu3S3eDHTjog | hcyVx3rWmEmrYQKKb4eH4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.2 | 41906627 | 41905443 | Engineering for Podium Crane |  |  |  |  | day | [14 empty] | 1 | 6 | UECplYOA4km3Mq6RPDPYhQ | hcyVx3rWmEmrYQKKb4eH4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.3 | 41905517 | 41905443 | Foundation Scope | 27 |  |  |  | day | 2022-05-04 07:00 | 2022-11-14 17:00 | [12 empty] | 2 | 6 | bLMgLnqyuE2UXx2Ql7g5jg | hcyVx3rWmEmrYQKKb4eH4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.3.1 | 41906625 | 41905517 | North - 25-31 | 46 |  |  |  | day | 2022-05-04 07:00 | 2022-11-04 17:00 | [12 empty] | 0 | 7 | ljHqGUD2X0+7LVoa2Ezw9Q | bLMgLnqyuE2UXx2Ql7g5jg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.3.1.1 | 41906767 | 41906625 | Excavation and SOE - North | 32 |  |  |  | day | 2022-05-31 07:00 | 2022-07-05 17:00 | [12 empty] | 0 | 8 | eQkECxsHk0quS2bhp4Tb2Q | ljHqGUD2X0+7LVoa2Ezw9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.3.1.2 | 41906772 | 41906625 | Sanitary Main - North | 4 |  |  |  | day | 2022-07-06 07:00 | 2022-08-25 17:00 | [12 empty] | 1 | 8 | zTs2tmuzk06fCMMOHud8pA | ljHqGUD2X0+7LVoa2Ezw9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.3.1.3 | 41906771 | 41906625 | Foundation and Backfill - North | 47 |  |  |  | day | 2022-08-26 07:00 | 2022-11-04 17:00 | [12 empty] | 2 | 8 | IpHErjqDE06NrNrFx2m+zw | ljHqGUD2X0+7LVoa2Ezw9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.3.1.4 | 41906768 | 41906625 | Elevator Pit PE16-17 - North |  |  |  |  | day | 2022-07-15 07:00 | 2022-08-23 17:00 | [12 empty] | 3 | 8 | myRs4MHy5UiGDi7lT0zVAQ | ljHqGUD2X0+7LVoa2Ezw9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.3.1.5 | 41906769 | 41906625 | Plumbing and Telecom East of Grade Beam 2- H Line - North | 3 |  |  |  | day | 2022-09-13 07:00 | 2022-09-28 17:00 | [12 empty] | 4 | 8 | 4OLIH8UemUSiJZg9e1xluA | ljHqGUD2X0+7LVoa2Ezw9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.3.2 | 41906626 | 41905517 | South - 19-25 | 34 |  |  |  | day | 2022-05-31 07:00 | 2022-11-14 17:00 | [12 empty] | 1 | 7 | n4FtO9QPlUirKaou5tZDFg | bLMgLnqyuE2UXx2Ql7g5jg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.3.2.1 | 41906765 | 41906626 | Excavation and SOE - South | 48 |  |  |  | day | 2022-05-31 07:00 | 2022-07-29 17:00 | [12 empty] | 0 | 8 | tsNFv9Tq5UaBXtMIfcTdIA | n4FtO9QPlUirKaou5tZDFg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.3.2.2 | 41906770 | 41906626 | Under Platform A Scope - 26 South | 16 |  |  |  | day | 2022-07-11 07:00 | 2022-08-09 17:00 | [12 empty] | 1 | 8 | EoesEw8Oe0y3IA62cDOKfg | n4FtO9QPlUirKaou5tZDFg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.11.3.2.3 | 41906766 | 41906626 | Foundation and Backfill - South |  |  |  |  | day | 2022-09-12 07:00 | 2022-11-14 17:00 | [12 empty] | 2 | 8 | FYsKk1ndskqWEefa9+zUkg | n4FtO9QPlUirKaou5tZDFg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12 | 41904398 | 41904251 | Structural (Ground to L12) H-J.75 Assist Crane #3 - Atlantic Mob2 | 27 |  |  |  | day | 2022-11-07 07:00 | 2023-10-06 17:00 | [12 empty] | 11 | 5 | 4AjHeUpJLkOMM5w4hePD5g | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1 | 41906628 | 41904398 | North | 29 |  |  |  | day | 2022-11-07 07:00 | 2023-09-29 17:00 | [12 empty] | 0 | 6 | hz1Secgn6E2xkjAprCfqsA | 4AjHeUpJLkOMM5w4hePD5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.1 | 41904710 | 41906628 | Col 29-31 - Lobby/Office Lease (Headhouse to Helix) | 28 |  |  |  | day | 2022-11-07 07:00 | 2023-03-06 17:00 | [12 empty] | 0 | 7 | 3z8v1Lln6EGTlyXMnYpSdQ | hz1Secgn6E2xkjAprCfqsA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.1.1 | 41905358 | 41904710 | A-01 LR |  |  |  |  | day | 2022-11-07 07:00 | 2023-01-18 17:00 | [12 empty] | 0 | 8 | Jn7guWxvF0O0YHBVw3oyog | 3z8v1Lln6EGTlyXMnYpSdQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.1.2 | 41905359 | 41904710 | A-03 BT-P1 | 5 |  |  |  | day | 2022-12-05 07:00 | 2023-02-08 17:00 | [12 empty] | 1 | 8 | Zt6WnCexpk6Tl+5/SQG9FA | 3z8v1Lln6EGTlyXMnYpSdQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.1.3 | 41905360 | 41904710 | A-05 P2-P3 | 34 |  |  |  | day | 2023-01-10 07:00 | 2023-02-27 17:00 | [12 empty] | 2 | 8 | Miye3UN0AUuzbCFM+Eb2Bg | 3z8v1Lln6EGTlyXMnYpSdQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.1.4 | 41905361 | 41904710 | A-07 P4-L11 | 40 |  |  |  | day | 2023-01-12 07:00 | 2023-03-01 17:00 | [12 empty] | 3 | 8 | ahzKohKCJ0ir6Rq4+BnccA | 3z8v1Lln6EGTlyXMnYpSdQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.1.5 | 41905362 | 41904710 | A-09 P4-L11 | 36 |  |  |  | day | 2023-02-03 07:00 | 2023-03-06 17:00 | [12 empty] | 4 | 8 | L09slxtc4Em1R++whciwKw | 3z8v1Lln6EGTlyXMnYpSdQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.2 | 41904711 | 41906628 | Col 25-29 - Parking Ramp (Helix) | 23 |  |  |  | day | 2022-11-10 07:00 | 2023-04-13 17:00 | [12 empty] | 1 | 7 | 6CVPfanP+EWnRTDE3gzuWw | hz1Secgn6E2xkjAprCfqsA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.2.1 | 41905354 | 41904711 | A-02 LR BT (Ramp) |  |  |  |  | day | 2022-11-10 07:00 | 2023-03-17 17:00 | [12 empty] | 0 | 8 | izF6MpWxSEa0g2qBQzcR2g | 6CVPfanP+EWnRTDE3gzuWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.2.2 | 41905355 | 41904711 | A-04 P1-P2 | 48 |  |  |  | day | 2022-12-14 07:00 | 2023-03-27 17:00 | [12 empty] | 1 | 8 | EK5CjHF2b0GiIbnJcAMAKA | 6CVPfanP+EWnRTDE3gzuWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.2.3 | 41905356 | 41904711 | A-06 P1-P3 | 45 |  |  |  | day | 2023-02-09 07:00 | 2023-04-13 17:00 | [12 empty] | 2 | 8 | 66L9H1kD9kmHWhliAywhnw | 6CVPfanP+EWnRTDE3gzuWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.2.4 | 41905357 | 41904711 | A-08 P4-L11 | 30 |  |  |  | day | 2023-02-03 07:00 | 2023-04-13 17:00 | [12 empty] | 3 | 8 | pcgmFmMqn0uXYKt8SSdCNw | 6CVPfanP+EWnRTDE3gzuWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.3 | 41904875 | 41906628 | Atlantic North - SOMDs and SPF - All Elevations | 34 |  |  |  | day | 2023-03-20 07:00 | 2023-07-18 17:00 | [12 empty] | 2 | 7 | mKurRXqwAkG80Qtc91wKmQ | hz1Secgn6E2xkjAprCfqsA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.4 | 41904874 | 41906628 | -- |  |  |  |  | day | [14 empty] | 3 | 7 | fYVK2ckIOU6jtcYPzbjWdA | hz1Secgn6E2xkjAprCfqsA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.5 | 41904813 | 41906628 | Primary Electrical Cable Chamber | 20 |  |  |  | day | 2023-05-10 07:00 | 2023-09-29 17:00 | [12 empty] | 4 | 7 | 6fDmDSKpeE+YhTi3uHl2qw | hz1Secgn6E2xkjAprCfqsA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.5.1 | 41907062 | 41904813 | Chamber - Ground - MBTA/Tower | 31 |  |  |  | day | [14 empty] | 0 | 8 | xo3fyL9coEutxexuK/62Hw | 6fDmDSKpeE+YhTi3uHl2qw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.5.2 | 41907063 | 41904813 | Chamber - Level 2 - MBTA/Tower | 22 |  |  |  | day | 2023-05-10 07:00 | 2023-09-29 17:00 | [12 empty] | 1 | 8 | Gi8oybpRUE28p8TK2wWclw | 6fDmDSKpeE+YhTi3uHl2qw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.5.3 | 41907065 | 41904813 | Chamber - LR - MBTA/Tower | 32 |  |  |  | day | 2023-05-11 07:00 | 2023-09-21 17:00 | [12 empty] | 2 | 8 | d3IkrnGqU0uwFAZeLHufYA | 6fDmDSKpeE+YhTi3uHl2qw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.5.4 | 41907066 | 41904813 | Chamber - BT - MBTA/Tower |  |  |  |  | day | 2023-05-18 07:00 | 2023-09-25 17:00 | [12 empty] | 3 | 8 | a/pmufort0+OsDg6fB+LlQ | 6fDmDSKpeE+YhTi3uHl2qw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.5.5 | 41907068 | 41904813 | Chamber - P1 - Tower | 17 |  |  |  | day | 2023-05-30 07:00 | 2023-09-27 17:00 | [12 empty] | 4 | 8 | dajaYuHXQEafjaMwUl0B1A | 6fDmDSKpeE+YhTi3uHl2qw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.5.6 | 41907069 | 41904813 | Chamber - P2 - Tower | 24 |  |  |  | day | 2023-06-05 07:00 | 2023-09-29 17:00 | [12 empty] | 5 | 8 | HFTtGfhpQkeINfppFhRasg | 6fDmDSKpeE+YhTi3uHl2qw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.1.5.7 | 41907070 | 41904813 | Chamber - P3 - Tower | 41 |  |  |  | day | 2023-06-15 07:00 | 2023-09-25 17:00 | [12 empty] | 6 | 8 | Z9Nl6vNGWU+ZnGQuLtnMiw | 6fDmDSKpeE+YhTi3uHl2qw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2 | 41906629 | 41904398 | South |  |  |  |  | day | 2022-12-20 07:00 | 2023-05-08 17:00 | [12 empty] | 1 | 6 | PCFAFGWsakK1+3lYK7yyLQ | 4AjHeUpJLkOMM5w4hePD5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2.1 | 41905363 | 41906629 | Col 25-22 - Storage (Helix to Bus Terminal) | 2 |  |  |  | day | 2022-12-20 07:00 | 2023-03-03 17:00 | [12 empty] | 0 | 7 | 5CF3h/4hWUKyhkskVEAdBQ | PCFAFGWsakK1+3lYK7yyLQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2.1.1 | 41905364 | 41905363 | A-10 BT-P1 | 39 |  |  |  | day | 2022-12-20 07:00 | 2023-01-18 17:00 | [12 empty] | 0 | 8 | LdlfCzNvoUmnPM9FtwcvmQ | 5CF3h/4hWUKyhkskVEAdBQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2.1.2 | 41905365 | 41905363 | A-11 P2-P3 | 45 |  |  |  | day | 2023-01-18 07:00 | 2023-02-09 17:00 | [12 empty] | 1 | 8 | yETSoMwGC0mbl6PHfyX91A | 5CF3h/4hWUKyhkskVEAdBQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2.1.3 | 41905366 | 41905363 | A-12 P4 |  |  |  |  | day | 2023-02-01 07:00 | 2023-03-03 17:00 | [12 empty] | 2 | 8 | X0nBgywZxE2YdIKDGJ4LYg | 5CF3h/4hWUKyhkskVEAdBQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2.2 | 41904712 | 41906629 | Col 22-19 - Storage (Helix to Bus Terminal) | 49 |  |  |  | day | 2022-12-26 07:00 | 2023-04-13 17:00 | [12 empty] | 1 | 7 | QTJJKTejGE2H71sl2wcjBQ | PCFAFGWsakK1+3lYK7yyLQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2.2.1 | 41905367 | 41904712 | A-13 BT | 31 |  |  |  | day | 2022-12-26 07:00 | 2023-03-23 17:00 | [12 empty] | 0 | 8 | FzHBeltasE20NwFrxY/Upg | QTJJKTejGE2H71sl2wcjBQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2.2.2 | 41905368 | 41904712 | A-14 P1 |  |  |  |  | day | 2023-01-05 07:00 | 2023-03-27 17:00 | [12 empty] | 1 | 8 | mgtoUhUCqEOKddgt5BDoGg | QTJJKTejGE2H71sl2wcjBQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2.2.3 | 41905369 | 41904712 | A-15 P2-P3 |  |  |  |  | day | 2023-02-16 07:00 | 2023-04-13 17:00 | [12 empty] | 2 | 8 | eJQRE25P1UqEmcBtxUDzKg | QTJJKTejGE2H71sl2wcjBQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2.2.4 | 41905370 | 41904712 | A-16 P4 | 22 |  |  |  | day | 2023-02-17 07:00 | 2023-04-13 17:00 | [12 empty] | 3 | 8 | 5d8vYI+rO0aSVEtGyR1Y+w | QTJJKTejGE2H71sl2wcjBQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2.3 | 41904876 | 41906629 | Atlantic South - SOMDs and SPF - All Elevations | 1 |  |  |  | day | 2023-03-27 07:00 | 2023-05-08 17:00 | [12 empty] | 2 | 7 | VIfE4VzaWEGyOVW+1LOWiA | PCFAFGWsakK1+3lYK7yyLQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.12.2.4 | 41906648 | 41906629 | -- |  |  |  |  | day | [14 empty] | 3 | 7 | uyTK8CyC8kOLnqR4P8qZig | PCFAFGWsakK1+3lYK7yyLQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13 | 41906213 | 41904251 | Utilities Atlantic | 41 |  |  |  | day | 2023-01-23 07:00 | 2024-03-22 17:00 | [12 empty] | 12 | 5 | Dn8ntkD7JEuK0fKkpwYfmw | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13.1 | 41907061 | 41906213 | old |  |  |  |  | day | 2023-01-25 07:00 | 2023-02-03 17:00 | [12 empty] | 0 | 6 | 2TGZ0EdNMkuHfNLO0wmL6A | Dn8ntkD7JEuK0fKkpwYfmw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13.2 | 41907057 | 41906213 | ATLANTIC SECTION A - 31-29 Line | 25 |  |  |  | day | 2023-01-23 07:00 | 2024-03-22 17:00 | [12 empty] | 1 | 6 | QEOt6qOo+UO8IVFQZH4Lqw | Dn8ntkD7JEuK0fKkpwYfmw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13.2.1 | 43728946 | 41907057 | Slab Excluding Front Waiting on Bulletin for Turnstile Relocation |  |  |  |  | day | 2023-11-13 07:00 | 2024-01-10 17:00 | [12 empty] | 0 | 7 | VnWEG8Pack6MWu53/zWL9A | QEOt6qOo+UO8IVFQZH4Lqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13.2.2 | 43728944 | 41907057 | Perm CAT Egress | 39 |  |  |  | day | 2023-08-28 07:00 | 2024-02-27 17:00 | [12 empty] | 1 | 7 | CHUQuhctKky0zX0bo2noAA | QEOt6qOo+UO8IVFQZH4Lqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13.2.3 | 43728947 | 41907057 | Demolition of Temp CAT Egress | 32 |  |  |  | day | 2024-02-27 07:00 | 2024-03-22 17:00 | [12 empty] | 2 | 7 | aZpUCfXnQES4xVBxwR8dVg | QEOt6qOo+UO8IVFQZH4Lqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13.3 | 41907058 | 41906213 | ATLANTIC SECTION B - 29-28 Line | 8 |  |  |  | day | 2023-01-23 07:00 | 2024-01-09 17:00 | [12 empty] | 2 | 6 | OMI6sJCTTkyluFwye9t2Ig | Dn8ntkD7JEuK0fKkpwYfmw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13.4 | 41907059 | 41906213 | ATLANTIC SECTION C - 28-25 Line | 42 |  |  |  | day | 2023-02-02 07:00 | 2023-07-28 17:00 | [12 empty] | 3 | 6 | oM6qxSkhjk6k0tjD3H47/Q | Dn8ntkD7JEuK0fKkpwYfmw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13.4.1 | 42532961 | 41907059 | NEw | 47 |  |  |  | day | 2023-04-10 07:00 | 2023-04-27 17:00 | [12 empty] | 0 | 7 | OE184CYAF0KBTf3+V/Maxw | oM6qxSkhjk6k0tjD3H47/Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13.5 | 41907060 | 41906213 | ATLANTIC SECTION D - 25-19 Line |  |  |  |  | day | 2023-02-18 07:00 | 2024-01-23 17:00 | [12 empty] | 4 | 6 | c93jcAVMlkOufr1BDKxFMw | Dn8ntkD7JEuK0fKkpwYfmw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13.5.1 | 43728974 | 41907060 | I | 28 |  |  |  | day | [14 empty] | 0 | 7 | rlYMroDmXE2XQYbCr9IwWw | c93jcAVMlkOufr1BDKxFMw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.13.5.2 | 43728975 | 41907060 | II | 41 |  |  |  | day | [14 empty] | 1 | 7 | wWh1N8gMNk+ch+pcSpL3KQ | c93jcAVMlkOufr1BDKxFMw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.14 | 41905728 | 41904251 | Podium Foundations - Dorchester Ave | 25 |  |  |  | day | 2022-06-21 07:00 | 2022-07-15 17:00 | [12 empty] | 13 | 5 | ptWVBFYunUyBTOd7EbtUGg | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.14.1 | 41907067 | 41905728 | Chamber - BT | 34 |  |  |  | day | [14 empty] | 0 | 6 | tGpXkzcxuEqeUgoXnjzyjQ | ptWVBFYunUyBTOd7EbtUGg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.15 | 41904451 | 41904251 | Structural (Comeback) - Dorchester Ave | 49 |  |  |  | day | 2022-05-31 07:00 | 2022-09-22 17:00 | [12 empty] | 14 | 5 | 2e6K+5NeEEKJispPWWJ4aQ | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.15.1 | 41905371 | 41904451 | 12E | 24 |  |  |  | day | 2022-05-31 07:00 | 2022-07-27 17:00 | [12 empty] | 0 | 6 | Ja92zE3kt0CUljwLCyCQMQ | 2e6K+5NeEEKJispPWWJ4aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.15.2 | 41905337 | 41904451 | 08E - North |  |  |  |  | day | 2022-06-06 07:00 | 2022-07-05 17:00 | [12 empty] | 1 | 6 | 65+qLZHI2066rNSLpSi8CQ | 2e6K+5NeEEKJispPWWJ4aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.15.3 | 41905372 | 41904451 | 13E |  |  |  |  | day | 2022-06-08 07:00 | 2022-07-13 17:00 | [12 empty] | 2 | 6 | 3NNqsUVlyESdu5uvohO5+A | 2e6K+5NeEEKJispPWWJ4aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.15.4 | 41905373 | 41904451 | 14E - Assist Crane #4 - Dorchester Ave |  |  |  |  | day | 2022-07-20 07:00 | 2022-08-02 17:00 | [12 empty] | 3 | 6 | BePmYW2gMEGt53+5xv2Z1A | 2e6K+5NeEEKJispPWWJ4aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.15.5 | 41905429 | 41904451 | 15E - Assist Crane #4 - Dorchester Ave | 35 |  |  |  | day | 2022-07-27 07:00 | 2022-08-11 17:00 | [12 empty] | 4 | 6 | 9bkg9YcdoEKQif/v5DjeGg | 2e6K+5NeEEKJispPWWJ4aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.15.6 | 41905518 | 41904451 | 08E - South Assist Crane #4 - Dorchester Ave | 44 |  |  |  | day | 2022-08-05 07:00 | 2022-08-25 17:00 | [12 empty] | 5 | 6 | IGHkm5dqlE6xNyQ1l9CoXw | 2e6K+5NeEEKJispPWWJ4aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.15.7 | 41905430 | 41904451 | 16E - Assist Crane #4 - Dorchester Ave | 19 |  |  |  | day | 2022-08-10 07:00 | 2022-09-06 17:00 | [12 empty] | 6 | 6 | bL+3DJ3qGUG17bgDnOCLwg | 2e6K+5NeEEKJispPWWJ4aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.15.8 | 41905374 | 41904451 | 17E - Assist Crane #4 - Dorchester Ave |  |  |  |  | day | 2022-08-12 07:00 | 2022-09-09 17:00 | [12 empty] | 7 | 6 | 9BQY1QAPfEqPe3+oPGGl3w | 2e6K+5NeEEKJispPWWJ4aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.15.9 | 41906663 | 41904451 | Dorchester Ave - SOMDs and SPF - All Elevations |  |  |  |  | day | 2022-08-22 07:00 | 2022-09-22 17:00 | [12 empty] | 8 | 6 | L8iI+qoOdEiMfXyPM63qvQ | 2e6K+5NeEEKJispPWWJ4aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.15.10 | 41905446 | 41904451 | --- | 45 |  |  |  | day | [14 empty] | 9 | 6 | B6tx0lcZbEqWiGnyWubUng | 2e6K+5NeEEKJispPWWJ4aQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.16 | 41904546 | 41904251 | Structural (Tower Comeback) |  |  |  |  | day | [14 empty] | 15 | 5 | jTjzvLkkkkOj2NoPPIdpEA | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.16.1 | 41904804 | 41904546 | Structural P2 (EL +84.5') | 13 |  |  |  | day | [14 empty] | 0 | 6 | r8d7kCq72E2EmOzcGbn6Nw | jTjzvLkkkkOj2NoPPIdpEA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.16.2 | 41904805 | 41904546 | Structural P3 (EL +94.5') | 11 |  |  |  | day | [14 empty] | 1 | 6 | 4WaqV5dQZka8fbVKP/wZXw | jTjzvLkkkkOj2NoPPIdpEA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.16.3 | 41904806 | 41904546 | Structural P4 (EL +109') (Office Sky Street) | 22 |  |  |  | day | [14 empty] | 2 | 6 | nPQXXAGctEqGhQaJfqV2SA | jTjzvLkkkkOj2NoPPIdpEA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.16.4 | 41904807 | 41904546 | Structural P5 (EL +122') (L10) | 14 |  |  |  | day | [14 empty] | 3 | 6 | CMsOy+c/00CUAYzvXMHY/Q | jTjzvLkkkkOj2NoPPIdpEA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.16.5 | 41904808 | 41904546 | Structural L11 (EL +135') (Residential Sky Street) | 27 |  |  |  | day | [14 empty] | 4 | 6 | o/+iJ3SSIE+7/Ih4Ev42qw | jTjzvLkkkkOj2NoPPIdpEA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.16.6 | 41904809 | 41904546 | Structural L12 (EL +148) (Top of Walkway) | 33 |  |  |  | day | [14 empty] | 5 | 6 | kGf816S4Z0+0O5ylAyIX8A | jTjzvLkkkkOj2NoPPIdpEA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.17 | 41906672 | 41904251 | Structural P2-(Yellow Steel) | 1 |  |  |  | day | 2023-05-26 07:00 | 2024-04-01 17:00 | [12 empty] | 16 | 5 | UY2guVZ9R0SrJMvVIjaETg | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.17.1 | 41907064 | 41906672 | Chamber - Level 2 |  |  |  |  | day | [14 empty] | 0 | 6 | qAFk4lk3zUeuFkG1b+65Rw | UY2guVZ9R0SrJMvVIjaETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.17.2 | 41905339 | 41906672 | P5 - Comeback Yellow Steel |  |  |  |  | day | 2023-06-09 07:00 | 2023-12-04 17:00 | [12 empty] | 1 | 6 | q2uck2L6HkS7UDBQ/ZU50w | UY2guVZ9R0SrJMvVIjaETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.17.3 | 41905338 | 41906672 | P4 - Comeback Yellow Steel | 21 |  |  |  | day | 2023-05-26 07:00 | 2023-11-06 17:00 | [12 empty] | 2 | 6 | yz9vc07N90mvNq9PecuDHw | UY2guVZ9R0SrJMvVIjaETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.17.4 | 41905331 | 41906672 | P2 - Comeback Yellow Steel |  |  |  |  | day | 2023-05-26 07:00 | 2023-08-11 17:00 | [12 empty] | 3 | 6 | lTQ1MbVg6EO+zB2IJ6IdsA | UY2guVZ9R0SrJMvVIjaETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.17.5 | 41905343 | 41906672 | L11 - Comeback Yellow Steel |  |  |  |  | day | 2023-06-09 07:00 | 2024-02-13 17:00 | [12 empty] | 4 | 6 | Q7sLWNH/rE6VfG6Jhi5K1w | UY2guVZ9R0SrJMvVIjaETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.17.6 | 41905344 | 41906672 | L12 - Comeback Yellow Steel | 21 |  |  |  | day | 2023-07-11 07:00 | 2024-03-11 17:00 | [12 empty] | 5 | 6 | pTLBpR5uGESgwS5iS+IeIQ | UY2guVZ9R0SrJMvVIjaETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.17.7 | 41905332 | 41906672 | P3 - Comeback Yellow Steel | 48 |  |  |  | day | 2023-05-26 07:00 | 2023-09-15 17:00 | [12 empty] | 6 | 6 | T+thcvQp/0qyctt0h2QHhQ | UY2guVZ9R0SrJMvVIjaETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.17.8 | 41906673 | 41906672 | Comeback Yellow - SOMDs and SPF - All Elevations |  |  |  |  | day | 2023-11-10 07:00 | 2024-04-01 17:00 | [12 empty] | 7 | 6 | hlKh+tfNUUesroDpKEAH5g | UY2guVZ9R0SrJMvVIjaETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.18 | 41904427 | 41904251 | Stairs |  |  |  |  | day | 2022-11-14 07:00 | 2024-01-31 17:00 | [12 empty] | 17 | 5 | 9D+7Wui0xkStDynAuU5+FA | AQasnsoJA0aMZnck2jOpZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.18.1 | 41904652 | 41904427 | Atlantic St H-K | 14 |  |  |  | day | 2023-05-25 07:00 | 2024-01-31 17:00 | [12 empty] | 0 | 6 | SGpKvR9Ao0y5IlZymcM38g | 9D+7Wui0xkStDynAuU5+FA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.18.2 | 41904651 | 41904427 | Center/Bus B-H | 42 |  |  |  | day | 2022-11-14 07:00 | 2024-01-09 17:00 | [12 empty] | 1 | 6 | 7cl+P9uGQkCDGPAOtULKvg | 9D+7Wui0xkStDynAuU5+FA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.18.2.1 | 41905380 | 41904651 | H-F | 36 |  |  |  | day | 2023-07-11 07:00 | 2023-08-09 17:00 | [12 empty] | 0 | 7 | sHRaxzuQ6kCBcPg6KKMYnQ | 7cl+P9uGQkCDGPAOtULKvg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.18.2.2 | 41905378 | 41904651 | F-D | 32 |  |  |  | day | [14 empty] | 1 | 7 | du9eiD6bOUCMLAoZhhNqbQ | 7cl+P9uGQkCDGPAOtULKvg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.18.2.3 | 41905379 | 41904651 | D-B |  |  |  |  | day | [14 empty] | 2 | 7 | 6GEK2Pk/ZEC4U2Yo5CT8ng | 7cl+P9uGQkCDGPAOtULKvg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.3.18.3 | 41904650 | 41904427 | Summer St AA-B | 43 |  |  |  | day | 2023-01-24 07:00 | 2023-06-27 17:00 | [12 empty] | 2 | 6 | QeAeEuYMVEmm2nwepqsAqQ | 9D+7Wui0xkStDynAuU5+FA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.4 | 41905519 | 41904241 | SOMDs | 43 |  |  |  | day | 2021-10-25 07:00 | 2022-11-25 17:00 | [12 empty] | 3 | 4 | 2GkPwpqNF0ymOkxUds6eMA | Tk7ZcUqLokiVH5BGj9QkhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.4.1 | 41905520 | 41905519 | LR (+36) | 4 |  |  |  | day | 2021-10-25 07:00 | 2022-03-03 17:00 | [12 empty] | 0 | 5 | 9MTnWBivrUm/GwCBHT78Uw | 2GkPwpqNF0ymOkxUds6eMA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.4.2 | 41905521 | 41905519 | Bus Terminal (+49) | 38 |  |  |  | day | 2021-10-25 07:00 | 2022-03-01 17:00 | [12 empty] | 1 | 5 | 8pxA8lsAvUWKV/kyFk9wIw | 2GkPwpqNF0ymOkxUds6eMA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.4.3 | 41905522 | 41905519 | Structural P1 (EL +74.5') |  |  |  |  | day | 2022-03-07 07:00 | 2022-06-13 17:00 | [12 empty] | 2 | 5 | c6sEeLcVC0+nkAv/oWRclg | 2GkPwpqNF0ymOkxUds6eMA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.4.4 | 41905523 | 41905519 | Structural P2 (EL +84.5') | 5 |  |  |  | day | 2022-04-04 07:00 | 2022-06-23 17:00 | [12 empty] | 3 | 5 | ACrn+g+NK0KoOEZKW81iBA | 2GkPwpqNF0ymOkxUds6eMA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.4.5 | 41905524 | 41905519 | Structural P3 (EL +94.5') | 44 |  |  |  | day | 2022-04-25 07:00 | 2022-06-16 17:00 | [12 empty] | 4 | 5 | rCULXOB0uUS2TZMRVn2f/Q | 2GkPwpqNF0ymOkxUds6eMA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.4.6 | 41905525 | 41905519 | Structural P4 (EL +109') | 31 |  |  |  | day | 2022-05-23 07:00 | 2022-06-10 17:00 | [12 empty] | 5 | 5 | 0Aoq5epQeEKT5fXSSjDpiQ | 2GkPwpqNF0ymOkxUds6eMA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.4.7 | 41905526 | 41905519 | Structural P5 (EL +122') (L10) | 29 |  |  |  | day | 2022-07-11 07:00 | 2022-07-29 17:00 | [12 empty] | 6 | 5 | j80Rqf/odUeVP/d6ojrgAw | 2GkPwpqNF0ymOkxUds6eMA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.4.8 | 41905527 | 41905519 | Structural Roof L11 (EL +135') | 46 |  |  |  | day | 2022-08-01 07:00 | 2022-11-25 17:00 | [12 empty] | 7 | 5 | dtHxWNvhmkWMXB2e425zKw | 2GkPwpqNF0ymOkxUds6eMA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5 | 41904267 | 41904241 | Podium Facade | 34 |  |  |  | day | 2022-09-22 07:00 | 2024-10-03 17:00 | [12 empty] | 4 | 4 | bumRAMwJrU62wFtFDrl43g | Tk7ZcUqLokiVH5BGj9QkhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1 | 41904455 | 41904267 | Atlantic Ave Facade | 39 |  |  |  | day | 2023-04-24 07:00 | 2024-10-03 17:00 | [12 empty] | 0 | 5 | N8DD4yNnf0eOCeQmTdJxNw | bumRAMwJrU62wFtFDrl43g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.1 | 41906631 | 41904455 | South 19-25 | 15 |  |  |  | day | 2023-04-28 07:00 | 2024-02-29 17:00 | [12 empty] | 0 | 6 | H7K0wmdX90O1I/ufJneBww | N8DD4yNnf0eOCeQmTdJxNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.1.1 | 41906659 | 41906631 | EXT 01 - South Elevation - J.75 - G Line (1 Swing Drop) |  |  |  |  | day | 2023-05-09 07:00 | 2023-11-17 17:00 | [12 empty] | 0 | 7 | 3pcJHrsgGkWNsLqn680heg | H7K0wmdX90O1I/ufJneBww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.1.2 | 46578719 | 41906631 | ATLANTIC AVE GROUND FLOOR - EXT 02 03 04 | 49 |  |  |  | day | 2024-01-08 07:00 | 2024-02-29 17:00 | [12 empty] | 1 | 7 | s3yxvKt+ck2EwG2RGeAPUQ | H7K0wmdX90O1I/ufJneBww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.1.3 | 41906656 | 41906631 | EXT 02 - West Elevation - 19 - 21.5 Line - (1 Swing Drop) | 41 |  |  |  | day | 2023-05-18 07:00 | 2023-11-24 17:00 | [12 empty] | 2 | 7 | uO4MDXj9g0OAdkpB4jtppg | H7K0wmdX90O1I/ufJneBww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.1.4 | 41906633 | 41906631 | EXT 03 - Scrim Wall South Elevation - J.5 - J.75 Line - 1 Swing Drop) | 29 |  |  |  | day | 2023-05-18 07:00 | 2024-01-19 17:00 | [12 empty] | 3 | 7 | aXbSk/fYIk2s/CLGZNqGSw | H7K0wmdX90O1I/ufJneBww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.1.5 | 41906635 | 41906631 | EXT 05 - West Elevation - G line - 25 - 21.5 Line - (3 - Swing Drop or Roof Scaffolding | 18 |  |  |  | day | 2023-09-11 07:00 | 2024-02-06 17:00 | [12 empty] | 4 | 7 | TH5wYn8t7EeudE8Cd911pg | H7K0wmdX90O1I/ufJneBww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.1.6 | 41906632 | 41906631 | EXT 04 - West Elevation - 21.5 - 25 Line - (4 Swing Drops) |  |  |  |  | day | 2023-04-28 07:00 | 2023-11-29 17:00 | [12 empty] | 5 | 7 | LsW7Qmr1jkalHNFIAlTqXw | H7K0wmdX90O1I/ufJneBww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.1.7 | 41906634 | 41906631 | EXT 06 - Scrim Wall North Elevation - J.75 - G Line - (1 Swing Drop & Roof Scaffolding) | 18 |  |  |  | day | 2023-09-05 07:00 | 2024-01-05 17:00 | [12 empty] | 6 | 7 | eWI7e4E78U2DZow+/z67Nw | H7K0wmdX90O1I/ufJneBww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.2 | 41906630 | 41904455 | North 25-31 | 27 |  |  |  | day | 2023-04-24 07:00 | 2024-10-03 17:00 | [12 empty] | 1 | 6 | PLO42f6kaUCnIesPB089eA | N8DD4yNnf0eOCeQmTdJxNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.2.1 | 41906641 | 41906630 | EXT 07 - Sky Street Elevation - South, North & East Elevations | 25 |  |  |  | day | 2024-01-15 07:00 | 2024-07-24 17:00 | [12 empty] | 0 | 7 | raAwbcSdE0yWrOEykBILsQ | PLO42f6kaUCnIesPB089eA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.2.2 | 43728945 | 41906630 | Altantic North Storefront |  |  |  |  | day | 2024-03-25 07:00 | 2024-10-03 17:00 | [12 empty] | 1 | 7 | MV9bFVoCoUeBQ5t1Bl6XZw | PLO42f6kaUCnIesPB089eA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.2.3 | 41906640 | 41906630 | EXT 08 - Office West Elevation - Atlantic Ave Terrace - 28 - 31 Line | 25 |  |  |  | day | 2023-09-06 07:00 | 2024-02-16 17:00 | [12 empty] | 2 | 7 | V0NWXD0ElEW4P1DmCxw5ew | PLO42f6kaUCnIesPB089eA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.2.4 | 41906638 | 41906630 | EXT 09 - West Elevation - 25 - 27 Line - 1 Swing Drops) |  |  |  |  | day | 2023-04-24 07:00 | 2023-11-29 17:00 | [12 empty] | 3 | 7 | K/KfhumIvECvN+IJaWzPAQ | PLO42f6kaUCnIesPB089eA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.2.5 | 41906636 | 41906630 | EXT 10 - West Elevation - 27 - 28 Line - (4,000 sf - 40 Mast-climber ) | 8 |  |  |  | day | 2023-10-20 07:00 | 2024-05-03 17:00 | [12 empty] | 4 | 7 | qoljwvYN7EWQI4O7GyuFow | PLO42f6kaUCnIesPB089eA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.2.6 | 41906637 | 41906630 | EXT 11 - West Elevation - Shuttle Lobby - 28 - 31 Line | 11 |  |  |  | day | 2023-07-10 07:00 | 2024-05-20 17:00 | [12 empty] | 5 | 7 | p+PJmGbjLk+sLDPMi0EPvA | PLO42f6kaUCnIesPB089eA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.1.2.7 | 41906639 | 41906630 | EXT 12 - Podium Enlarged North Elevation ALT - H - J.75 Line | 0 |  |  |  | day | 2023-07-10 07:00 | 2023-08-28 17:00 | [12 empty] | 6 | 7 |  | PLO42f6kaUCnIesPB089eA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.2 | 41904456 | 41904267 | Dorchester Ave Facade | 0 |  |  |  | day | 2022-09-22 07:00 | 2023-11-21 17:00 | [12 empty] | 1 | 5 | rTa5BN13E0K09cl3siQNsg | bumRAMwJrU62wFtFDrl43g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.2.1 | 41906642 | 41904456 | EXT 13 - Service Core North Elevation |  |  |  |  | day | 2022-11-21 07:00 | 2023-11-03 17:00 | [12 empty] | 0 | 6 | ZJDXd5B/lEq9yZAdmCZSsw | rTa5BN13E0K09cl3siQNsg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.2.2 | 41906643 | 41904456 | EXT 14 - Service Core East Elevation | 33 |  |  |  | day | 2022-12-05 07:00 | 2023-11-08 17:00 | [12 empty] | 1 | 6 | 9cFSaBvp/UGO4a8K011gUg | rTa5BN13E0K09cl3siQNsg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.2.3 | 41906644 | 41904456 | EXT 15 - Stair 1C South Elevation | 31 |  |  |  | day | 2023-01-09 07:00 | 2023-11-10 17:00 | [12 empty] | 2 | 6 | FmPJKMZEL0ehPDKkJgGfVQ | rTa5BN13E0K09cl3siQNsg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.2.4 | 41906645 | 41904456 | EXT 16 - Service Core and Loading Dock South Elevation |  |  |  |  | day | 2023-01-09 07:00 | 2023-11-14 17:00 | [12 empty] | 3 | 6 | 57agvPavE0SdxIqQxGGFow | rTa5BN13E0K09cl3siQNsg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.2.5 | 41906646 | 41904456 | EXT 17 - Fan Tower East Elevation | 24 |  |  |  | day | 2022-09-23 07:00 | 2023-11-16 17:00 | [12 empty] | 4 | 6 | KHSUMTVpDE+mExqYzIjWiQ | rTa5BN13E0K09cl3siQNsg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.2.6 | 41906647 | 41904456 | EXT 18 - Fan Tower South Elevation | 39 |  |  |  | day | 2022-09-30 07:00 | 2023-11-21 17:00 | [12 empty] | 5 | 6 | qXN7e2D0UUqRccu6sKqkRw | rTa5BN13E0K09cl3siQNsg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.2.7 | 41904718 | 41904456 | Garage Elevator & Access Stairs at Roof |  |  |  |  | day | [14 empty] | 6 | 6 | xkeeFMVO0k+1N6QYb9DFtA | rTa5BN13E0K09cl3siQNsg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.2.8 | 41904713 | 41904456 | Garage Elevator & Parking Office at P1 | 0 |  |  |  | day | [14 empty] | 7 | 6 | NS3YISRSL0GcB4J/T2jooA | rTa5BN13E0K09cl3siQNsg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.3 | 41906674 | 41904267 | North Facade (Waiting on Yellow Steel) | 15 |  |  |  | day | 2024-04-01 07:00 | 2024-07-22 17:00 | [12 empty] | 2 | 5 | UlzJWQ1I00C4q9hSZqdYAQ | bumRAMwJrU62wFtFDrl43g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.3.1 | 41906675 | 41906674 | EXT 19 - North H-F (A4.06) |  |  |  |  | day | 2024-04-02 07:00 | 2024-06-07 17:00 | [12 empty] | 0 | 6 | BHQr1y3xFk+tdJxHmqzgNA | UlzJWQ1I00C4q9hSZqdYAQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.3.2 | 41906676 | 41906674 | EXT 20 |  |  |  |  | day | 2024-04-17 07:00 | 2024-07-22 17:00 | [12 empty] | 1 | 6 | 6oGmbJDbFkOYnpBgSRZDQg | UlzJWQ1I00C4q9hSZqdYAQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.4 | 41906705 | 41904267 | Rooftop Elevator, Stair and Storage Exteriors | 21 |  |  |  | day | 2022-11-23 07:00 | 2023-11-29 17:00 | [12 empty] | 3 | 5 | kJzWyRGVl0KCzsHvQbh5nA | bumRAMwJrU62wFtFDrl43g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.4.1 | 41906706 | 41906705 | EXT 21 - Stair 6B and SE06 & SE07 | 28 |  |  |  | day | 2022-12-15 07:00 | 2023-11-23 17:00 | [12 empty] | 0 | 6 | 6tOzrKMvm0q6v6jdHkOh6g | kJzWyRGVl0KCzsHvQbh5nA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.4.2 | 41906707 | 41906705 | EXT 22 - Stair 6C | 2 |  |  |  | day | 2022-11-27 07:00 | 2023-11-27 17:00 | [12 empty] | 1 | 6 | 4am1zg31UUKRIq+o2DS2eg | kJzWyRGVl0KCzsHvQbh5nA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.4.3 | 41906708 | 41906705 | EXT 23 - Stair 7 | 11 |  |  |  | day | 2022-11-23 07:00 | 2023-11-29 17:00 | [12 empty] | 2 | 6 | 5VWu3ql32Eu9aIfD5jrBxQ | kJzWyRGVl0KCzsHvQbh5nA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.4.4 | 41906709 | 41906705 | EXT 24 - Storage | 25 |  |  |  | day | [14 empty] | 3 | 6 | 8AdMBpcWfUiZhg+b4SPhvA | kJzWyRGVl0KCzsHvQbh5nA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.5.5 | 41904461 | 41904267 | Elevator and Escalator at Platform | 15 |  |  |  | day | 2024-08-09 07:00 | 2024-09-12 17:00 | [12 empty] | 4 | 5 | wyVXlYM1G0igce2q644HjQ | bumRAMwJrU62wFtFDrl43g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6 | 41904276 | 41904241 | Podium Roofing | 36 |  |  |  | day | 2022-12-27 07:00 | 2024-09-30 17:00 | [12 empty] | 5 | 4 | //vJC2fsiEGnywSQGe7RhQ | Tk7ZcUqLokiVH5BGj9QkhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.1 | 41905376 | 41904276 | Shuttle Lobby Canopy (EL +42) | 21 |  |  |  | day | [14 empty] | 0 | 5 | Qx5ebYRARkej/6zlB1K4Tg | //vJC2fsiEGnywSQGe7RhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.1.1 | 41905377 | 41905376 | Outdoor Terrace - Hot Fluid Applied Roofing | 28 |  |  |  | day | [14 empty] | 0 | 6 | lc9r2xqANUWy1WLkiyIlyw | Qx5ebYRARkej/6zlB1K4Tg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.2 | 45047845 | 41904276 | Roofing L14 (EL+ 174') |  |  |  |  | day | 2024-01-15 07:00 | 2024-04-29 17:00 | [12 empty] | 1 | 5 | UY/sKupI7UytCGUUsSSvbA | //vJC2fsiEGnywSQGe7RhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.2.1 | 41906702 | 45047845 | ROF 15 - Hot Fluid Applied Rubberized Asphalt Waterproofing Roof - Atlantic Elevators | 27 |  |  |  | day | 2024-01-15 07:00 | 2024-04-29 17:00 | [12 empty] | 0 | 6 | AzDz2/UtzkGHy4M6YiDxBw | UY/sKupI7UytCGUUsSSvbA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.2.1.1 | 41906703 | 41906702 | Temp Roof |  |  |  |  | day | 2024-01-15 07:00 | 2024-01-23 17:00 | [12 empty] | 0 | 7 | eN5IN+m7g0K04HOXC+/M3w | AzDz2/UtzkGHy4M6YiDxBw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.2.1.2 | 41906704 | 41906702 | Permanent Roof | 46 |  |  |  | day | 2024-01-24 07:00 | 2024-04-29 17:00 | [12 empty] | 1 | 7 | hglaCHuua0iuT9ivP4WDxg | AzDz2/UtzkGHy4M6YiDxBw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.3 | 41904462 | 41904276 | Roofing P4 (EL +109') | 48 |  |  |  | day | 2023-10-16 07:00 | 2024-09-30 17:00 | [12 empty] | 2 | 5 | xbGNO2pX1kG/72pVwKeJTg | //vJC2fsiEGnywSQGe7RhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.3.1 | 41904720 | 41904462 | ROF 01 - Top of BOH Atlantic - PVC Roofing | 29 |  |  |  | day | 2023-10-30 07:00 | 2024-02-12 17:00 | [12 empty] | 0 | 6 | sJmAYgFFW0ONQ9FydzNATw | xbGNO2pX1kG/72pVwKeJTg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.3.1.1 | 41906664 | 41904720 | Temp Roof |  |  |  |  | day | 2023-10-30 07:00 | 2023-11-01 17:00 | [12 empty] | 0 | 7 | OXDfVK6HXEmCxDbchC8PBg | sJmAYgFFW0ONQ9FydzNATw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.3.1.2 | 41906665 | 41904720 | Permanent Roof | 4 |  |  |  | day | 2024-01-24 07:00 | 2024-02-12 17:00 | [12 empty] | 1 | 7 | tRQWhfaFSEi7E4x9MShQIA | sJmAYgFFW0ONQ9FydzNATw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.3.2 | 41904719 | 41904462 | ROF 02 - Outdoor Terrace - Hot Fluid Applied Roofing | 11 |  |  |  | day | 2023-10-16 07:00 | 2024-09-30 17:00 | [12 empty] | 1 | 6 | 51+DOQSsgku0dO/izGynMw | xbGNO2pX1kG/72pVwKeJTg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.3.2.1 | 41906666 | 41904719 | Temp Roof |  |  |  |  | day | 2023-10-16 07:00 | 2024-01-09 17:00 | [12 empty] | 0 | 7 | Q6joYYcN7EaSBA3gTls4Rg | 51+DOQSsgku0dO/izGynMw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.3.2.2 | 41906667 | 41904719 | Permanent Roof | 25 |  |  |  | day | 2024-09-20 07:00 | 2024-09-30 17:00 | [12 empty] | 1 | 7 | YLzze3uJsE6B5iDmfBlU8Q | 51+DOQSsgku0dO/izGynMw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.4 | 41904463 | 41904276 | Roofing P5 (EL +122') | 25 |  |  |  | day | 2022-12-27 07:00 | 2023-10-27 17:00 | [12 empty] | 3 | 5 | wybY6zrEEU63BvH+DV8Sww | //vJC2fsiEGnywSQGe7RhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.4.1 | 41904721 | 41904463 | ROF 03 - Bus/Train Exhaust Fan - PVC Roofing | 47 |  |  |  | day | 2022-12-27 07:00 | 2023-10-27 17:00 | [12 empty] | 0 | 6 | bRQBpxyJLkmCUt8ZoLPB9w | wybY6zrEEU63BvH+DV8Sww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.4.1.1 | 41906668 | 41904721 | Temp Roof | 20 |  |  |  | day | 2022-12-27 07:00 | 2022-12-30 17:00 | [12 empty] | 0 | 7 | cybjQOYcYkG9/qm/1YeEpA | bRQBpxyJLkmCUt8ZoLPB9w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.4.1.2 | 41906669 | 41904721 | Permanent Roof |  |  |  |  | day | 2023-06-12 07:00 | 2023-10-27 17:00 | [12 empty] | 1 | 7 | 9EbGDC8HC0KkP4EHuiWIsw | bRQBpxyJLkmCUt8ZoLPB9w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5 | 41904464 | 41904276 | Roofing L11 (EL +135') | 35 |  |  |  | day | 2023-12-26 07:00 | 2024-08-12 17:00 | [12 empty] | 4 | 5 | xXYWlgTWbUyotExFpz+i6Q | //vJC2fsiEGnywSQGe7RhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.1 | 41904722 | 41904464 | ROF 04 - Main Podium - EPDM Roof w Landscaping - J.5-H | 32 |  |  |  | day | 2023-12-26 07:00 | 2024-06-25 17:00 | [12 empty] | 0 | 6 | KVD0u8F8/EGZRx5ZKgZaQA | xXYWlgTWbUyotExFpz+i6Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.1.1 | 41906670 | 41904722 | Temp Roof |  |  |  |  | day | 2023-12-26 07:00 | 2024-01-25 17:00 | [12 empty] | 0 | 7 | P/zPsCrXg0yjuVuNHgUfWA | KVD0u8F8/EGZRx5ZKgZaQA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.1.2 | 41906671 | 41904722 | Permanent Roof |  |  |  |  | day | 2024-06-05 07:00 | 2024-06-25 17:00 | [12 empty] | 1 | 7 | 0rEOp2uKJEatc6ac3ORYew | KVD0u8F8/EGZRx5ZKgZaQA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.2 | 41905375 | 41904464 | ROF 06 - Main Podium - EPDM Roof w Landscaping - E-B | 22 |  |  |  | day | 2023-12-26 07:00 | 2024-08-12 17:00 | [12 empty] | 1 | 6 | WHHRsmRx4kuum0osydW3iQ | xXYWlgTWbUyotExFpz+i6Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.2.1 | 41906795 | 41905375 | Temp Roof | 9 |  |  |  | day | 2023-12-26 07:00 | 2024-01-25 17:00 | [12 empty] | 0 | 7 | m+c0aJpe/km9nnqKIMCuEQ | WHHRsmRx4kuum0osydW3iQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.2.2 | 41906686 | 41905375 | Permanent Roof | 4 |  |  |  | day | 2024-03-11 07:00 | 2024-08-12 17:00 | [12 empty] | 1 | 7 | vnKD1ATI2US6WJdHRzKi8A | WHHRsmRx4kuum0osydW3iQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.3 | 41905381 | 41904464 | ROF 05 - Main Podium - EPDM Roof w Landscaping - H-E | 35 |  |  |  | day | 2023-12-26 07:00 | 2024-07-30 17:00 | [12 empty] | 2 | 6 | B3bYUASKkkK4CkBhLqkhWA | xXYWlgTWbUyotExFpz+i6Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.3.1 | 41906796 | 41905381 | Temp Roof |  |  |  |  | day | 2023-12-26 07:00 | 2024-01-25 17:00 | [12 empty] | 0 | 7 | sV5D3DvVikW2v1tutf46bA | B3bYUASKkkK4CkBhLqkhWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.3.2 | 41906687 | 41905381 | Permanent Roof |  |  |  |  | day | 2024-03-11 07:00 | 2024-07-30 17:00 | [12 empty] | 1 | 7 | WOxb3C6jUkWHIMRM/FAWmQ | B3bYUASKkkK4CkBhLqkhWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.4 | 41906677 | 41904464 | ROF 07 - Main Podium - Yellow Steel Comeback | 9 |  |  |  | day | 2024-04-02 07:00 | 2024-07-18 17:00 | [12 empty] | 3 | 6 | tjDMVUY5mEife9BH9aNAlg | xXYWlgTWbUyotExFpz+i6Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.4.1 | 41906684 | 41906677 | Temp Roof | 18 |  |  |  | day | 2024-04-02 07:00 | 2024-04-23 17:00 | [12 empty] | 0 | 7 | Ci23u2Vgqki/BMdeG9bhNg | tjDMVUY5mEife9BH9aNAlg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.5.4.2 | 41906685 | 41906677 | Permanent Roof | 31 |  |  |  | day | 2024-04-24 07:00 | 2024-07-18 17:00 | [12 empty] | 1 | 7 | dBp+Zzj9AUyWNpfXnDwVbA | tjDMVUY5mEife9BH9aNAlg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6 | 41904465 | 41904276 | Roofing L12 (EL+148') | 0 |  |  |  | day | 2023-08-14 07:00 | 2024-05-21 17:00 | [12 empty] | 5 | 5 | w+gXifgeN0ioizLPd2oAqQ | //vJC2fsiEGnywSQGe7RhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.1 | 41904716 | 41904465 | ROF 12 - Top of Walkway - EPDM Roof w Landscaping (Waiting on Yellow Steel) |  |  |  |  | day | 2024-04-02 07:00 | 2024-05-21 17:00 | [12 empty] | 0 | 6 | s98K/BAzNkmlLvVtZjPVsg | w+gXifgeN0ioizLPd2oAqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.1.1 | 41906688 | 41904716 | Temp Roof | 44 |  |  |  | day | 2024-04-02 07:00 | 2024-04-23 17:00 | [12 empty] | 0 | 7 | kGaiDzRmgUejf8FXRzc63A | s98K/BAzNkmlLvVtZjPVsg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.1.2 | 41906689 | 41904716 | Permanent Roof | 3 |  |  |  | day | 2024-04-24 07:00 | 2024-05-21 17:00 | [12 empty] | 1 | 7 | UbecnZ4K00WS27V5CAvH3A | s98K/BAzNkmlLvVtZjPVsg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.2 | 41906678 | 41904465 | ROF 08 - SBS Modified Bituminous Roof - Stair 6A and SE06 & SE07 | 15 |  |  |  | day | 2023-09-18 07:00 | 2024-01-02 17:00 | [12 empty] | 1 | 6 | fSaajGlX9UyZlFoxrnmtAQ | w+gXifgeN0ioizLPd2oAqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.2.1 | 41906690 | 41906678 | Temp Roof | 23 |  |  |  | day | 2023-09-18 07:00 | 2023-09-22 17:00 | [12 empty] | 0 | 7 | kuYD5sf0/UeXK8ZqCdcaeQ | fSaajGlX9UyZlFoxrnmtAQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.2.2 | 41906691 | 41906678 | Permanent Roof | 15 |  |  |  | day | 2023-09-20 07:00 | 2024-01-02 17:00 | [12 empty] | 1 | 7 | kcY7WDPrIk27ej1TD+AOWQ | fSaajGlX9UyZlFoxrnmtAQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.3 | 41906679 | 41904465 | ROF 09 - SBS Modified Bituminous Roof - Stair 6B | 1 |  |  |  | day | 2023-09-25 07:00 | 2024-01-03 17:00 | [12 empty] | 2 | 6 | +uL1ndvA8UORwv+6N0bAkA | w+gXifgeN0ioizLPd2oAqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.3.1 | 41906692 | 41906679 | Temp Roof |  |  |  |  | day | 2023-09-25 07:00 | 2023-09-27 17:00 | [12 empty] | 0 | 7 | eAKEEY570UaTYAPN/ydBTg | +uL1ndvA8UORwv+6N0bAkA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.3.2 | 41906693 | 41906679 | Permanent Roof | 27 |  |  |  | day | 2023-09-25 07:00 | 2024-01-03 17:00 | [12 empty] | 1 | 7 | XzSG44QaKE+YiuXMsMvGiA | +uL1ndvA8UORwv+6N0bAkA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.4 | 41906680 | 41904465 | ROF 10 - SBS Modified Bituminous Roof - Stair 7 | 31 |  |  |  | day | 2023-09-26 07:00 | 2024-01-02 17:00 | [12 empty] | 3 | 6 | 4Z0eHMp9xkqaYkMtASJwIQ | w+gXifgeN0ioizLPd2oAqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.4.1 | 41906694 | 41906680 | Temp Roof | 26 |  |  |  | day | 2023-09-26 07:00 | 2023-09-28 17:00 | [12 empty] | 0 | 7 |  | 4Z0eHMp9xkqaYkMtASJwIQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.4.2 | 41906695 | 41906680 | Permanent Roof | 19 |  |  |  | day | 2023-09-26 07:00 | 2024-01-02 17:00 | [12 empty] | 1 | 7 | Ld/jtKqkrkqFEEqefHCZaw | 4Z0eHMp9xkqaYkMtASJwIQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.5 | 41906681 | 41904465 | ROF 11 - SBS Modified Bituminous Roof - Storage (Deleted Bulletin 060) |  |  |  |  | day | [14 empty] | 4 | 6 | iN0KaC+I5E2FOlr+yI7mGQ | w+gXifgeN0ioizLPd2oAqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.5.1 | 41906696 | 41906681 | Temp Roof |  |  |  |  | day | [14 empty] | 0 | 7 | UpJPnL5UMkubpQy8SyN1xA | iN0KaC+I5E2FOlr+yI7mGQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.5.2 | 41906697 | 41906681 | Permanent Roof | 49 |  |  |  | day | [14 empty] | 1 | 7 | MGqWa/b3I0+hVsXXsF/V9Q | iN0KaC+I5E2FOlr+yI7mGQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.6 | 41906682 | 41904465 | ROF 14 - Hot Fluid Applied Rubberized Asphalt Waterproofing Roof - Service Core - Stair 1E and | 34 |  |  |  | day | 2023-08-14 07:00 | 2024-01-18 17:00 | [12 empty] | 5 | 6 | kDL/R7gWvEq8/JdCeJ78rg | w+gXifgeN0ioizLPd2oAqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.6.1 | 41906698 | 41906682 | Temp Roof | 32 |  |  |  | day | 2023-08-14 07:00 | 2023-09-11 17:00 | [12 empty] | 0 | 7 | z2VlesXxY0CNzGp1AH5bIg | kDL/R7gWvEq8/JdCeJ78rg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.6.2 | 41906699 | 41906682 | Permanent Roof | 32 |  |  |  | day | 2023-09-04 07:00 | 2024-01-18 17:00 | [12 empty] | 1 | 7 | gbQyh+vxyEWF57hO/2Kk/g | kDL/R7gWvEq8/JdCeJ78rg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.7 | 41906683 | 41904465 | ROF 13 - Hot Fluid Applied Rubberized Asphalt Waterproofing Roof - GE01 & GE02 | 42 |  |  |  | day | 2023-12-26 07:00 | 2024-02-12 17:00 | [12 empty] | 6 | 6 | WxyVsAWGrU+WAWIeogOFXA | w+gXifgeN0ioizLPd2oAqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.7.1 | 41906700 | 41906683 | Temp Roof | 36 |  |  |  | day | 2023-12-26 07:00 | 2024-01-04 17:00 | [12 empty] | 0 | 7 | 935Yieg10ES02sLBH5z97w | WxyVsAWGrU+WAWIeogOFXA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.6.6.7.2 | 41906701 | 41906683 | Permanent Roof |  |  |  |  | day | 2024-01-05 07:00 | 2024-02-12 17:00 | [12 empty] | 1 | 7 | GVCaNtc9/0uHEMK+a/ojVw | WxyVsAWGrU+WAWIeogOFXA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7 | 41904277 | 41904241 | Podium Elevators & Escalators |  |  |  |  | day | 2022-12-27 07:00 | 2025-05-30 17:00 | [12 empty] | 6 | 4 | yQUHZNUyAUmLGbMeSjImNw | Tk7ZcUqLokiVH5BGj9QkhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.1 | 45225227 | 41904277 | Podium Elevator Summary | 0 |  |  |  | day | 2023-12-26 07:00 | 2025-05-30 17:00 | [12 empty] | 0 | 5 | wH7jce3FkkudUXISseDpVg | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.2 | 41906222 | 41904277 | GE3-4 (Waiting on Taking the Platform & Yellow Steel) | 32 |  |  |  | day | 2023-04-24 07:00 | 2024-07-18 17:00 | [12 empty] | 1 | 5 | 2zhwkugcxUSRxgEUCOqXDQ | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.3 | 41906223 | 41904277 | GE5 Roped Hydro | 39 |  |  |  | day | 2023-12-26 07:00 | 2024-06-05 17:00 | [12 empty] | 2 | 5 | mh6aaNgYYUS5d0dqkJnpyA | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.4 | 41906224 | 41904277 | SE4-5 | 9 |  |  |  | day | 2024-01-19 07:00 | 2024-08-06 17:00 | [12 empty] | 3 | 5 | kjJmoKAxoECGP/ehcy9iug | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.5 | 41906225 | 41904277 | Escalator 1 (Waiting on Tower Foundation) | 42 |  |  |  | day | 2022-12-27 07:00 | 2024-06-07 17:00 | [12 empty] | 4 | 5 | wWXjzhrtKkOUWs39PgfCwQ | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.6 | 41906226 | 41904277 | Escalator 2 (Waiting on Tower Foundation) |  |  |  |  | day | 2023-05-31 07:00 | 2024-06-14 17:00 | [12 empty] | 5 | 5 | GfbVhk0IxEiH1yEDZ/W4vg | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.7 | 41906227 | 41904277 | GE1-2 (Waiting on Steel and Approval of 013100-10) | 28 |  |  |  | day | 2025-01-31 07:00 | 2025-05-30 17:00 | [12 empty] | 6 | 5 | jsuZEUMF+ki53WXVrgf8WA | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.8 | 41906228 | 41904277 | PE18-19 Jump | 12 |  |  |  | day | 2024-01-15 07:00 | 2024-08-06 17:00 | [12 empty] | 7 | 5 | 688x3TJt3UOs6cGWfFT//Q | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.9 | 41906229 | 41904277 | PE 20-21 | 11 |  |  |  | day | 2024-01-15 07:00 | 2024-08-15 17:00 | [12 empty] | 8 | 5 | b5zojZLRBkqd+cCgN+T19A | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.10 | 41906230 | 41904277 | SE6-7 | 30 |  |  |  | day | 2024-02-07 07:00 | 2024-08-01 17:00 | [12 empty] | 9 | 5 | MnhtaSEeJUudXMaa1c1+Cw | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.11 | 41906231 | 41904277 | PE 22 | 45 |  |  |  | day | 2024-01-15 07:00 | 2024-08-15 17:00 | [12 empty] | 10 | 5 | T5kAYm7pmUCKpccIQ7GGZg | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.12 | 41906232 | 41904277 | PE 23-24 | 1 |  |  |  | day | 2024-01-15 07:00 | 2024-08-15 17:00 | [12 empty] | 11 | 5 | 84VK9HmU0EqzYmE6vcElSA | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.7.13 | 41906233 | 41904277 | PE 16-17 |  |  |  |  | day | 2024-01-15 07:00 | 2024-07-11 17:00 | [12 empty] | 12 | 5 | /O0z403skkmZPa6KaSLZrQ | yQUHZNUyAUmLGbMeSjImNw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8 | 41904265 | 41904241 | Podium Rough MEP & Finishes | 39.8927 | 2023-09-10 08:00 | 2023-10-13 17:00 | 20 | day | 2021-07-08 07:00 | 2025-02-07 17:00 | [12 empty] | 7 | 4 | t1PjyV/kJkSV1+bBZ6hoUw | Tk7ZcUqLokiVH5BGj9QkhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1 | 41906722 | 41904265 | Office and Resident Lobbys | 22 |  |  |  | day | 2024-01-30 07:00 | 2025-02-07 17:00 | [12 empty] | 0 | 5 | Jw9BbZ/yAEyn21FwarAiUA | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.1 | 41906710 | 41906722 | Ground Floor - Lower Shuttle Lobby & Lower Residental Lobby | 16 |  |  |  | day | 2024-01-30 07:00 | 2025-01-23 17:00 | [12 empty] | 0 | 6 | dC2eQwttb0uDaJuzriEhZA | Jw9BbZ/yAEyn21FwarAiUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.1.1 | 41906714 | 41906710 | Rough |  |  |  |  | day | 2024-01-30 07:00 | 2024-10-03 17:00 | [12 empty] | 0 | 7 | TmMmX5jcl0a7CHw9g6+PcA | dC2eQwttb0uDaJuzriEhZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.1.2 | 41906715 | 41906710 | Finishes | 7 |  |  |  | day | 2024-10-04 07:00 | 2025-01-23 17:00 | [12 empty] | 1 | 7 | EBKcsMz7T0GY2Y6hzRfIqA | dC2eQwttb0uDaJuzriEhZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.2 | 41906711 | 41906722 | P4 - Sky Street Lobby & Amenities Space (Double Height Space) - Sky Street Connector Lobby | 28 |  |  |  | day | 2024-04-02 07:00 | 2025-01-10 17:00 | [12 empty] | 1 | 6 | WMcAuaLSykiM2D9VHve7Tw | Jw9BbZ/yAEyn21FwarAiUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.2.1 | 41906716 | 41906711 | Rough | 25 |  |  |  | day | 2024-04-02 07:00 | 2024-09-06 17:00 | [12 empty] | 0 | 7 | 2LRTD9UPnkOt2VbMl3/bvg | WMcAuaLSykiM2D9VHve7Tw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.2.2 | 41906717 | 41906711 | Finishes | 9 |  |  |  | day | 2024-08-30 07:00 | 2025-01-10 17:00 | [12 empty] | 1 | 7 | 4Hc+oF2SWEKbwfUlJfEiHA | WMcAuaLSykiM2D9VHve7Tw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.3 | 41906712 | 41906722 | P4 - Sky Street Lobby & Amenities Space (Double Height Space) - Tower Lobby | 25 |  |  |  | day | 2024-04-24 07:00 | 2025-02-07 17:00 | [12 empty] | 2 | 6 | jHTYbICbWUmDttjUkN3tWw | Jw9BbZ/yAEyn21FwarAiUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.3.1 | 41906718 | 41906712 | Rough |  |  |  |  | day | 2024-04-24 07:00 | 2024-09-27 17:00 | [12 empty] | 0 | 7 | aoAMw2nvFke+F9wbLYHwiA | jHTYbICbWUmDttjUkN3tWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.3.2 | 41906719 | 41906712 | Finishes | 40 |  |  |  | day | 2024-09-23 07:00 | 2025-02-07 17:00 | [12 empty] | 1 | 7 | M/+VbT7GYkW9+4Yily+Jqw | jHTYbICbWUmDttjUkN3tWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.4 | 41906713 | 41906722 | 11th - Floor Residential Sky Street | 6 |  |  |  | day | 2024-05-01 07:00 | 2024-11-04 17:00 | [12 empty] | 3 | 6 | nnZDORBQCk+LKytyaj0Y8A | Jw9BbZ/yAEyn21FwarAiUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.4.1 | 41906720 | 41906713 | Rough | 3 |  |  |  | day | 2024-05-01 07:00 | 2024-08-15 17:00 | [12 empty] | 0 | 7 | yxauLjtapkqWzmE3bjX7WQ | nnZDORBQCk+LKytyaj0Y8A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.1.4.2 | 41906721 | 41906713 | Finishes | 49 |  |  |  | day | 2024-08-09 07:00 | 2024-11-04 17:00 | [12 empty] | 1 | 7 | ey9JxRQWwU6Mzg+uuZhFdg | nnZDORBQCk+LKytyaj0Y8A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.2 | 41904428 | 41904265 | Summary Podium Rough & Finishes | 44 |  |  |  | day | 2022-02-07 07:00 | 2024-07-01 17:00 | [12 empty] | 1 | 5 | G0kpyQTwWEW0zV4TWOAOVw | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.2.1 | 41905146 | 41904428 | Work Under Platform A | 10 |  |  |  | day | [14 empty] | 0 | 6 | d2g88X5Ua0q5rLyxBUxg1A | G0kpyQTwWEW0zV4TWOAOVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.2.2 | 41904755 | 41904428 | Summary Podium Rough & Finishes |  |  |  |  | day | 2022-02-07 07:00 | 2024-07-01 17:00 | [12 empty] | 1 | 6 | V17cQ5xTCEC3ae/EiD7QHA | G0kpyQTwWEW0zV4TWOAOVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.2.3 | 41906624 | 41904428 | BT Summary (EL +49') |  |  |  |  | day | [14 empty] | 2 | 6 | VkjLVmwo4EK6R8xomQoEIQ | G0kpyQTwWEW0zV4TWOAOVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.3 | 41904424 | 41904265 | Podium Risers | 24 |  |  |  | day | [14 empty] | 2 | 5 | vh9thxAfekqIbScHt/Uo9g | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.3.1 | 41904723 | 41904424 | Risers - Atlantic Ave - H-J.5 Line | 20 |  |  |  | day | [14 empty] | 0 | 6 | cN8F2f8kVECGBsvpp/uZLA | vh9thxAfekqIbScHt/Uo9g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.3.2 | 41904724 | 41904424 | Risers - Dorchester Ave - B-AA Line | 35 |  |  |  | day | [14 empty] | 1 | 6 | 2V2UdnQ5/UOpln1mevPgnw | vh9thxAfekqIbScHt/Uo9g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.3.2.1 | 41904831 | 41904724 | Track and Bus Ventilation Risers | 9 |  |  |  | day | [14 empty] | 0 | 7 | GaV+zfghCUGmvHKZFMlP2w | 2V2UdnQ5/UOpln1mevPgnw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.4 | 41904426 | 41904265 | Podium Rough and Finishes Lower Level (EL +3') | 36 |  |  |  | day | [14 empty] | 3 | 5 | j8Qhyocju0KeWdPPd6vfcw | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5 | 41904425 | 41904265 | Podium Rough and Finishes Track Level (EL +18') | 45.8927 | 2023-09-07 08:00 | 2023-10-10 17:00 | 20 | day | 2021-08-19 07:00 | 2024-09-28 17:00 | [12 empty] | 4 | 5 | 30/RaML5QkWEGrPnTou+bw | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.1 | 41905382 | 41904425 | Pre CMP-10 - Temp Normal Fans F.5 Line (Canopy B) | 23 |  |  |  | day | 2021-08-19 07:00 | 2021-12-05 17:00 | [12 empty] | 0 | 6 | BzavyJBu6ESU4jHX9Cg8gQ | 30/RaML5QkWEGrPnTou+bw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2 | 41904399 | 41904425 | CMP-10&11 - Plenum - Underside Work (M-F 8:00pm to 4:30am) | 47.8927 | 2023-09-07 08:00 | 2023-10-04 17:00 | 20 | day | 2022-01-12 07:00 | 2024-09-28 17:00 | [12 empty] | 1 | 6 | 3gNfq5uBQU208nbZyDqCzA | 30/RaML5QkWEGrPnTou+bw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.1 | 41905672 | 41904399 | Summary | 48 |  |  |  | day | 2022-02-03 07:00 | 2023-06-19 17:00 | [12 empty] | 0 | 7 | DPw3Fzh1EUSwFria1LPJCw | 3gNfq5uBQU208nbZyDqCzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.1.1 | 41905726 | 41905672 | Temp Fans & Dampers |  |  |  |  | day | 2022-02-10 07:00 | 2022-07-08 17:00 | [12 empty] | 0 | 8 | pOZ5xJCmO0uaExVKXUbgsg | DPw3Fzh1EUSwFria1LPJCw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.1.2 | 41905674 | 41905672 | Phase 1 - Temp MEPs | 47 |  |  |  | day | 2022-02-22 07:00 | 2022-04-08 17:00 | [12 empty] | 1 | 8 | IqV6ppShR0evPLgxKk0aQw | DPw3Fzh1EUSwFria1LPJCw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.1.3 | 41905673 | 41905672 | Phase 2 - Bracket Install and Catenary Relocation Off Canopies | 35 |  |  |  | day | 2022-02-03 07:00 | 2022-03-26 17:00 | [12 empty] | 2 | 8 | dY0kb1qCd0SH+rcx07XhNA | DPw3Fzh1EUSwFria1LPJCw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.1.4 | 41905675 | 41905672 | Phase 3 - Demo Canopies | 17 |  |  |  | day | 2022-04-19 07:00 | 2022-07-01 17:00 | [12 empty] | 3 | 8 | XCm6vWSsukCirHpoOPmkqw | DPw3Fzh1EUSwFria1LPJCw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.1.5 | 41906212 | 41905672 | Phase 4 - Lath/Steel Installation | 48 |  |  |  | day | 2022-07-05 07:00 | 2023-02-14 17:00 | [12 empty] | 4 | 8 | xQStPNdeYE6AK0HM9ZdjKA | DPw3Fzh1EUSwFria1LPJCw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.1.6 | 41905676 | 41905672 | Phase 5 - Spray Fireproofing |  |  |  |  | day | 2022-07-05 07:00 | 2022-09-27 17:00 | [12 empty] | 5 | 8 | ly109BAD1EGOnFZ5DmEUtQ | DPw3Fzh1EUSwFria1LPJCw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.1.7 | 41905677 | 41905672 | Phase 6 - Permanent MEP Install |  |  |  |  | day | 2023-04-05 07:00 | 2023-06-19 17:00 | [12 empty] | 6 | 8 | DHTU95pMrkyuBzhvk/HV0Q | DPw3Fzh1EUSwFria1LPJCw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.2 | 41905383 | 41904399 | Temp Normal Fans B.5 Line (Canopy F) | 23 |  |  |  | day | 2022-01-12 07:00 | 2022-03-09 17:00 | [12 empty] | 1 | 7 | sTcbIrjgHUKt/rTPjof9nA | 3gNfq5uBQU208nbZyDqCzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.3 | 41906208 | 41904399 | Phase 1 - Temp MEPs | 22 |  |  |  | day | 2022-02-22 07:00 | 2022-04-08 17:00 | [12 empty] | 2 | 7 | a5aSdmJvYkeAc0uk5YDiNQ | 3gNfq5uBQU208nbZyDqCzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.3.1 | 41905686 | 41906208 | Temp Install/Make-Safe - Platform F |  |  |  |  | day | 2022-02-22 07:00 | 2022-04-08 17:00 | [12 empty] | 0 | 8 | tseUCdCjE024rOjuTK+SFQ | a5aSdmJvYkeAc0uk5YDiNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.3.2 | 41905691 | 41906208 | Temp Install/Make-Safe - Platform B&C |  |  |  |  | day | 2022-04-04 07:00 | 2022-04-08 17:00 | [12 empty] | 1 | 8 | 4+IPcczTf0S50wbGMZnwUA | a5aSdmJvYkeAc0uk5YDiNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.3.3 | 41905696 | 41906208 | Temp Install/Make-Safe - Platform D&E | 11 |  |  |  | day | 2022-04-06 07:00 | 2022-04-08 17:00 | [12 empty] | 2 | 8 | Du88z6LPxk+UKUH0Yxjuvw | a5aSdmJvYkeAc0uk5YDiNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.4 | 41905678 | 41904399 | Phase 2 - Bracket Install and Catenary Relocation Off Canopies |  |  |  |  | day | 2022-02-03 07:00 | 2022-04-23 17:00 | [12 empty] | 3 | 7 | DoqCJgFbkkeW/w6L0ZnHag | 3gNfq5uBQU208nbZyDqCzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.4.1.1 | 41905680 | 41905679 | Tracks 9-11 | 12 |  |  |  | day | 2022-02-08 07:00 | 2022-02-10 17:00 | [12 empty] | 0 | 9 | D4yzJcOWZECL82IhKxlOAA | wKYBqKlQQUmeusqeZfLU0w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.4.1.2 | 41905681 | 41905679 | Tracks 5-8 | 22 |  |  |  | day | 2022-03-12 07:00 | 2022-03-30 17:00 | [12 empty] | 1 | 9 | WiYTNyXGiECfbmNzzhCM0w | wKYBqKlQQUmeusqeZfLU0w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.4.1.3 | 41905682 | 41905679 | Tracks 2-4 |  |  |  |  | day | 2022-02-12 07:00 | 2022-02-13 17:00 | [12 empty] | 2 | 9 | +5h8Z8nNu0iWIuJU3l+rtw | wKYBqKlQQUmeusqeZfLU0w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.4.2 | 41905683 | 41905678 | Amtrak Scope | 34 |  |  |  | day | 2022-03-05 07:00 | 2022-04-23 17:00 | [12 empty] | 1 | 8 | nsX6IZ3bm0O5855zhPZ7ow | DoqCJgFbkkeW/w6L0ZnHag | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.5 | 41906209 | 41904399 | Phase 3 - Demo Canopies |  |  |  |  | day | 2022-04-11 07:00 | 2022-07-01 17:00 | [12 empty] | 4 | 7 | 8xMnuw7i0k+1FUIS6QjG4w | 3gNfq5uBQU208nbZyDqCzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.5.1 | 41905692 | 41906209 | Demo - Canopy B - Tracks 1,2,3,4 | 29 |  |  |  | day | 2022-04-11 07:00 | 2022-05-19 17:00 | [12 empty] | 0 | 8 | QxUHbO4xo06z+v2ptjL2lg | 8xMnuw7i0k+1FUIS6QjG4w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.5.2 | 41906210 | 41906209 | Demo - Canopy C - Tracks 3,4,5,6 |  |  |  |  | day | 2022-05-12 07:00 | 2022-05-26 17:00 | [12 empty] | 1 | 8 | MEGQfg3ucUmzPQAO1Bh6Ig | 8xMnuw7i0k+1FUIS6QjG4w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.5.3 | 41905697 | 41906209 | Demo - Canopy D - Tracks 5,6,7,8 |  |  |  |  | day | 2022-05-26 07:00 | 2022-06-13 17:00 | [12 empty] | 2 | 8 | Ydd8eQDG0UW7USQQsQt9Ig | 8xMnuw7i0k+1FUIS6QjG4w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.5.4 | 41906211 | 41906209 | Demo - Canopy E - Tracks 7,8,9,10 | 19 |  |  |  | day | 2022-06-14 07:00 | 2022-06-17 17:00 | [12 empty] | 3 | 8 | kcR27Va+qEqrbhbRhpT2lA | 8xMnuw7i0k+1FUIS6QjG4w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.5.5 | 41905687 | 41906209 | Demo - Canopy F - 9,10,11,12 | 47 |  |  |  | day | 2022-06-20 07:00 | 2022-07-01 17:00 | [12 empty] | 4 | 8 | /kdAAyzDQUStRZstFEWL6w | 8xMnuw7i0k+1FUIS6QjG4w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.6 | 41906773 | 41904399 | Phase 4a - 29 Line North - Lath/Steel Installation / Spray Fireproofing |  |  |  |  | day | 2022-05-31 07:00 | 2022-07-01 17:00 | [12 empty] | 5 | 7 | bM0DlUpkTka3kYhRA+nVDw | 3gNfq5uBQU208nbZyDqCzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.7 | 41905684 | 41904399 | Phase 4 - Lath/Steel Installation | 21 |  |  |  | day | [14 empty] | 6 | 7 | gCFM/eGpZkWzANyJd/H/Pg | 3gNfq5uBQU208nbZyDqCzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.7.1 | 41905685 | 41905684 | Tracks 1, 10-13 | 12 |  |  |  | day | [14 empty] | 0 | 8 | hfJibl7zNU++3dH55V+Ogw | gCFM/eGpZkWzANyJd/H/Pg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.7.1.1 | 41905688 | 41905685 | Lath Install | 18 |  |  |  | day | [14 empty] | 0 | 9 | 9wicg+n8t02P27R2tTQ+XQ | hfJibl7zNU++3dH55V+Ogw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.7.1.2 | 41905689 | 41905685 | Steel Support Installation |  |  |  |  | day | [14 empty] | 1 | 9 | 8pwrgZ/OLUW6dzRfG/RouA | hfJibl7zNU++3dH55V+Ogw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.7.2 | 41905690 | 41905684 | Tracks 2-5 |  |  |  |  | day | [14 empty] | 1 | 8 | iZJLBwPPnUG7Rr00R26O5Q | gCFM/eGpZkWzANyJd/H/Pg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.7.2.1 | 41905693 | 41905690 | Lath Install | 11 |  |  |  | day | [14 empty] | 0 | 9 | O5IGs3GTskGvqhjNYpl1xA | iZJLBwPPnUG7Rr00R26O5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.7.2.2 | 41905694 | 41905690 | Steel Support Installation | 40 |  |  |  | day | [14 empty] | 1 | 9 | q4NlYa7bOEOnX0+be+2vLg | iZJLBwPPnUG7Rr00R26O5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.7.3 | 41905695 | 41905684 | Tracks 6-9 | 18 |  |  |  | day | [14 empty] | 2 | 8 | uXHa/dIlDUaFYEtO+bcH/Q | gCFM/eGpZkWzANyJd/H/Pg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.7.3.1 | 41905698 | 41905695 | Lath Install | 11 |  |  |  | day | [14 empty] | 0 | 9 | GPjZSWIlZkGW4cRI7bm48w | uXHa/dIlDUaFYEtO+bcH/Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.7.3.2 | 41905699 | 41905695 | Steel Support Installation | 8 |  |  |  | day | [14 empty] | 1 | 9 | LN97zI6YaEu2XC1pX0PBUA | uXHa/dIlDUaFYEtO+bcH/Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.8 | 41905700 | 41904399 | Phase 5 - Spray Fireproofing | 6 |  |  |  | day | 2022-07-05 07:00 | 2022-11-08 17:00 | [12 empty] | 7 | 7 | GNzONsey506q4W8BN8WLbw | 3gNfq5uBQU208nbZyDqCzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.8.1 | 41905701 | 41905700 | Tracks 1-4 + Platform B |  |  |  |  | day | 2022-07-05 07:00 | 2022-07-27 17:00 | [12 empty] | 0 | 8 | 6vG3zjI/GEWkb/yhqAfTLA | GNzONsey506q4W8BN8WLbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.8.2 | 41905702 | 41905700 | Tracks 4-7 + Platform C+D |  |  |  |  | day | [14 empty] | 1 | 8 | PxLoJeYkYUGARWmcToGsUQ | GNzONsey506q4W8BN8WLbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.8.3 | 41905703 | 41905700 | Tracks 8-11 + Platform E+F |  |  |  |  | day | [14 empty] | 2 | 8 | llb1CYKaZEKvygTMzUTiKw | GNzONsey506q4W8BN8WLbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.8.4 | 41906791 | 41905700 | Tracks 12+3 | 18 |  |  |  | day | [14 empty] | 3 | 8 | vKyFOdHbGkyV0QttLwquhw | GNzONsey506q4W8BN8WLbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.9 | 41906800 | 41904399 | Phase 5a - Lighting Support | 46 |  |  |  | day | 2022-12-10 07:00 | 2024-01-02 17:00 | [12 empty] | 8 | 7 | y3DGlmolpEeponxL2RqnfA | 3gNfq5uBQU208nbZyDqCzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.9.1 | 43728962 | 41906800 | Platform C | 15 |  |  |  | day | 2023-06-12 07:00 | 2023-06-14 17:00 | [12 empty] | 0 | 8 | gizBO76xkEm3rsmZCQdBQQ | y3DGlmolpEeponxL2RqnfA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.9.2 | 43728963 | 41906800 | Platform D | 4 |  |  |  | day | 2023-06-15 07:00 | 2023-06-16 17:00 | [12 empty] | 1 | 8 | kosWzilGjUOaYJhM60UkDQ | y3DGlmolpEeponxL2RqnfA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.9.3 | 43728964 | 41906800 | Platform E |  |  |  |  | day | 2023-07-03 07:00 | 2023-07-07 17:00 | [12 empty] | 2 | 8 | 9dCRzyKyYEK1b8T/b5w0RQ | y3DGlmolpEeponxL2RqnfA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.9.4 | 43728965 | 41906800 | Platform B |  |  |  |  | day | 2023-09-23 07:00 | 2023-09-24 17:00 | [12 empty] | 3 | 8 | rjoiN45LckWkIr78JmwvHA | y3DGlmolpEeponxL2RqnfA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.9.5 | 43728966 | 41906800 | Platform G | 24 |  |  |  | day | 2023-12-26 07:00 | 2024-01-02 17:00 | [12 empty] | 4 | 8 | pFv4RCqKuEm+0xKpel9nbg | y3DGlmolpEeponxL2RqnfA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10 | 41905704 | 41904399 | Phase 6 - Permanent MEP Install | 56.8927 | 2023-09-09 08:00 | 2023-10-06 17:00 | 20 | day | 2023-03-10 07:00 | 2024-03-13 17:00 | [12 empty] | 9 | 7 | mjIxY9rjQUqUrsAAKdMl5A | 3gNfq5uBQU208nbZyDqCzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.1 | 41905705 | 41905704 | Tracks 1, 10-13 |  |  |  |  | day | [14 empty] | 0 | 8 | abVTMJwYJ0+FCPTVK4V/vQ | mjIxY9rjQUqUrsAAKdMl5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.1.1 | 41905706 | 41905705 | Demo Mob 2 |  |  |  |  | day | [14 empty] | 0 | 9 | 28FuBD8EI0GQBu/+JP/9Fg | abVTMJwYJ0+FCPTVK4V/vQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.1.2 | 41905707 | 41905705 | Concrete | 22 |  |  |  | day | [14 empty] | 1 | 9 | 934+BlZ59UudmyBg86OKjg | abVTMJwYJ0+FCPTVK4V/vQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.1.3 | 41905708 | 41905705 | Plumbing | 15 |  |  |  | day | [14 empty] | 2 | 9 | yUgj1XKfZUOFgoMFPSewHg | abVTMJwYJ0+FCPTVK4V/vQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.1.4 | 41905709 | 41905705 | Fire Protection | 38 |  |  |  | day | [14 empty] | 3 | 9 | jWEFSC2q3kyerXIWVrcOHg | abVTMJwYJ0+FCPTVK4V/vQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.1.5 | 41905710 | 41905705 | Mechanical | 44 |  |  |  | day | [14 empty] | 4 | 9 | 26tGHq+lQUawdghU1Yfxyg | abVTMJwYJ0+FCPTVK4V/vQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.1.6 | 41905711 | 41905705 | Electrical | 41 |  |  |  | day | [14 empty] | 5 | 9 | KMYPZhM1yk+mckFj+UWlng | abVTMJwYJ0+FCPTVK4V/vQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.2 | 45199146 | 41905704 | Platform H | 38 |  |  |  | day | 2023-10-30 07:00 | 2024-02-20 17:00 | [12 empty] | 1 | 8 | EqB8WjRuXkmBXE+OWviY3Q | mjIxY9rjQUqUrsAAKdMl5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.2.1 | 45199147 | 45199146 | Site / Structure |  |  |  |  | day | 2023-10-30 07:00 | 2024-02-06 17:00 | [12 empty] | 0 | 9 | THYjjdna9UWK+QxqVGOdeg | EqB8WjRuXkmBXE+OWviY3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.2.2 | 45199148 | 45199146 | Finishes |  |  |  |  | day | 2023-12-08 07:00 | 2024-02-20 17:00 | [12 empty] | 1 | 9 | XLa+l108Kk+miLXqivMYTg | EqB8WjRuXkmBXE+OWviY3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.3 | 43728956 | 41905704 | Lighting Adjustment |  |  |  |  | day | 2023-03-10 07:00 | 2024-01-02 17:00 | [12 empty] | 2 | 8 | 4v4t4x+1pU2vdvG6YCBaxg | mjIxY9rjQUqUrsAAKdMl5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.4 | 43728955 | 41905704 | Platform B | 92 | 2023-09-13 08:00 | 2023-10-09 17:00 | 16 | day | 2023-07-03 07:00 | 2023-12-24 17:00 | [12 empty] | 3 | 8 | 113nalJEUk+cDAyWIRMxCg | mjIxY9rjQUqUrsAAKdMl5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.5 | 43728959 | 41905704 | Platform C | 18.2069 | 2023-09-12 08:00 | 2023-10-16 17:00 | 20 | day | 2023-08-01 07:00 | 2024-01-09 17:00 | [12 empty] | 4 | 8 | Y7JuQaI2wUOSrfAizTtjXw | mjIxY9rjQUqUrsAAKdMl5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.6 | 43728957 | 41905704 | Platform D | 28 |  |  |  | day | 2023-09-09 07:00 | 2024-02-06 17:00 | [12 empty] | 5 | 8 | vjiLmjkrRkSKyicxiJBfPQ | mjIxY9rjQUqUrsAAKdMl5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.7 | 43728958 | 41905704 | Platform E | 42 |  |  |  | day | 2023-08-07 07:00 | 2024-01-16 17:00 | [12 empty] | 6 | 8 | Kbn9FM/N8UisoeupNkRptA | mjIxY9rjQUqUrsAAKdMl5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.8 | 43728960 | 41905704 | Platform F | 10 |  |  |  | day | 2024-01-17 07:00 | 2024-03-13 17:00 | [12 empty] | 7 | 8 | XPW7tFBWDEWHGgrnGuJ25Q | mjIxY9rjQUqUrsAAKdMl5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.9 | 43728961 | 41905704 | Platform G | 17 |  |  |  | day | 2023-11-06 07:00 | 2024-02-21 17:00 | [12 empty] | 8 | 8 | HfjABZ0FkUqu8IixdRvkDQ | mjIxY9rjQUqUrsAAKdMl5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.10 | 41905712 | 41905704 | Tracks 2-5 |  |  |  |  | day | [14 empty] | 9 | 8 | 9R+19aMMZUGWRWvnu7lDaQ | mjIxY9rjQUqUrsAAKdMl5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.10.1 | 41905713 | 41905712 | Demo Mob 2 |  |  |  |  | day | [14 empty] | 0 | 9 | 7vjBSRuoIE2nDlwAxCG2Tg | 9R+19aMMZUGWRWvnu7lDaQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.10.2 | 41905714 | 41905712 | Concrete | 8 |  |  |  | day | [14 empty] | 1 | 9 | yuBNuwGPrEuwid9dltGsBw | 9R+19aMMZUGWRWvnu7lDaQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.10.3 | 41905715 | 41905712 | Plumbing | 9 |  |  |  | day | [14 empty] | 2 | 9 | Dlq1+dOzGUmvaCkALeaaQg | 9R+19aMMZUGWRWvnu7lDaQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.10.4 | 41905716 | 41905712 | Fire Protection | 43 |  |  |  | day | [14 empty] | 3 | 9 | HOqUcnUHkUKDM3dHqfXMYw | 9R+19aMMZUGWRWvnu7lDaQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.10.5 | 41905717 | 41905712 | Mechanical | 16 |  |  |  | day | [14 empty] | 4 | 9 | yxJy5EBsAE6fevxd3byHEA | 9R+19aMMZUGWRWvnu7lDaQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.10.6 | 41905718 | 41905712 | Electrical | 37 |  |  |  | day | [14 empty] | 5 | 9 | jjszg96XgU6Thbo4NnnKkQ | 9R+19aMMZUGWRWvnu7lDaQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.11 | 41905719 | 41905704 | Tracks 6-9 | 6 |  |  |  | day | [14 empty] | 10 | 8 | h/wtCUOUM0iN7UsupSXy4g | mjIxY9rjQUqUrsAAKdMl5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.11.1 | 41905720 | 41905719 | Demo Mob 2 | 45 |  |  |  | day | [14 empty] | 0 | 9 | w7hKZ0hxi0ioT4PmN48pcw | h/wtCUOUM0iN7UsupSXy4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.11.2 | 41905721 | 41905719 | Concrete | 12 |  |  |  | day | [14 empty] | 1 | 9 | TYawJVYXb0GyrJezDouH4g | h/wtCUOUM0iN7UsupSXy4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.11.3 | 41905722 | 41905719 | Plumbing | 39 |  |  |  | day | [14 empty] | 2 | 9 | aQPM38xodkaDxJjmEbQiOw | h/wtCUOUM0iN7UsupSXy4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.11.4 | 41905723 | 41905719 | Fire Protection |  |  |  |  | day | [14 empty] | 3 | 9 | VUP5nxmtXUiRdKLUVf8M4w | h/wtCUOUM0iN7UsupSXy4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.11.5 | 41905724 | 41905719 | Mechanical | 8 |  |  |  | day | [14 empty] | 4 | 9 | Ace9jfitm0SUE/HE0Q3U2A | h/wtCUOUM0iN7UsupSXy4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.10.11.6 | 41905725 | 41905719 | Electrical | 49 |  |  |  | day | [14 empty] | 5 | 9 | S9S1GSpdH06cLKTjL7GRXg | h/wtCUOUM0iN7UsupSXy4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.11 | 41906801 | 41904399 | Track 1 / Platform A | 26 |  |  |  | day | 2023-04-10 07:00 | 2024-09-28 17:00 | [12 empty] | 10 | 7 | mHL/myaNXEKr7jLQseP/Dw | 3gNfq5uBQU208nbZyDqCzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.11.1 | 45025278 | 41906801 | New Platform A | 1 |  |  |  | day | 2023-10-07 07:00 | 2024-01-18 17:00 | [12 empty] | 0 | 8 | j91X5IDJbU2Y6FFBbdkSww | mHL/myaNXEKr7jLQseP/Dw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.11.1.1 | 45036291 | 45025278 | -- | 4 |  |  |  | day | 2023-10-18 07:00 | 2023-12-28 17:00 | [12 empty] | 0 | 9 | LjaOO0YCkk+smuCZYKT+rw | j91X5IDJbU2Y6FFBbdkSww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.2.11.1.2 | 45036292 | 45025278 |  | 28 |  |  |  | day | 2023-10-07 07:00 | 2024-01-18 17:00 | [12 empty] | 1 | 9 | LzXJsTrZaUGVohLWU+iJvA | j91X5IDJbU2Y6FFBbdkSww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.3 | 41905292 | 41904425 | Emergency Response Center / Bus Terminal Fire Command Center (See A3.62.1/23) | 36 |  |  |  | day | 2022-02-28 07:00 | 2023-08-25 17:00 | [12 empty] | 2 | 6 | VtD1hOP/VEef1b5uHSKBTQ | 30/RaML5QkWEGrPnTou+bw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.3.1 | 41905293 | 41905292 | Demo Structure Exteriors | 37 |  |  |  | day | 2022-02-28 07:00 | 2023-06-07 17:00 | [12 empty] | 0 | 7 | /ZmCCTL45Eqn1PrTRKS8qQ | VtD1hOP/VEef1b5uHSKBTQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.3.2 | 41905294 | 41905292 | Interiors | 18 |  |  |  | day | 2022-07-06 07:00 | 2023-08-25 17:00 | [12 empty] | 1 | 7 | OB5NU0mGCkuvLOTlZgNKTQ | VtD1hOP/VEef1b5uHSKBTQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.3.2.1 | 41905295 | 41905294 | BTFCC | 7 |  |  |  | day | 2022-07-06 07:00 | 2023-08-25 17:00 | [12 empty] | 0 | 8 | OJMUGjtVU0S5Zt6o6sK4ew | OB5NU0mGCkuvLOTlZgNKTQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.5.3.2.2 | 41905296 | 41905294 | Community Center |  |  |  |  | day | 2023-06-08 07:00 | 2023-07-28 17:00 | [12 empty] | 1 | 8 | 7GPzH/IKAkOkT+2zg7l2Qw | OB5NU0mGCkuvLOTlZgNKTQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6 | 41904422 | 41904265 | Podium Rough and Finishes Plenum/ Lower Level Rotonda (EL +36') | 44 |  |  |  | day | 2021-07-08 07:00 | 2023-05-01 17:00 | [12 empty] | 5 | 5 | LkSG88OvsUSNGP3Py8cYmQ | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.1 | 41905666 | 41904422 | Pre-Temp Fan and Damper Scope | 0 |  |  |  | day | 2021-12-02 07:00 | 2022-08-12 17:00 | [12 empty] | 0 | 6 |  | LkSG88OvsUSNGP3Py8cYmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.1.1 | 41905668 | 41905666 | Area II - 19-27 H-D.5 | 21 |  |  |  | day | 2021-12-20 07:00 | 2022-02-24 17:00 | [12 empty] | 0 | 7 | Y9YkQ6DMlU2u6NrjGh6LfQ |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.1.2 | 41905667 | 41905666 | Area I - 31-27 H-D.5 |  |  |  |  | day | 2021-12-02 07:00 | 2022-08-12 17:00 | [12 empty] | 1 | 7 | baYOzhsNOEmi3E29ZlUk+A |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.1.3 | 41905670 | 41905666 | Area IV - 19-27 D.5- A.3 | 6 |  |  |  | day | 2022-02-07 07:00 | 2022-08-05 17:00 | [12 empty] | 2 | 7 | BMptXBKEmky6qN7XqgOQGA |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.1.4 | 41905669 | 41905666 | Area III - 31-27 D.5- A.3 |  |  |  |  | day | 2022-02-28 07:00 | 2022-08-05 17:00 | [12 empty] | 3 | 7 | It6wAe6JL0Or+Uqp0e6+XA |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.2 | 41905384 | 41904422 | E.5 LINE - Temp Emergency Fans | 44 |  |  |  | day | 2021-07-08 07:00 | 2022-05-24 17:00 | [12 empty] | 1 | 6 | l2fxWcg4EUO6D1MPsfc1wg | LkSG88OvsUSNGP3Py8cYmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.3 | 41905385 | 41904422 | B.5 LINE - Temp Emergency Fans | 3 |  |  |  | day | 2022-03-15 07:00 | 2022-06-29 17:00 | [12 empty] | 2 | 6 | slujFQScFEedVmZNER9dIA | LkSG88OvsUSNGP3Py8cYmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.4 | 41905447 | 41904422 | Damper Install | 35 |  |  |  | day | 2022-04-25 07:00 | 2023-02-10 17:00 | [12 empty] | 3 | 6 | Civg0faArkaZu7/csQpFHA | LkSG88OvsUSNGP3Py8cYmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.5 | 41904653 | 41904422 | Floor Summary |  |  |  |  | day | 2022-02-07 07:00 | 2023-02-10 17:00 | [12 empty] | 4 | 6 | 5wKTBIEix0+/qbu32zqbTg | LkSG88OvsUSNGP3Py8cYmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.6 | 41904644 | 41904422 | Layout, Risers & Toptrack *** | 30 |  |  |  | day | 2022-07-18 07:00 | 2022-09-02 17:00 | [12 empty] | 5 | 6 | z/+7iEy3dk6Rasuwlw9CaQ | LkSG88OvsUSNGP3Py8cYmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.7 | 41904645 | 41904422 | OH Rough *** |  |  |  |  | day | 2022-08-22 07:00 | 2022-10-28 17:00 | [12 empty] | 6 | 6 | cdxBdHi/hkmKp2QweAUtFQ | LkSG88OvsUSNGP3Py8cYmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.8 | 41904646 | 41904422 | Equipment *** |  |  |  |  | day | 2022-08-15 07:00 | 2022-10-11 17:00 | [12 empty] | 7 | 6 | /nafkfYZKUKK3eR96rP1Qg | LkSG88OvsUSNGP3Py8cYmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.9 | 41904647 | 41904422 | In-Wall Rough *** | 38 |  |  |  | day | 2022-10-11 07:00 | 2022-11-15 17:00 | [12 empty] | 8 | 6 | fyETXm/KAEO1Be0RZbZaxQ | LkSG88OvsUSNGP3Py8cYmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.10 | 41904648 | 41904422 | Finishes *** | 26 |  |  |  | day | 2022-11-21 07:00 | 2023-05-01 17:00 | [12 empty] | 9 | 6 | GvDuqU2AWE+T2yBh95S0hw | LkSG88OvsUSNGP3Py8cYmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.10.1 | 41904832 | 41904648 | Summer St AA-B | 9 |  |  |  | day | [14 empty] | 0 | 7 | BPpzDtsQ7k6c9qKiNwnfKQ | GvDuqU2AWE+T2yBh95S0hw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.10.2 | 41904833 | 41904648 | Center/Bus B-J |  |  |  |  | day | [14 empty] | 1 | 7 | BkhC27htPEWDhzo164e4uQ | GvDuqU2AWE+T2yBh95S0hw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.10.3 | 41904834 | 41904648 | Atlantic St J-K | 18 |  |  |  | day | [14 empty] | 2 | 7 | j52rhWGg1kind/gFZlfEAg | GvDuqU2AWE+T2yBh95S0hw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.6.11 | 41904649 | 41904422 | Elevator Lobbies |  |  |  |  | day | [14 empty] | 10 | 6 | R00bO5/iykmdHdG+oOmwgA | LkSG88OvsUSNGP3Py8cYmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7 | 41904423 | 41904265 | Podium Rough and Finishes Bus Terminal (EL +49')- [CMP 12A-D] | 2 |  |  |  | day | 2022-03-21 07:00 | 2024-10-22 17:00 | [12 empty] | 6 | 5 | H7+/bq8x5kSqatQQHueLYQ | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.1 | 41906821 | 41904423 | New B-H Line BT | 44 |  |  |  | day | 2022-08-02 07:00 | 2024-04-05 17:00 | [12 empty] | 0 | 6 | nOzS7dRr80aOPQDUOW1ZxA | H7+/bq8x5kSqatQQHueLYQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.1.1 | 41907071 | 41906821 | Fire Pump Replacement | 12 |  |  |  | day | 2023-02-27 07:00 | 2023-09-18 17:00 | [12 empty] | 0 | 7 | kXJ7CYITHkK6IWqLU8muRw | nOzS7dRr80aOPQDUOW1ZxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.1.2 | 41906824 | 41906821 | 23-30 Line Bus Terminal | 49 |  |  |  | day | 2022-08-15 07:00 | 2023-09-29 17:00 | [12 empty] | 1 | 7 | UY5wc6RM50eFdGwtR1pLGQ | nOzS7dRr80aOPQDUOW1ZxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.1.3 | 41906822 | 41906821 | 23-19 Line (Existing Bus) |  |  |  |  | day | 2022-10-17 07:00 | 2024-04-05 17:00 | [12 empty] | 2 | 7 | V1I3+s0mS0OCSxkS+Ys1Mg | nOzS7dRr80aOPQDUOW1ZxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.1.3.1 | 41906823 | 41906822 | (New WBS) | 19 |  |  |  | day | [14 empty] | 0 | 8 | Q/CDMjNE9EKu+CRk88jTWQ | V1I3+s0mS0OCSxkS+Ys1Mg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.1.4 | 41906825 | 41906821 | AHU-8 / Bathroom Comeback | 27 |  |  |  | day | 2022-10-03 07:00 | 2024-01-09 17:00 | [12 empty] | 3 | 7 | InrwK05R30q/Tix9y1pRYQ | nOzS7dRr80aOPQDUOW1ZxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.1.5 | 41906826 | 41906821 | East - Bus Drivelane |  |  |  |  | day | 2022-08-15 07:00 | 2023-12-04 17:00 | [12 empty] | 4 | 7 | QGQxR5NHTUKiwWWr4QJMug | nOzS7dRr80aOPQDUOW1ZxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.1.6 | 41906827 | 41906821 | North - Bus Drivelane |  |  |  |  | day | 2022-08-22 07:00 | 2023-12-04 17:00 | [12 empty] | 5 | 7 | 02j31xU0AkOw/9t7eE6whw | nOzS7dRr80aOPQDUOW1ZxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.1.7 | 41906828 | 41906821 | West - Bus Drivelane |  |  |  |  | day | 2022-08-02 07:00 | 2023-12-04 17:00 | [12 empty] | 6 | 7 | MCm+8iggJ0GduwajtVSyBg | nOzS7dRr80aOPQDUOW1ZxA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.2 | 41904654 | 41904423 | Floor Summary | 0 |  |  |  | day | 2022-04-11 07:00 | 2024-04-05 17:00 | [12 empty] | 1 | 6 | i/j1oRGVqkGOyqz7o2QYNw | H7+/bq8x5kSqatQQHueLYQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3 | 41904725 | 41904423 | Main Area - H-B Line | 2 |  |  |  | day | 2022-03-21 07:00 | 2024-10-22 17:00 | [12 empty] | 2 | 6 | GsWn8G4qL06zK/Ui16/9ZA | H7+/bq8x5kSqatQQHueLYQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.1 | 41905463 | 41904725 | Electrical Duct Bank |  |  |  |  | day | 2022-05-26 07:00 | 2022-07-27 17:00 | [12 empty] | 0 | 7 | Q+QoIExM0UC8yFqgVzOoIA | GsWn8G4qL06zK/Ui16/9ZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.2 | 41905466 | 41904725 | Electrical Duct Bank-1 | 27 |  |  |  | day | 2022-04-11 07:00 | 2022-06-02 17:00 | [12 empty] | 1 | 7 | oKyl1YKc90S6dkbphkQhkA | GsWn8G4qL06zK/Ui16/9ZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.3 | 41905462 | 41904725 | D - H Line | 48 |  |  |  | day | [14 empty] | 2 | 7 | DIJh6yknkk+Hng0xT8L/EQ | GsWn8G4qL06zK/Ui16/9ZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.3.1 | 41906205 | 41905462 | Area II - 19-27 H-D.5 | 24 |  |  |  | day | [14 empty] | 0 | 8 | 1pg26fFPk06vPYxav9tZLA | DIJh6yknkk+Hng0xT8L/EQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.3.2 | 41906204 | 41905462 | Area I - 31-27 H-D.5 | 32 |  |  |  | day | [14 empty] | 1 | 8 | jx1RkbhKxU+I8H2HeyrF0Q | DIJh6yknkk+Hng0xT8L/EQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.3.3 | 41906207 | 41905462 | Area IV - 19-27 D.5- A.3 | 37 |  |  |  | day | [14 empty] | 2 | 8 | kGk0DRWCQUilSHhtlft7uA | DIJh6yknkk+Hng0xT8L/EQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.3.4 | 41906206 | 41905462 | Area III - 31-27 D.5- A.3 | 5 |  |  |  | day | [14 empty] | 3 | 8 | epQUAAqb80KiszQjM26e5Q | DIJh6yknkk+Hng0xT8L/EQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4 | 41904877 | 41904725 | CMP-12A | 43 |  |  |  | day | 2022-04-29 07:00 | 2022-09-26 17:00 | [12 empty] | 3 | 7 | vOCvRXn8U0mfpvhbqyen5A | GsWn8G4qL06zK/Ui16/9ZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4.1 | 41905099 | 41904877 | Layout, Risers & Toptrack |  |  |  |  | day | 2022-06-13 07:00 | 2022-08-05 17:00 | [12 empty] | 0 | 8 | DioXDyPll0eYBmxOsXcWgg | vOCvRXn8U0mfpvhbqyen5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4.2 | 41905091 | 41904877 | Bus Mezz Concrete Ductbank |  |  |  |  | day | [14 empty] | 1 | 8 | JKuoBy1Hx0us5mhvurjvVA | vOCvRXn8U0mfpvhbqyen5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4.3 | 41905100 | 41904877 | OH Rough |  |  |  |  | day | 2022-08-01 07:00 | 2022-09-26 17:00 | [12 empty] | 2 | 8 | C7vxOZly2UmoQA4uGHXX6Q | vOCvRXn8U0mfpvhbqyen5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4.4 | 41905101 | 41904877 | Equipment | 46 |  |  |  | day | [14 empty] | 3 | 8 | qsh44n9vSEGJR+OXwUJd8Q | vOCvRXn8U0mfpvhbqyen5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4.5 | 41905102 | 41904877 | In-Wall Rough | 20 |  |  |  | day | 2022-08-08 07:00 | 2022-09-12 17:00 | [12 empty] | 4 | 8 | MquJ3edFUUuxp73ZCGEDsw | vOCvRXn8U0mfpvhbqyen5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4.6 | 41905122 | 41904877 | Finishes - Main Bus Terminal - Storage and Fan Rooms | 15 |  |  |  | day | [14 empty] | 5 | 8 | YEp1PPFMX0Sfr6C/SKRrpQ | vOCvRXn8U0mfpvhbqyen5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4.7 | 41905123 | 41904877 | Finishes - Main Bus Terminal - Passenger Area | 20 |  |  |  | day | [14 empty] | 6 | 8 | I2gDuBOHI0OrSNmJmkbmjA | vOCvRXn8U0mfpvhbqyen5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4.7.1 | 41905167 | 41905123 | Lobby/ Waiting Area |  |  |  |  | day | [14 empty] | 0 | 9 | TOrnr1rtRUSryBHcT/HwuA | I2gDuBOHI0OrSNmJmkbmjA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4.7.2 | 41905164 | 41905123 | Finishes - Bathrooms | 36 |  |  |  | day | [14 empty] | 1 | 9 | XvROEonvu0Cp9cTp9dt4Wg | I2gDuBOHI0OrSNmJmkbmjA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4.7.3 | 41905163 | 41905123 | Elevator |  |  |  |  | day | [14 empty] | 2 | 9 | 4XUGhv3N1UKGIcuI4cuDSQ | I2gDuBOHI0OrSNmJmkbmjA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.4.8 | 41905104 | 41904877 | Garage Finishes | 34 |  |  |  | day | [14 empty] | 7 | 8 | Qjo55sknmEWusnBSGjj4GQ | vOCvRXn8U0mfpvhbqyen5A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.5 | 41904878 | 41904725 | CMP-12B & CMP-12C | 18 |  |  |  | day | [14 empty] | 4 | 7 | KMYPlu4P9k+XfcmP/RnEcQ | GsWn8G4qL06zK/Ui16/9ZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.5.1 | 41905121 | 41904878 | Change Configuration to CMP-12B (Work Hours Mon-Fri 8:00 pm to 4:30 am) | 19 |  |  |  | day | [14 empty] | 0 | 8 | UZyraq94PkK+p+3phAmh8g | KMYPlu4P9k+XfcmP/RnEcQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.5.2 | 41905127 | 41904878 | Change Configuration to CMP 12-C (Work Hours Mon-Fri 8:00 pm to 4:30 am) |  |  |  |  | day | [14 empty] | 1 | 8 | eS+c2bcWFkKXQGfq/8XybA | KMYPlu4P9k+XfcmP/RnEcQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.5.3 | 41905120 | 41904878 | Mechanical Mezzanine |  |  |  |  | day | [14 empty] | 2 | 8 | DPGjj5s0iEy1/8OIZFYRLg | KMYPlu4P9k+XfcmP/RnEcQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.5.3.1 | 41905168 | 41905120 | Prepatory Demolition | 40 |  |  |  | day | [14 empty] | 0 | 9 | 7M6losWqi0m0BJoXrkGdnA | DPGjj5s0iEy1/8OIZFYRLg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.5.3.2 | 41905165 | 41905120 | Structure |  |  |  |  | day | [14 empty] | 1 | 9 | Lk9KVuLRkkS9/sUxLPk4og | DPGjj5s0iEy1/8OIZFYRLg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.5.3.3 | 41905166 | 41905120 | OH Rough & Equipment |  |  |  |  | day | [14 empty] | 2 | 9 | XePgVeLY80ex0YRnEV1Jpw | DPGjj5s0iEy1/8OIZFYRLg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.5.4 | 41905103 | 41904878 | Finishes - Main Bus Terminal |  |  |  |  | day | [14 empty] | 3 | 8 | p3OQsnCbJUycKaRNdpmQrQ | KMYPlu4P9k+XfcmP/RnEcQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.5.5 | 41905124 | 41904878 | Finishes - Connection to Existing Bus Terminal | 30 |  |  |  | day | [14 empty] | 4 | 8 | N7GO5S+KZ0KZBe+s/ZOEaQ | KMYPlu4P9k+XfcmP/RnEcQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.6 | 41904879 | 41904725 | CMP-12D | 0 |  |  |  | day | 2024-04-08 07:00 | 2024-10-22 17:00 | [12 empty] | 5 | 7 | eOWir7HLZEKIvj/6ZK+HvA | GsWn8G4qL06zK/Ui16/9ZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.6.1 | 41905125 | 41904879 | Change Configuration (Work Hours Mon-Fri 8:00 pm to 4:30 am) | 2 |  |  |  | day | 2024-04-08 07:00 | 2024-04-11 17:00 | [12 empty] | 0 | 8 | NTmbgS/6TEWYfetkoM/Avg | eOWir7HLZEKIvj/6ZK+HvA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.6.2 | 41905126 | 41904879 | Retail Work (By Others) | 15 |  |  |  | day | 2024-04-12 07:00 | 2024-10-02 17:00 | [12 empty] | 1 | 8 | qF4yfDgyF0ObNweDd5YrwA | eOWir7HLZEKIvj/6ZK+HvA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.3.6.3 | 41905128 | 41904879 | Final Turnover | 22 |  |  |  | day | 2024-09-13 07:00 | 2024-10-21 17:00 | [12 empty] | 2 | 8 | 9OH4Yx/A9U2skrBet1Xdyg | eOWir7HLZEKIvj/6ZK+HvA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.4 | 41904726 | 41904423 | Electrical Rooms - B-AA Line | 10 |  |  |  | day | 2022-09-20 07:00 | 2024-03-25 17:00 | [12 empty] | 3 | 6 | W/iTHqpueE6oeE4kSTfX4w | H7+/bq8x5kSqatQQHueLYQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.4.1 | 41904835 | 41904726 | Equipment | 11 |  |  |  | day | [14 empty] | 0 | 7 | CTp5JSkL3EmHaZ5bbUcb8w | W/iTHqpueE6oeE4kSTfX4w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.4.2 | 41904810 | 41904726 | Bus Mezz - MBTA TransformerVault; Elec, Emergency Elec & Generator Rooms +49 | 9 |  |  |  | day | 2022-09-20 07:00 | 2024-03-25 17:00 | [12 empty] | 1 | 7 | p8Tvx3uhE0uBH59fS6RjLQ | W/iTHqpueE6oeE4kSTfX4w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.4.2.1 | 41905092 | 41904810 | MBTA Transformer Vault |  |  |  |  | day | 2022-09-20 07:00 | 2024-03-25 17:00 | [12 empty] | 0 | 8 | MUpYdvYWckGgNwi9trIGbQ | p8Tvx3uhE0uBH59fS6RjLQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.4.2.2 | 41905093 | 41904810 | MBTA Switchgear Room | 15 |  |  |  | day | 2022-09-21 07:00 | 2023-05-05 17:00 | [12 empty] | 1 | 8 | y+jOE+Q1NEuG6ShhJFgWiw | p8Tvx3uhE0uBH59fS6RjLQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.4.2.3 | 41905106 | 41904810 | MBTA Em Gen Room | 7 |  |  |  | day | 2022-11-01 07:00 | 2023-07-28 17:00 | [12 empty] | 2 | 8 | 3Pb2sVWA7UKZLwpnClBvyg | p8Tvx3uhE0uBH59fS6RjLQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.5 | 41906858 | 41904423 | Fan Rooms |  |  |  |  | day | 2022-10-03 07:00 | 2022-12-02 17:00 | [12 empty] | 4 | 6 | Mn8032CJe0mQUpz3BYm+cw | H7+/bq8x5kSqatQQHueLYQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.6 | 41904727 | 41904423 | Atlantic Lobby - H-J.5 Line |  |  |  |  | day | [14 empty] | 5 | 6 | 0XhDWJXBYU6viPXKHz7gyg | H7+/bq8x5kSqatQQHueLYQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.7.6.1 | 41904836 | 41904727 | Equipment | 23 |  |  |  | day | [14 empty] | 0 | 7 | qVVOFXUfqkaqkAKL8Ou8Ug | 0XhDWJXBYU6viPXKHz7gyg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8 | 41904415 | 41904265 | Podium Rough and Finishes P1 (EL +74.5') |  |  |  |  | day | 2022-04-27 07:00 | 2024-05-24 17:00 | [12 empty] | 7 | 5 | S3r5N2L/GU2wFPKobNwxQQ | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.1 | 41904655 | 41904415 | Floor Summary |  |  |  |  | day | 2022-07-01 07:00 | 2024-04-03 17:00 | [12 empty] | 0 | 6 | 6aU3Bd+kekWM9674mexR/w | S3r5N2L/GU2wFPKobNwxQQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2 | 41904728 | 41904415 | Main Area - H-B Line | 27 |  |  |  | day | 2022-07-06 07:00 | 2024-04-19 17:00 | [12 empty] | 1 | 6 | 6Wqd5ZqMcUaTsUs9tM+GvQ | S3r5N2L/GU2wFPKobNwxQQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.1 | 41904882 | 41904728 | Rough |  |  |  |  | day | 2022-07-06 07:00 | 2023-06-19 17:00 | [12 empty] | 0 | 7 | HSO5HrJufUaJ6uxyKEiJSQ | 6Wqd5ZqMcUaTsUs9tM+GvQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.1.1 | 41905095 | 41904882 | Layout, Risers & Toptrack | 25 |  |  |  | day | 2022-07-06 07:00 | 2022-12-02 17:00 | [12 empty] | 0 | 8 | wHIsmYu5J0SRfdXpvsH93Q | HSO5HrJufUaJ6uxyKEiJSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.1.2 | 41905144 | 41904882 | CMU | 7 |  |  |  | day | 2022-11-10 07:00 | 2022-12-16 17:00 | [12 empty] | 1 | 8 | p7mw2LYqq0yVUQJAhL9ZWA | HSO5HrJufUaJ6uxyKEiJSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.1.3 | 41905096 | 41904882 | OH Rough | 49 |  |  |  | day | 2022-07-27 07:00 | 2023-06-19 17:00 | [12 empty] | 2 | 8 | 6MjA+Dis/E+zHsVc25uL9Q | HSO5HrJufUaJ6uxyKEiJSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.1.4 | 41905097 | 41904882 | Framing & In-Wall Rough | 27 |  |  |  | day | 2022-11-21 07:00 | 2023-05-12 17:00 | [12 empty] | 3 | 8 | q0oykOGqjk6Jx6pdWeDHow | HSO5HrJufUaJ6uxyKEiJSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.1.5 | 41905141 | 41904882 | Rough Inspections | 27 |  |  |  | day | 2023-05-15 07:00 | 2023-05-19 17:00 | [12 empty] | 4 | 8 | LbxYtn4sdUWEpWJyHOdgxw | HSO5HrJufUaJ6uxyKEiJSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2 | 41904883 | 41904728 | Finishes |  |  |  |  | day | 2022-11-04 07:00 | 2024-04-19 17:00 | [12 empty] | 1 | 7 | nkzqFIHyMECKH9jdyFe1Kg | 6Wqd5ZqMcUaTsUs9tM+GvQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.1 | 41905129 | 41904883 | Loading Dock | 40 |  |  |  | day | 2023-07-03 07:00 | 2024-04-10 17:00 | [12 empty] | 0 | 8 | p0C6oku4BEq3GCpH3Q3IEg | nkzqFIHyMECKH9jdyFe1Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.2 | 41905134 | 41904883 | Parking | 35 |  |  |  | day | 2024-01-17 07:00 | 2024-04-19 17:00 | [12 empty] | 1 | 8 | ZJial98aokOGRdkV9o51QQ | nkzqFIHyMECKH9jdyFe1Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.3 | 41905135 | 41904883 | Transformers & Switchgear |  |  |  |  | day | 2022-11-04 07:00 | 2024-04-05 17:00 | [12 empty] | 2 | 8 | fi6NeV8LTUSWBKWYkuObkg | nkzqFIHyMECKH9jdyFe1Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.3.1 | 41905159 | 41905135 | Tower NSTAR Vault 1 | 16 |  |  |  | day | 2023-07-10 07:00 | 2024-03-08 17:00 | [12 empty] | 0 | 9 | ku1zlNfNqkaNpR+xymuCZw | fi6NeV8LTUSWBKWYkuObkg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.3.2 | 41905161 | 41905135 | Tower NSTAR Vault 2 |  |  |  |  | day | 2023-07-10 07:00 | 2024-04-05 17:00 | [12 empty] | 1 | 9 | B2GiMa8zkESkCvPda3R59w | fi6NeV8LTUSWBKWYkuObkg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.3.3 | 41905160 | 41905135 | Tower Switchgear Room 1 | 32 |  |  |  | day | 2022-11-04 07:00 | 2024-01-30 17:00 | [12 empty] | 2 | 9 | jT+KyiRv8EWBDBekSjVwWQ | fi6NeV8LTUSWBKWYkuObkg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.3.4 | 41905162 | 41905135 | Tower Switchgear Room 2 | 19 |  |  |  | day | 2022-11-07 07:00 | 2024-01-30 17:00 | [12 empty] | 3 | 9 | 6YDPGmUNVkGlIokAxWmlbg | fi6NeV8LTUSWBKWYkuObkg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.4 | 41905130 | 41904883 | Domestic Water Pump Room & Attached Rooms |  |  |  |  | day | 2023-07-10 07:00 | 2024-01-24 17:00 | [12 empty] | 3 | 8 | 1XiY+54u+Uej2Vgy4zkfog | nkzqFIHyMECKH9jdyFe1Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.5 | 41905132 | 41904883 | Parking Office Incl. Storage |  |  |  |  | day | 2023-07-10 07:00 | 2024-01-17 17:00 | [12 empty] | 4 | 8 |  | nkzqFIHyMECKH9jdyFe1Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.6 | 41905131 | 41904883 | Fan Rooms | 47 |  |  |  | day | 2023-07-03 07:00 | 2023-11-15 17:00 | [12 empty] | 5 | 8 | dKnICPUXOkCU9YYYbSY5JQ | nkzqFIHyMECKH9jdyFe1Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.7 | 41905133 | 41904883 | Fuel Oil Storage | 28 |  |  |  | day | 2022-12-12 07:00 | 2023-11-08 17:00 | [12 empty] | 6 | 8 | ied2NNg6mEOXArqRBMb+MQ | nkzqFIHyMECKH9jdyFe1Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.8 | 41905143 | 41904883 | Stair 7 Corridor, Screening & Bike Storage (Adj.Fuel Oil Storage) | 12 |  |  |  | day | 2023-06-14 07:00 | 2024-02-27 17:00 | [12 empty] | 7 | 8 | 82TpeR3LHU+TWoWQAksogg | nkzqFIHyMECKH9jdyFe1Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.9 | 41905142 | 41904883 | Recycling & Bike Storage Incl. Elevators & Circulation | 45 |  |  |  | day | 2023-06-20 07:00 | 2024-03-29 17:00 | [12 empty] | 8 | 8 | R93p0DiSKEKjrH0w30jLLA | nkzqFIHyMECKH9jdyFe1Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.9.1 | 41905169 | 41905142 | Elevator Lobbies | 34 |  |  |  | day | 2023-12-26 07:00 | 2024-02-01 17:00 | [12 empty] | 0 | 9 | hEs5OCSWlUm4NWUEGMH6jQ | R93p0DiSKEKjrH0w30jLLA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.10 | 41905098 | 41904883 | Tower Screening Area Incl. Elevators Stairs & Storage | 5 |  |  |  | day | 2023-12-27 07:00 | 2024-02-28 17:00 | [12 empty] | 9 | 8 | bO4uxQ2AbkeQvGvkWx6epQ | nkzqFIHyMECKH9jdyFe1Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.2.2.10.1 | 41905170 | 41905098 | Elevator Lobbies | 17 |  |  |  | day | 2024-01-04 07:00 | 2024-02-12 17:00 | [12 empty] | 0 | 9 | FWnDLPLsRk6xS1HI5QNu4Q | bO4uxQ2AbkeQvGvkWx6epQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.3 | 41904729 | 41904415 | Comeback Dorchester Ave - B-AA Line | 4 |  |  |  | day | 2022-11-03 07:00 | 2024-01-22 17:00 | [12 empty] | 2 | 6 | t4Zmuuh3XUWFXhOGO1e5gQ | S3r5N2L/GU2wFPKobNwxQQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.3.1 | 41904886 | 41904729 | Finishes |  |  |  |  | day | 2023-12-26 07:00 | 2024-01-22 17:00 | [12 empty] | 0 | 7 | motI/a9TbEynwIAt15d3Wg | t4Zmuuh3XUWFXhOGO1e5gQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.3.1.1 | 41905139 | 41904886 | Parking & Loading Dock (Adjacent to Fan Building) | 24 |  |  |  | day | 2023-12-26 07:00 | 2024-01-22 17:00 | [12 empty] | 0 | 8 | DNJxkUhET0m1xNxzyineUw | motI/a9TbEynwIAt15d3Wg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.4 | 41904732 | 41904415 | Comeback - Fan Building | 1 |  |  |  | day | 2022-11-14 07:00 | 2024-01-03 17:00 | [12 empty] | 3 | 6 | gQTCihaUOkSzr35Ab7zBuw | S3r5N2L/GU2wFPKobNwxQQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.4.1 | 41904884 | 41904732 | Rough | 9 |  |  |  | day | 2022-11-14 07:00 | 2023-08-21 17:00 | [12 empty] | 0 | 7 | 5KLpChcX4kOsEskYpcWyfA | gQTCihaUOkSzr35Ab7zBuw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.4.1.1 | 41905145 | 41904884 | CMU |  |  |  |  | day | 2022-11-14 07:00 | 2022-12-08 17:00 | [12 empty] | 0 | 8 | LTt5znSjSEq14qxw/xJVGQ | 5KLpChcX4kOsEskYpcWyfA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.4.1.2 | 41905136 | 41904884 | Layout, Risers & Toptrack | 49 |  |  |  | day | 2022-11-14 07:00 | 2022-12-16 17:00 | [12 empty] | 1 | 8 | 0r3u1Z7k8k6IkLhzvgoPAQ | 5KLpChcX4kOsEskYpcWyfA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.4.1.3 | 41905137 | 41904884 | OH Rough | 44 |  |  |  | day | 2022-12-12 07:00 | 2023-05-26 17:00 | [12 empty] | 2 | 8 | iuFjqw4Z7kinDmkJFW0qYw | 5KLpChcX4kOsEskYpcWyfA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.4.1.4 | 41905138 | 41904884 | Framing & In-Wall Rough | 4 |  |  |  | day | 2023-03-23 07:00 | 2023-08-21 17:00 | [12 empty] | 3 | 8 | CjkdoGtTTUGU1XjoX02Cdg | 5KLpChcX4kOsEskYpcWyfA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.4.2 | 41904885 | 41904732 | Finishes | 32 |  |  |  | day | 2023-03-11 07:00 | 2024-01-03 17:00 | [12 empty] | 1 | 7 | JiDNMQBrDUCvsP0m8V3YMQ | gQTCihaUOkSzr35Ab7zBuw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.4.2.1 | 41905105 | 41904885 | Tower Em Gen Room (P1-P4) | 0 |  |  |  | day | 2023-03-11 07:00 | 2024-01-03 17:00 | [12 empty] | 0 | 8 | hI24C0dRP0O/DxD0Oliq0w | JiDNMQBrDUCvsP0m8V3YMQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.4.2.2 | 41905140 | 41904885 | Fan Rooms (P1-P4) | 17 |  |  |  | day | 2023-07-10 07:00 | 2023-12-29 17:00 | [12 empty] | 1 | 8 | D5JK4gLN+UCQIfhSKZV+/w | JiDNMQBrDUCvsP0m8V3YMQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.5 | 41904730 | 41904415 | Comeback - Atlantic Lobby - H-J.5 Line | 31 |  |  |  | day | [14 empty] | 4 | 6 |  | S3r5N2L/GU2wFPKobNwxQQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.5.1 | 41904880 | 41904730 | Rough |  |  |  |  | day | [14 empty] | 0 | 7 | EXBPF0w/xEGFejMZSYJeag |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.5.2 | 41904881 | 41904730 | Finishes | 48 |  |  |  | day | [14 empty] | 1 | 7 | zdCfztvP4U6OKFLt98dscw |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.8.6 | 41904731 | 41904415 | Punch & Final Clean | 10 |  |  |  | day | 2024-04-22 07:00 | 2024-05-24 17:00 | [12 empty] | 5 | 6 | RwR23v9WAUWaA9NWQJb5fg | S3r5N2L/GU2wFPKobNwxQQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.9 | 41904416 | 41904265 | Podium Rough and Finishes P2 (EL +84.5') | 20 |  |  |  | day | 2022-07-13 07:00 | 2024-04-30 17:00 | [12 empty] | 8 | 5 | nPGH8sTjpUmIVOJgrR4YHw | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.9.1 | 41906753 | 41904416 | Interior Summary & Milestones | 25 |  |  |  | day | 2022-08-09 07:00 | 2024-04-30 17:00 | [12 empty] | 0 | 6 | 8dCfdAfhhkyi5EkCycVpUQ | nPGH8sTjpUmIVOJgrR4YHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.9.2 | 41906735 | 41904416 | Electrical Duct Bank | 24 |  |  |  | day | [14 empty] | 1 | 6 | +69l31BtT02fn2wXgWyhTQ | nPGH8sTjpUmIVOJgrR4YHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.9.3 | 41904656 | 41904416 | Floor Summary | 21 |  |  |  | day | 2022-08-09 07:00 | 2024-04-30 17:00 | [12 empty] | 2 | 6 | yBtFjm1SX0q+rvdLXZS5XA | nPGH8sTjpUmIVOJgrR4YHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.9.4 | 41904657 | 41904416 | Layout, Risers & Toptrack |  |  |  |  | day | 2022-08-15 07:00 | 2022-09-26 17:00 | [12 empty] | 3 | 6 | vK/pZSkIQEGtoVZdPjetiA | nPGH8sTjpUmIVOJgrR4YHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.9.5 | 41904658 | 41904416 | OH Rough | 48 |  |  |  | day | 2022-09-27 07:00 | 2022-11-22 17:00 | [12 empty] | 4 | 6 |  | nPGH8sTjpUmIVOJgrR4YHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.9.6 | 41904659 | 41904416 | Equipment | 12 |  |  |  | day | [14 empty] | 5 | 6 | d/OTyDq6o0eLU1xeZRY4kw | nPGH8sTjpUmIVOJgrR4YHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.9.7 | 41904660 | 41904416 | In-Wall Rough | 32 |  |  |  | day | 2022-11-08 07:00 | 2023-05-12 17:00 | [12 empty] | 6 | 6 | VB2YRQMJrkiw0zdWlFzWLQ | nPGH8sTjpUmIVOJgrR4YHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.9.8 | 41904661 | 41904416 | Finishes |  |  |  |  | day | 2023-05-15 07:00 | 2024-01-23 17:00 | [12 empty] | 7 | 6 | s8SJiZKsdkiL353N5LlNbA | nPGH8sTjpUmIVOJgrR4YHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.9.9 | 41904662 | 41904416 | Elevator Lobbies | 40 |  |  |  | day | 2023-07-03 07:00 | 2024-01-16 17:00 | [12 empty] | 8 | 6 | eaicGjSsvECWfEx8wLpSeg | nPGH8sTjpUmIVOJgrR4YHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.9.10 | 41904663 | 41904416 | Garage Finishes | 34 |  |  |  | day | 2023-12-26 07:00 | 2024-04-30 17:00 | [12 empty] | 9 | 6 | 6rKrXDupskOq5mkZbevbng | nPGH8sTjpUmIVOJgrR4YHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10 | 41904417 | 41904265 | Podium Rough and Finishes P3 (EL +94.5') |  |  |  |  | day | 2022-07-25 07:00 | 2024-07-01 17:00 | [12 empty] | 9 | 5 | 1qFzujeKskmoxHiO3mkr1g | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.1 | 41906752 | 41904417 | Interior Summary & Milestones | 20 |  |  |  | day | 2022-08-09 07:00 | 2024-07-01 17:00 | [12 empty] | 0 | 6 | azRTz8pXEUm8ql41wfxJzA | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.2 | 41904664 | 41904417 | Floor Summary | 47 |  |  |  | day | 2022-07-25 07:00 | 2024-07-01 17:00 | [12 empty] | 1 | 6 | VEOMx9UvNE+QdKqeqkfllw | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.3 | 41906994 | 41904417 | P3 - Bulletin 55 | 5 |  |  |  | day | 2023-12-26 07:00 | 2024-01-16 17:00 | [12 empty] | 2 | 6 | 0quqSGuQ3Eu32DwnlZnM6g | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.4 | 41904665 | 41904417 | Layout, Risers & Toptrack |  |  |  |  | day | 2022-08-29 07:00 | 2022-11-01 17:00 | [12 empty] | 3 | 6 | Sw9mLvJBzU2XaU6b1HVVIQ | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.5 | 41904666 | 41904417 | OH Rough |  |  |  |  | day | 2022-11-02 07:00 | 2023-07-14 17:00 | [12 empty] | 4 | 6 | GQbqvE4QokKpjrZiavM7Vg | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.6 | 41904667 | 41904417 | Equipment | 4 |  |  |  | day | 2023-07-03 07:00 | 2023-07-10 17:00 | [12 empty] | 5 | 6 | hWy39QhL3Ee4mTgS12rOGw | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.7 | 41904668 | 41904417 | In-Wall Rough |  |  |  |  | day | 2023-12-26 07:00 | 2024-01-31 17:00 | [12 empty] | 6 | 6 | gc6cBtBBDEqOOfF/iLoaKw | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.8 | 41904669 | 41904417 | Finishes |  |  |  |  | day | 2024-02-01 07:00 | 2024-04-01 17:00 | [12 empty] | 7 | 6 | DMnHy1N1OkGPPY8p4R6Tpw | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.9 | 41904670 | 41904417 | Elevator Lobbies | 37 |  |  |  | day | 2024-02-08 07:00 | 2024-03-25 17:00 | [12 empty] | 8 | 6 | ffym5BLcI0Od6opS6U9XFQ | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.10 | 41904671 | 41904417 | Garage Finishes | 2 |  |  |  | day | 2024-02-27 07:00 | 2024-07-01 17:00 | [12 empty] | 9 | 6 | 7J7q1pzo/U60T9I+4rxJ1Q | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.11 | 41904617 | 41904417 | P3 - Concrete Ductbank | 22 |  |  |  | day | 2022-08-15 07:00 | 2022-09-29 17:00 | [12 empty] | 10 | 6 | lKyDTz/V2ki2n6OKg5tkeQ | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.10.12 | 41904704 | 41904417 | P3 - Generator Room |  |  |  |  | day | 2022-11-21 07:00 | 2023-11-14 17:00 | [12 empty] | 11 | 6 | w4qKsbg+uUuHYyGK16svxQ | 1qFzujeKskmoxHiO3mkr1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.11 | 41904418 | 41904265 | Podium Rough and Finishes P4 (EL +109') (Office Sky Street) | 36 |  |  |  | day | 2022-08-08 07:00 | 2024-07-08 17:00 | [12 empty] | 10 | 5 | WOD5/7EmqkCEn09yecHXUg | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.11.1 | 41906743 | 41904418 | Interior Summary & Milestones | 9 |  |  |  | day | 2022-08-26 07:00 | 2024-07-08 17:00 | [12 empty] | 0 | 6 | q54vpLR0RkyzCdO8KxmWLQ | WOD5/7EmqkCEn09yecHXUg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.11.2 | 41906995 | 41904418 | P4 - Bulletin 55 | 9 |  |  |  | day | 2024-01-10 07:00 | 2024-01-30 17:00 | [12 empty] | 1 | 6 | IM4W0V9h0Uav9l75wqHOOQ | WOD5/7EmqkCEn09yecHXUg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.11.3 | 41906736 | 41904418 | Layout, Risers & Toptrack | 18 |  |  |  | day | 2022-08-29 07:00 | 2023-03-21 17:00 | [12 empty] | 2 | 6 | N0REHgu9MUWPaLm6ElryNw | WOD5/7EmqkCEn09yecHXUg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.11.4 | 41906737 | 41904418 | OH Rough |  |  |  |  | day | 2023-02-21 07:00 | 2024-01-10 17:00 | [12 empty] | 3 | 6 | m+lg7asbcEy0tHesXCUHMw | WOD5/7EmqkCEn09yecHXUg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.11.5 | 41906738 | 41904418 | Equipment | 20 |  |  |  | day | [14 empty] | 4 | 6 | bBIzO/H3m0CJFYPJY15z6A | WOD5/7EmqkCEn09yecHXUg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.11.6 | 41906739 | 41904418 | In-Wall Rough | 13 |  |  |  | day | 2023-12-27 07:00 | 2024-02-06 17:00 | [12 empty] | 5 | 6 | 4UXKCDTM2Uq5Kajmm6pgQA | WOD5/7EmqkCEn09yecHXUg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.11.7 | 41906740 | 41904418 | Finishes | 8 |  |  |  | day | 2024-02-07 07:00 | 2024-04-05 17:00 | [12 empty] | 6 | 6 | fMbaI/4CRkObFrrG1l5LiQ | WOD5/7EmqkCEn09yecHXUg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.11.8 | 41906741 | 41904418 | Elevator Lobbies |  |  |  |  | day | 2024-02-14 07:00 | 2024-03-29 17:00 | [12 empty] | 7 | 6 | UlpD3n/I3UifbGmsH9sMrw | WOD5/7EmqkCEn09yecHXUg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.11.9 | 41906742 | 41904418 | Garage Finishes |  |  |  |  | day | 2024-03-04 07:00 | 2024-07-08 17:00 | [12 empty] | 8 | 6 | 9PjVxZRA0EGGuvpKBlBYWQ | WOD5/7EmqkCEn09yecHXUg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.12 | 41904419 | 41904265 | Podium Rough and Finishes P5 (EL +122') (L10) | 44 |  |  |  | day | 2022-12-05 07:00 | 2024-11-01 17:00 | [12 empty] | 11 | 5 | 7wu9tWapAUqgnDPCWalTyQ | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.12.1 | 41906744 | 41904419 | Interior Summary & Milestones |  |  |  |  | day | 2023-12-26 07:00 | 2024-11-01 17:00 | [12 empty] | 0 | 6 | rkzlT9szX0WRzj2OJdbcuA | 7wu9tWapAUqgnDPCWalTyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.12.2 | 45115303 | 41904419 | Bulletin 130 |  |  |  |  | day | 2023-11-13 07:00 | 2024-05-06 17:00 | [12 empty] | 1 | 6 | z/8eaRlMWE2LF82cd13Kbg | 7wu9tWapAUqgnDPCWalTyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.12.3 | 41906996 | 41904419 | P5 - Bulletin 55 | 0 |  |  |  | day | 2024-01-24 07:00 | 2024-02-13 17:00 | [12 empty] | 2 | 6 | rYAEV7OPAkiix8eLubMnjA | 7wu9tWapAUqgnDPCWalTyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.12.4 | 41906745 | 41904419 | Layout, Risers & Toptrack |  |  |  |  | day | 2023-02-01 07:00 | 2023-07-10 17:00 | [12 empty] | 3 | 6 | /gLVfgY0WEy4Od+fY8aq/Q | 7wu9tWapAUqgnDPCWalTyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.12.5 | 41906746 | 41904419 | OH Rough | 39 |  |  |  | day | 2023-02-16 07:00 | 2024-01-03 17:00 | [12 empty] | 4 | 6 | hNGLXTbrykqfnrjeAPXzpA | 7wu9tWapAUqgnDPCWalTyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.12.6 | 41906747 | 41904419 | Equipment | 31 |  |  |  | day | [14 empty] | 5 | 6 | 9JXxweymokqP6jqPl5zb3w | 7wu9tWapAUqgnDPCWalTyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.12.7 | 41906748 | 41904419 | In-Wall Rough | 33 |  |  |  | day | 2024-05-07 07:00 | 2024-06-04 17:00 | [12 empty] | 6 | 6 | 9V0Xg+EzqEultKm7U2us9Q | 7wu9tWapAUqgnDPCWalTyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.12.8 | 41906749 | 41904419 | Finishes | 27 |  |  |  | day | 2024-06-05 07:00 | 2024-08-02 17:00 | [12 empty] | 7 | 6 | E07wdkrTnU2MQiLhbsQWzw | 7wu9tWapAUqgnDPCWalTyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.12.9 | 41906750 | 41904419 | Elevator Lobbies |  |  |  |  | day | 2024-06-12 07:00 | 2024-07-26 17:00 | [12 empty] | 8 | 6 | 4Fkj/qK8D0Kph/95sOXQQQ | 7wu9tWapAUqgnDPCWalTyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.12.10 | 41906751 | 41904419 | Garage Finishes | 7 |  |  |  | day | 2024-06-28 07:00 | 2024-11-01 17:00 | [12 empty] | 9 | 6 | nbQtz6MsyUCXk+QDFPe2HQ | 7wu9tWapAUqgnDPCWalTyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.13 | 41904420 | 41904265 | Podium Rough and Finishes L11 (EL +135') (Residential Sky Street) |  |  |  |  | day | [14 empty] | 12 | 5 | aH7B+P5Ko0uSA52RzpZJGg | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.14 | 41904421 | 41904265 | Podium Rough and Finishes L12 (EL +148) (Top of Walkway) |  |  |  |  | day | [14 empty] | 13 | 5 | q89rX3Y6Mk2eDYYu+0O4fQ | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.15 | 41904395 | 41904265 | New Primary Electric Service from Atlantic Ave |  |  |  |  | day | [14 empty] | 14 | 5 | h4TlBWwm7UyiYkQs5iKTXw | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.8.16 | 41904552 | 41904265 | Podium - Atlantic Entrance UG/ SOG | 2 |  |  |  | day | [14 empty] | 15 | 5 | Z8o/GpkgTUmGoqfjZTDUiA | t1PjyV/kJkSV1+bBZ6hoUw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.2.9 | 41904266 | 41904241 | Podium Finishes |  |  |  |  | day | 2024-01-30 07:00 | 2024-06-05 17:00 | [12 empty] | 8 | 4 | Qiyn1lN4zEaoS+jpqNfsAQ | Tk7ZcUqLokiVH5BGj9QkhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.3 | 41904246 | 41905203 | Existing Bus Terminal (Night Shift Hours 8:00 pm to 5:00 am) |  |  |  |  | day | 2023-12-26 07:00 | 2023-12-26 17:00 | [12 empty] | 2 | 3 | AQ+PQqWBb0islgdHda/Khw | iRqoq5YdVEasR9RY3sZSmg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.3.1 | 41904305 | 41904246 | Fireproofing Underside of Existing Bus Terminal (El +49') | 0 |  |  |  | day | [14 empty] | 0 | 4 | 18fyr9ZBJE2BDpwJDN5O1w | AQ+PQqWBb0islgdHda/Khw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.3.1.1 | 41904490 | 41904305 | 2020 Summer Months (April- October) | 43 |  |  |  | day | [14 empty] | 0 | 5 | kxp1WdQucUa8P/1EznXtTg | 18fyr9ZBJE2BDpwJDN5O1w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.3.1.2 | 41904491 | 41904305 | 2021 Summer Months (April- October) | 4 |  |  |  | day | [14 empty] | 1 | 5 | BVLsd9GRDUCIg+EvrIh7IQ | 18fyr9ZBJE2BDpwJDN5O1w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4 | 41904236 | 41905203 | Tower Office / C/S | 0 | 2023-09-07 08:00 | 2023-10-12 17:00 | 26 | day | 2020-09-18 07:00 | 2025-05-01 17:00 | [12 empty] | 3 | 3 | MjDx2K8Y4ki27Z8wd1MiAw | iRqoq5YdVEasR9RY3sZSmg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1 | 41905269 | 41904236 | ENABLING TOWER FOUNDATION | 29 |  |  |  | day | 2020-09-18 07:00 | 2024-01-15 17:00 | [12 empty] | 0 | 4 | tuvybnxZOUu6qV59D6WXkw | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.1 | 41905270 | 41905269 | Demo (Finish Working Off +3') | 16 |  |  |  | day | 2021-03-18 07:00 | 2021-04-22 17:00 | [12 empty] | 0 | 5 | ShGSC24zsku9KQ7PPG+TnA | tuvybnxZOUu6qV59D6WXkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.2 | 41905271 | 41905269 | Clear Obstructions and Excavate/Backfill (Working Off +3') | 47 |  |  |  | day | 2021-05-06 07:00 | 2021-09-29 17:00 | [12 empty] | 1 | 5 | 4tVTAKHa90WGLAe8sUwLyw | tuvybnxZOUu6qV59D6WXkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.2.1 | 41905272 | 41905271 | Clear Obstructions for Sheets |  |  |  |  | day | 2021-05-06 07:00 | 2021-09-29 17:00 | [12 empty] | 0 | 6 | dUU5csXuWkyJGl5QijchGQ | 4tVTAKHa90WGLAe8sUwLyw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.2.2 | 41905273 | 41905271 | Clear Obstructions for LBE |  |  |  |  | day | [14 empty] | 1 | 6 | pT6Mp7v0vk6LEyy1gc4YRQ | 4tVTAKHa90WGLAe8sUwLyw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.3 | 41905274 | 41905269 | DMP 36-Line (Working Off +3') | 14 |  |  |  | day | 2021-05-20 07:00 | 2021-06-11 17:00 | [12 empty] | 2 | 5 | r/0Q1gNzS0yZH0WkUduGuA | tuvybnxZOUu6qV59D6WXkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.4 | 41905275 | 41905269 | SOE | 36 |  |  |  | day | 2021-03-08 07:00 | 2021-08-25 17:00 | [12 empty] | 3 | 5 | zaYhjNktb0u0IDB8UDbwww | tuvybnxZOUu6qV59D6WXkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.4.1 | 41905276 | 41905275 | Temp Bridge (Working Off +18') | 20 |  |  |  | day | 2021-03-08 07:00 | 2021-08-25 17:00 | [12 empty] | 0 | 6 | GQlykSIXjkCqXtWI18Q9Dw | zaYhjNktb0u0IDB8UDbwww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.4.2 | 41905277 | 41905275 | Remaining Sheets (Working Off +14') |  |  |  |  | day | 2021-06-07 07:00 | 2021-06-19 17:00 | [12 empty] | 1 | 6 | WFK5jtKmuE29Ai07SsGP1w | zaYhjNktb0u0IDB8UDbwww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.5 | 41905278 | 41905269 | LBE(Working Off +14') |  |  |  |  | day | [14 empty] | 4 | 5 | z/vyM9Rc70GrS6WIE0IaLQ | tuvybnxZOUu6qV59D6WXkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.6 | 41905388 | 41905269 | Enabling - Service Coordior LBE 45 & 46 | 10 |  |  |  | day | 2021-09-13 07:00 | 2021-12-29 17:00 | [12 empty] | 5 | 5 | gVtmZCNdwky8lNR9Uyp7iA | tuvybnxZOUu6qV59D6WXkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.7 | 41905184 | 41905269 | Existing Headhouse Roof | 38 |  |  |  | day | 2020-09-18 07:00 | 2024-01-15 17:00 | [12 empty] | 6 | 5 | Y5lRLJHD0kOSUcPfBIbuqg | tuvybnxZOUu6qV59D6WXkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.7.1 | 41905190 | 41905184 | As-Built | 37 |  |  |  | day | 2022-09-07 07:00 | 2022-09-30 17:00 | [12 empty] | 0 | 6 | GZoHMKWipUedSXxv+hVBtQ | Y5lRLJHD0kOSUcPfBIbuqg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.7.2 | 41905185 | 41905184 | RTU-1A | 33 |  |  |  | day | 2022-09-15 07:00 | 2023-06-30 17:00 | [12 empty] | 1 | 6 | KYB+y+FGG06zcbYM/LwQ0Q | Y5lRLJHD0kOSUcPfBIbuqg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.7.3 | 41905186 | 41905184 | RTU-1B | 37 |  |  |  | day | 2022-09-15 07:00 | 2023-06-30 17:00 | [12 empty] | 2 | 6 | r3TnM3bVvEeM1kIhiAvy5g | Y5lRLJHD0kOSUcPfBIbuqg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.7.4 | 41905187 | 41905184 | EF-20 | 49 |  |  |  | day | 2022-10-07 07:00 | 2024-01-15 17:00 | [12 empty] | 3 | 6 | 8DgwkVbFxkC3lewnDhvj8Q | Y5lRLJHD0kOSUcPfBIbuqg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.1.7.5 | 41905188 | 41905184 | ACC-1 | 33 |  |  |  | day | 2020-09-18 07:00 | 2021-03-12 17:00 | [12 empty] | 4 | 6 | tsqeCkVDX0iuJICfFuLD6g | Y5lRLJHD0kOSUcPfBIbuqg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2 | 41904269 | 41904236 | TOWER FOUNDATIONS (El +3.5') |  |  |  |  | day | 2021-09-06 07:00 | 2022-03-10 17:00 | [12 empty] | 1 | 4 | FV8Al1mrsUurjUobZk3mUQ | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1 | 41904484 | 41904269 | LBEs (Double Shift) | 29 |  |  |  | day | 2021-09-06 07:00 | 2022-03-10 17:00 | [12 empty] | 0 | 5 | KOjGtXJ75UivR0Sk9BGKJQ | FV8Al1mrsUurjUobZk3mUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.1 | 41904741 | 41904484 | LBE Seq01-10 | 14 |  |  |  | day | 2021-10-20 07:00 | 2021-11-10 17:00 | [12 empty] | 0 | 6 | RRfsaozdKES6flsvLmhZ4g | KOjGtXJ75UivR0Sk9BGKJQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.1.1 | 41904889 | 41904741 | LBE-39 | 26 |  |  |  | day | 2021-10-20 07:00 | 2021-10-22 17:00 | [12 empty] | 0 | 7 | 75UGo8urQkGsrLilhLLFhA | RRfsaozdKES6flsvLmhZ4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.1.2 | 41904890 | 41904741 | LBE-09 | 33 |  |  |  | day | 2021-10-21 07:00 | 2021-10-25 17:00 | [12 empty] | 1 | 7 | t269BJYykU+lXYlSn/keRA | RRfsaozdKES6flsvLmhZ4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.1.3 | 41904896 | 41904741 | LBE-37 | 37 |  |  |  | day | 2021-10-23 07:00 | 2021-10-26 17:00 | [12 empty] | 2 | 7 | vW3ieg2woEiYlR8pQZHH3g | RRfsaozdKES6flsvLmhZ4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.1.4 | 41904891 | 41904741 | LBE-40 | 32 |  |  |  | day | 2021-10-25 07:00 | 2021-10-28 17:00 | [12 empty] | 3 | 7 | nWqASy04X0aYQVIsb8xu0Q | RRfsaozdKES6flsvLmhZ4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.1.5 | 41904892 | 41904741 | LBE-13 | 23 |  |  |  | day | 2021-10-26 07:00 | 2021-10-29 17:00 | [12 empty] | 4 | 7 | o4l7jR58kEu/cACbNS6kNg | RRfsaozdKES6flsvLmhZ4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.1.6 | 41904893 | 41904741 | LBE-03 | 14 |  |  |  | day | 2021-10-23 07:00 | 2021-11-01 17:00 | [12 empty] | 5 | 7 | nPm18o0QFkus9OW6/fs+Fg | RRfsaozdKES6flsvLmhZ4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.1.7 | 41904899 | 41904741 | LBE-20 |  |  |  |  | day | 2021-10-29 07:00 | 2021-11-08 17:00 | [12 empty] | 6 | 7 | gjdpG4Ge10+qEfrpF3UU4w | RRfsaozdKES6flsvLmhZ4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.1.8 | 41904894 | 41904741 | LBE-28 | 41 |  |  |  | day | 2021-10-29 07:00 | 2021-11-05 17:00 | [12 empty] | 7 | 7 | vYn1/rXAjU6BirWb8/Go3g | RRfsaozdKES6flsvLmhZ4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.1.9 | 41904910 | 41904741 | LBE-10 |  |  |  |  | day | 2021-11-05 07:00 | 2021-11-10 17:00 | [12 empty] | 8 | 7 | B0I+XTxHDUmkbntKs6qo1Q | RRfsaozdKES6flsvLmhZ4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.1.10 | 41904903 | 41904741 | LBE-41 | 4 |  |  |  | day | 2021-11-02 07:00 | 2021-11-09 17:00 | [12 empty] | 9 | 7 | YZDa6xYOBESRpUnQMKoqhg | RRfsaozdKES6flsvLmhZ4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2 | 41904742 | 41904484 | LBE Seq11-20 | 28 |  |  |  | day | 2021-11-05 07:00 | 2021-12-01 17:00 | [12 empty] | 1 | 6 | XNCgT7YrmUuHdfuREDDJ0A | KOjGtXJ75UivR0Sk9BGKJQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2.1 | 41904900 | 41904742 | LBE-32 | 3 |  |  |  | day | 2021-11-05 07:00 | 2021-11-10 17:00 | [12 empty] | 0 | 7 | 5k7Jqqo/4E22PnYtWVIpEg | XNCgT7YrmUuHdfuREDDJ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2.2 | 41904924 | 41904742 | LBE-14 | 9 |  |  |  | day | 2021-11-09 07:00 | 2021-11-12 17:00 | [12 empty] | 1 | 7 | E4tAsTr0nE6cQ5Pet/a8qA | XNCgT7YrmUuHdfuREDDJ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2.3 | 41904907 | 41904742 | LBE-02 | 16 |  |  |  | day | 2021-11-10 07:00 | 2021-11-15 17:00 | [12 empty] | 2 | 7 | RhfazUUMo0CfH6x94w65+A | XNCgT7YrmUuHdfuREDDJ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2.4 | 41904904 | 41904742 | LBE-22 |  |  |  |  | day | 2021-11-15 07:00 | 2021-11-17 17:00 | [12 empty] | 3 | 7 | lH6X098zIkW8BtDgLhQwYg | XNCgT7YrmUuHdfuREDDJ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2.5 | 41904911 | 41904742 | LBE-29 |  |  |  |  | day | 2021-11-16 07:00 | 2021-11-19 17:00 | [12 empty] | 4 | 7 | 9hhrJDK0dUyQsaO8NfFYxQ | XNCgT7YrmUuHdfuREDDJ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2.6 | 41904913 | 41904742 | LBE-07 | 19 |  |  |  | day | 2021-11-18 07:00 | 2021-11-22 17:00 | [12 empty] | 5 | 7 | x4aSCmNDvk+G/Wc79mky/w | XNCgT7YrmUuHdfuREDDJ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2.7 | 41904898 | 41904742 | LBE-38 |  |  |  |  | day | 2021-11-20 07:00 | 2021-11-23 17:00 | [12 empty] | 6 | 7 | eVct0Fb+mUaXDd5kYN9CuA | XNCgT7YrmUuHdfuREDDJ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2.8 | 41904902 | 41904742 | LBE-33 |  |  |  |  | day | 2021-11-22 07:00 | 2021-11-24 17:00 | [12 empty] | 7 | 7 | ZllrvJWEAEqk73284lSfsQ | XNCgT7YrmUuHdfuREDDJ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2.9 | 41904901 | 41904742 | LBE-24 | 33 |  |  |  | day | 2021-11-23 07:00 | 2021-11-26 17:00 | [12 empty] | 8 | 7 | HdzQRST+KU6TEqCFLOqOuQ | XNCgT7YrmUuHdfuREDDJ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2.10 | 41904905 | 41904742 | LBE-36 | 5 |  |  |  | day | 2021-11-26 07:00 | 2021-11-29 17:00 | [12 empty] | 9 | 7 | RBrcBhRH0kyTrY0qof85ZA | XNCgT7YrmUuHdfuREDDJ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.2.11 | 41904897 | 41904742 | LBE-12 | 1 |  |  |  | day | 2021-11-27 07:00 | 2021-12-01 17:00 | [12 empty] | 10 | 7 | f4pe56D6BEOvPDiPGE01OA | XNCgT7YrmUuHdfuREDDJ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.3 | 41904743 | 41904484 | LBE Seq 21-30 | 12 |  |  |  | day | 2021-11-30 07:00 | 2021-12-17 17:00 | [12 empty] | 2 | 6 | uISCPmofG06OHCHTNxOtfw | KOjGtXJ75UivR0Sk9BGKJQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.3.1 | 41904906 | 41904743 | LBE-01 |  |  |  |  | day | 2021-11-30 07:00 | 2021-12-03 17:00 | [12 empty] | 0 | 7 | 0KEgZCWeYUC3jon19F3SwQ | uISCPmofG06OHCHTNxOtfw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.3.2 | 41904908 | 41904743 | LBE-31 |  |  |  |  | day | 2021-12-01 07:00 | 2021-12-06 17:00 | [12 empty] | 1 | 7 | t0zFWxqUck2gAUAiKKiUSA | uISCPmofG06OHCHTNxOtfw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.3.3 | 41904909 | 41904743 | LBE-21 | 47 |  |  |  | day | 2021-12-03 07:00 | 2021-12-08 17:00 | [12 empty] | 2 | 7 | ML+RvYviu0auN/79q4ymVw | uISCPmofG06OHCHTNxOtfw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.3.4 | 41904895 | 41904743 | LBE-05 | 10 |  |  |  | day | 2021-12-07 07:00 | 2021-12-09 17:00 | [12 empty] | 3 | 7 | A/n3l9h7fUiyMvpyLtnKHQ | uISCPmofG06OHCHTNxOtfw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.3.5 | 41904912 | 41904743 | LBE-42 |  |  |  |  | day | 2021-12-08 07:00 | 2021-12-10 17:00 | [12 empty] | 4 | 7 | OR48MzT57EG0kQQJ63B2Tw | uISCPmofG06OHCHTNxOtfw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.3.6 | 41904914 | 41904743 | LBE-26 | 22 |  |  |  | day | 2021-12-09 07:00 | 2021-12-13 17:00 | [12 empty] | 5 | 7 | SgvvwzBALUOFjEF4aK9I8A | uISCPmofG06OHCHTNxOtfw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.3.7 | 41904915 | 41904743 | LBE-30 | 15 |  |  |  | day | 2021-12-10 07:00 | 2021-12-15 17:00 | [12 empty] | 6 | 7 | thorOFDzyESKF8dTSCIq8w | uISCPmofG06OHCHTNxOtfw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.3.8 | 41904916 | 41904743 | LBE-08 |  |  |  |  | day | 2021-12-13 07:00 | 2021-12-16 17:00 | [12 empty] | 7 | 7 | ARbphBa5IUChfFlCEm5qaQ | uISCPmofG06OHCHTNxOtfw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.3.9 | 41904917 | 41904743 | LBE-04 | 10 |  |  |  | day | 2021-12-15 07:00 | 2021-12-17 17:00 | [12 empty] | 8 | 7 | 927RemiNrUiaRc5Zu0K3DQ | uISCPmofG06OHCHTNxOtfw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.3.10 | 41904918 | 41904743 | LBE-07 |  |  |  |  | day | 2021-12-16 07:00 | 2021-12-17 17:00 | [12 empty] | 9 | 7 | GuiPm9/yqEe9/T1HWfXrNA | uISCPmofG06OHCHTNxOtfw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.4 | 41905494 | 41904484 | LBE Seq 31-40 | 7 |  |  |  | day | 2021-12-16 07:00 | 2022-01-04 17:00 | [12 empty] | 3 | 6 | LXy5NONPaEaRUYPYwx3I6A | KOjGtXJ75UivR0Sk9BGKJQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.4.1 | 41904919 | 41905494 | LBE-25 |  |  |  |  | day | 2021-12-16 07:00 | 2021-12-22 17:00 | [12 empty] | 0 | 7 | k6rEgGnTIE+mLZH82Wgxhw | LXy5NONPaEaRUYPYwx3I6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.4.2 | 41904920 | 41905494 | LBE-44 |  |  |  |  | day | 2021-12-18 07:00 | 2021-12-22 17:00 | [12 empty] | 1 | 7 | gTxJ6foIg0uOMbXQeDNovQ | LXy5NONPaEaRUYPYwx3I6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.4.3 | 41904921 | 41905494 | LBE-08 |  |  |  |  | day | 2021-12-20 07:00 | 2021-12-23 17:00 | [12 empty] | 2 | 7 | zqU+GIzIO0yxGw/g7VQ1ug | LXy5NONPaEaRUYPYwx3I6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.4.4 | 41904922 | 41905494 | LBE-19 | 24 |  |  |  | day | 2021-12-21 07:00 | 2021-12-27 17:00 | [12 empty] | 3 | 7 | DK4pMRu6MkmfZkE8ieT8Mw | LXy5NONPaEaRUYPYwx3I6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.4.5 | 41904923 | 41905494 | LBE-31 | 2 |  |  |  | day | 2021-12-22 07:00 | 2021-12-28 17:00 | [12 empty] | 4 | 7 | 6ce1xvqcvkSwyBkCUV4LZQ | LXy5NONPaEaRUYPYwx3I6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.4.6 | 41904925 | 41905494 | LBE-35 |  |  |  |  | day | 2021-12-23 07:00 | 2021-12-29 17:00 | [12 empty] | 5 | 7 | uciE6vgRk0CAzukXLfmGlw | LXy5NONPaEaRUYPYwx3I6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.4.7 | 41904926 | 41905494 | LBE-17 | 2 |  |  |  | day | 2021-12-27 07:00 | 2021-12-30 17:00 | [12 empty] | 6 | 7 | TBHCgbG+0Ue4OrV3B0cJyg | LXy5NONPaEaRUYPYwx3I6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.4.8 | 41904927 | 41905494 | LBE-06 | 26 |  |  |  | day | 2021-12-28 07:00 | 2022-01-03 17:00 | [12 empty] | 7 | 7 | g9+evpQFBUudslDr5MSddQ | LXy5NONPaEaRUYPYwx3I6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.4.9 | 41904928 | 41905494 | LBE-36 |  |  |  |  | day | 2021-12-29 07:00 | 2022-01-04 17:00 | [12 empty] | 8 | 7 | 6/hfXLMy6k2mWrsAtg6Xbw | LXy5NONPaEaRUYPYwx3I6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.5 | 41905495 | 41904484 | LBE Seq 41-49 |  |  |  |  | day | 2021-12-30 07:00 | 2022-01-27 17:00 | [12 empty] | 4 | 6 | Hd2huTFJTU63D6l3tG1fWw | KOjGtXJ75UivR0Sk9BGKJQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.5.1 | 41904929 | 41905495 | LBE-17 | 49 |  |  |  | day | 2021-12-30 07:00 | 2022-01-05 17:00 | [12 empty] | 0 | 7 | 1RvHxGZ5Xk+HtJ7rOVWGpA | Hd2huTFJTU63D6l3tG1fWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.5.2 | 41904930 | 41905495 | LBE-44 | 18 |  |  |  | day | 2022-01-04 07:00 | 2022-01-07 17:00 | [12 empty] | 1 | 7 | rj6z9FDpi02/9xMF6bAwAg | Hd2huTFJTU63D6l3tG1fWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.5.3 | 41904931 | 41905495 | LBE-45 | 20 |  |  |  | day | 2022-01-06 07:00 | 2022-01-14 17:00 | [12 empty] | 2 | 7 | 08B1tieXtUWpcpT+OpPhuw | Hd2huTFJTU63D6l3tG1fWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.5.4 | 41904932 | 41905495 | LBE-15 |  |  |  |  | day | 2022-01-13 07:00 | 2022-01-17 17:00 | [12 empty] | 3 | 7 | CjkxlJIhZ0K/Q4+2IRj3UA | Hd2huTFJTU63D6l3tG1fWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.5.5 | 41904933 | 41905495 | LBE-43 | 17 |  |  |  | day | 2022-01-17 07:00 | 2022-01-18 17:00 | [12 empty] | 4 | 7 | /3ejDtTej0GSxZdGcW4rYQ | Hd2huTFJTU63D6l3tG1fWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.5.6 | 41904934 | 41905495 | LBE-TC1(47) |  |  |  |  | day | 2022-01-19 07:00 | 2022-01-20 17:00 | [12 empty] | 5 | 7 | 2m9VMKvI2ka6gC4OxX/66A | Hd2huTFJTU63D6l3tG1fWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.5.7 | 41905467 | 41905495 | LBE-46 | 41 |  |  |  | day | 2022-01-18 07:00 | 2022-01-21 17:00 | [12 empty] | 6 | 7 | oXn0Qm/aFE2FeFQx6CBfCw | Hd2huTFJTU63D6l3tG1fWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.5.8 | 41905468 | 41905495 | LBE-TC2(48) | 21 |  |  |  | day | 2022-01-24 07:00 | 2022-01-25 17:00 | [12 empty] | 7 | 7 | PxiMW2OQS0Ssf3L7ob5JQA | Hd2huTFJTU63D6l3tG1fWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.5.9 | 41905469 | 41905495 | LBE-TC2(49) | 20 |  |  |  | day | 2022-01-25 07:00 | 2022-01-27 17:00 | [12 empty] | 8 | 7 | yKWdwbsdiE6ZCqw0ZoaGbA | Hd2huTFJTU63D6l3tG1fWw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.1.6 | 41904744 | 41904484 | Demob |  |  |  |  | day | 2022-01-28 07:00 | 2022-02-11 17:00 | [12 empty] | 5 | 6 | /a14lWyA5kWS7FyUfkU90w | KOjGtXJ75UivR0Sk9BGKJQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.2 | 41904486 | 41904269 | Mini Piles (Standard Shift) | 0 |  |  |  | day | [14 empty] | 1 | 5 | MEE13IivQkyJTSPRgO0T6Q | FV8Al1mrsUurjUobZk3mUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.3 | 41904485 | 41904269 | Grade Beams (El -2.75' to +17.25') (Double Shift 5d/week) | 4 |  |  |  | day | [14 empty] | 2 | 5 | zxZ6/HaKJkCzP8dB7pF6TA | FV8Al1mrsUurjUobZk3mUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.3.1 | 41904745 | 41904485 | NGB, SGB, WGB, EGB | 40 |  |  |  | day | [14 empty] | 0 | 6 | JOywU1ZkLEqns9mAIw/D6g | zxZ6/HaKJkCzP8dB7pF6TA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.3.2 | 41904746 | 41904485 | West - GB-1 GB-3 GB-3A & P1 El +3.53" Slabs |  |  |  |  | day | [14 empty] | 1 | 6 | dgBA/YKBRkul1tJVZ9BqTA | zxZ6/HaKJkCzP8dB7pF6TA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.3.3 | 41904785 | 41904485 | East - Enabling for Grade Beam 3 (LBE 45 & 46) | 25 |  |  |  | day | [14 empty] | 2 | 6 | uU90aXeONkagHETiBkw7tA | zxZ6/HaKJkCzP8dB7pF6TA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.3.4 | 41904747 | 41904485 | East - GB-2 GB-3 & P1 El +3.53" Slabs | 45 |  |  |  | day | [14 empty] | 3 | 6 | VYSbOn7KrUuv+J5VqvNYBQ | zxZ6/HaKJkCzP8dB7pF6TA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.2.3.5 | 41904786 | 41904485 | South - Storage | 33 |  |  |  | day | [14 empty] | 4 | 6 | Dsw9UDdt8UyPpO93//6gZw | zxZ6/HaKJkCzP8dB7pF6TA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.3 | 41905470 | 41904236 | TOWER MASS EXCAVATION |  |  |  |  | day | 2022-02-15 07:00 | 2022-05-19 17:00 | [12 empty] | 2 | 4 | ZD4Yw6GdkEO2oVbT2/T2Aw | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.3.1 | 41906657 | 41905470 | Final Design for Temp Bridge Stablization | 13 |  |  |  | day | 2022-03-07 07:00 | 2022-05-19 17:00 | [12 empty] | 0 | 5 | NWJ1a4zxm0eeM0/81E97Yw | ZD4Yw6GdkEO2oVbT2/T2Aw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.3.1.1 | 41906658 | 41906657 | Design |  |  |  |  | day | 2022-03-10 07:00 | 2022-04-26 17:00 | [12 empty] | 0 | 6 | 2a471FrAmkK3nZ6mfJvs5w | NWJ1a4zxm0eeM0/81E97Yw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.3.1.2 | 41906660 | 41906657 | Added Scope |  |  |  |  | day | 2022-03-14 07:00 | 2022-05-19 17:00 | [12 empty] | 1 | 6 | 2+yFjSqOJEeaRV3Re1BbZA | NWJ1a4zxm0eeM0/81E97Yw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4 | 41904253 | 41904236 | TOWER STRUCTURE |  |  |  |  | day | 2021-10-20 07:00 | 2024-09-18 17:00 | [12 empty] | 3 | 4 | sZchiSLlkUSGEhHuiFwXFA | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.1 | 41905493 | 41904253 | Summarys | 8 |  |  |  | day | 2021-10-20 07:00 | 2024-06-13 17:00 | [12 empty] | 0 | 5 | BEaVDO9VK0SpAPoPZorvnA | sZchiSLlkUSGEhHuiFwXFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.1.1 | 41905497 | 41905493 | LBE | 25 |  |  |  | day | 2021-10-20 07:00 | 2022-05-09 17:00 | [12 empty] | 0 | 6 | QpR5QjoSKEOdZIcRG7W6XA | BEaVDO9VK0SpAPoPZorvnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.1.2 | 44452453 | 41905493 | Core | 46 |  |  |  | day | 2022-04-14 07:00 | 2023-08-09 17:00 | [12 empty] | 1 | 6 |  | BEaVDO9VK0SpAPoPZorvnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.1.3 | 41905499 | 41905493 | Concrete Structure | 21 |  |  |  | day | 2023-12-26 07:00 | 2024-05-22 17:00 | [12 empty] | 2 | 6 | tT1oF8vxk0OMMjZSbDz05A | BEaVDO9VK0SpAPoPZorvnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.1.4 | 41905498 | 41905493 | Structural Steel |  |  |  |  | day | 2023-01-11 07:00 | 2024-06-13 17:00 | [12 empty] | 3 | 6 | 7OIOJtXfrkKWepMcbhOk6Q | BEaVDO9VK0SpAPoPZorvnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.2 | 41904306 | 41904253 | TOWER CRANE | 29 |  |  |  | day | 2022-03-07 07:00 | 2024-09-18 17:00 | [12 empty] | 1 | 5 | Ad199XlDJkWZJur+2a5VxQ | sZchiSLlkUSGEhHuiFwXFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.2.1 | 41904497 | 41904306 | Tower Crane #01- Core- WOLFF 1250B | 42 |  |  |  | day | 2022-03-07 07:00 | 2023-11-25 17:00 | [12 empty] | 0 | 6 | N9nY/Btf9k+ttq9OFctOZg | Ad199XlDJkWZJur+2a5VxQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.2.2 | 41904498 | 41904306 | Tower Crane #02- Exterior- WOLFF 700B | 47 |  |  |  | day | 2022-04-04 07:00 | 2024-09-18 17:00 | [12 empty] | 1 | 6 | 2e5VtCjoHk6YxitNRe4ZLw | Ad199XlDJkWZJur+2a5VxQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.2.2.1 | 41906661 | 41904498 | P605 | 16 |  |  |  | day | 2022-04-04 07:00 | 2023-03-05 17:00 | [12 empty] | 0 | 7 | yVjA46+DG0qGPBcPhQel1A | 2e5VtCjoHk6YxitNRe4ZLw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.2.2.2 | 41906662 | 41904498 | 700B | 25 |  |  |  | day | 2023-03-05 07:00 | 2024-09-18 17:00 | [12 empty] | 1 | 7 | rv6gBm0KUUCClQxyP1px4Q | 2e5VtCjoHk6YxitNRe4ZLw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.2.3 | 41905386 | 41904306 | TC2 | 35 |  |  |  | day | [14 empty] | 2 | 6 | 81J5+fOco0erVCIuYwBnlA | Ad199XlDJkWZJur+2a5VxQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.3 | 41905471 | 41904253 | Grade Beams | 0 |  |  |  | day | 2022-03-28 07:00 | 2022-07-30 17:00 | [12 empty] | 2 | 5 | sTz2IpuFSEil0wAAJ256Ng | sZchiSLlkUSGEhHuiFwXFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.3.1 | 41906754 | 41905471 | GB-1 TK.8 T3/T6 | 7 |  |  |  | day | 2022-03-31 07:00 | 2022-05-06 17:00 | [12 empty] | 0 | 6 | MeIrSZYC4kaSNdDIYMn6+w | sTz2IpuFSEil0wAAJ256Ng | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.3.2 | 41906756 | 41905471 | T6 Caps | 48 |  |  |  | day | 2022-04-20 07:00 | 2022-04-28 17:00 | [12 empty] | 1 | 6 | 79TSjyVqCUevEgEVGo5L+w | sTz2IpuFSEil0wAAJ256Ng | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.3.3 | 41906755 | 41905471 | SGB, WGB, NGB, EGB |  |  |  |  | day | 2022-04-14 07:00 | 2022-06-17 17:00 | [12 empty] | 2 | 6 | 7lzCu52b/USzhnoCzoU22A | sTz2IpuFSEil0wAAJ256Ng | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.3.4 | 41905500 | 41905471 | GB-3 and GB-2 Service Corridor | 14 |  |  |  | day | 2022-03-28 07:00 | 2022-07-30 17:00 | [12 empty] | 3 | 6 | cpicTZfUHEaAkOJlGDmiVg | sTz2IpuFSEil0wAAJ256Ng | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.3.4.1 | 41906764 | 41905500 | Outside Corridor | 46 |  |  |  | day | 2022-05-27 07:00 | 2022-07-30 17:00 | [12 empty] | 0 | 7 | 1+jJ9lh070mkTRbrDOwfFg | cpicTZfUHEaAkOJlGDmiVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.3.5 | 41906762 | 41905471 | South Wall - Basement Expansion |  |  |  |  | day | 2022-05-18 07:00 | 2022-07-21 17:00 | [12 empty] | 4 | 6 | WX+KnTNM00uALvaZa4fuIA | sTz2IpuFSEil0wAAJ256Ng | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.4 | 41905472 | 41904253 | 17 |  |  |  |  | day | 2022-06-08 07:00 | 2022-12-21 17:00 | [12 empty] | 3 | 5 | ZhMisT8CaEGvN7+zBE/pPg | sZchiSLlkUSGEhHuiFwXFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.4.1 | 41906757 | 41905472 | Center of Cap Beam | 25 |  |  |  | day | 2022-06-08 07:00 | 2022-12-21 17:00 | [12 empty] | 0 | 6 | P2pGzbcdykG0pRARNj7E8w | ZhMisT8CaEGvN7+zBE/pPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.4.2 | 41906758 | 41905472 | West Basement | 27 |  |  |  | day | 2022-06-24 07:00 | 2022-07-08 17:00 | [12 empty] | 1 | 6 | OI4TOAloSUKYtAdsTZcOLQ | ZhMisT8CaEGvN7+zBE/pPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.4.3 | 41906759 | 41905472 | South Basement | 22 |  |  |  | day | 2022-07-07 07:00 | 2022-07-29 17:00 | [12 empty] | 2 | 6 | rTkY3qgNb0a+J/B9XzdlpQ | ZhMisT8CaEGvN7+zBE/pPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.4.4 | 41906760 | 41905472 | East Basement | 13 |  |  |  | day | 2022-07-25 07:00 | 2022-08-11 17:00 | [12 empty] | 3 | 6 | xtLW5Z6BbEe11slTiKNu6A | ZhMisT8CaEGvN7+zBE/pPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.4.5 | 41906761 | 41905472 | Steel Erection | 23 |  |  |  | day | 2022-07-13 07:00 | 2022-08-23 17:00 | [12 empty] | 4 | 6 | o8xjAJMRMkSS9UH0pTdCbA | ZhMisT8CaEGvN7+zBE/pPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.4.5.1 | 41906792 | 41906761 | West | 1 |  |  |  | day | 2022-07-13 07:00 | 2022-07-27 17:00 | [12 empty] | 0 | 7 |  | o8xjAJMRMkSS9UH0pTdCbA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.4.5.2 | 41906793 | 41906761 | South | 44 |  |  |  | day | 2022-08-03 07:00 | 2022-08-12 17:00 | [12 empty] | 1 | 7 | Fy6v5MwMpEeGG9BhsObbNA | o8xjAJMRMkSS9UH0pTdCbA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.4.5.3 | 41906794 | 41906761 | East | 25 |  |  |  | day | 2022-07-29 07:00 | 2022-08-23 17:00 | [12 empty] | 2 | 7 | FsZONoWwxU6F98agND+z+g | o8xjAJMRMkSS9UH0pTdCbA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.4.6 | 41906763 | 41905472 | SOMD and SOG +18 | 13 |  |  |  | day | 2022-08-24 07:00 | 2022-08-26 17:00 | [12 empty] | 5 | 6 | 1N2Qisc38Em4Bvs7V4Utkg | ZhMisT8CaEGvN7+zBE/pPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.5 | 41905473 | 41904253 | 17-83 | 6 |  |  |  | day | 2022-06-06 07:00 | 2022-09-27 17:00 | [12 empty] | 4 | 5 | xio9yxyqn0mQxQblPSiolA | sZchiSLlkUSGEhHuiFwXFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.5.1 | 41906806 | 41905473 | Pre-Pour 03 | 2 |  |  |  | day | 2022-06-06 07:00 | 2022-08-30 17:00 | [12 empty] | 0 | 6 | jjAIgasK60i7zn7SJISbXA | xio9yxyqn0mQxQblPSiolA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.5.2 | 41906802 | 41905473 | Pour 03 to +52-10" | 46 |  |  |  | day | 2022-08-16 07:00 | 2022-09-12 17:00 | [12 empty] | 1 | 6 | KdsnsXVLX06YGpWrzwex5w | xio9yxyqn0mQxQblPSiolA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.5.3 | 41906803 | 41905473 | Pour 04 to +63'8" | 22 |  |  |  | day | 2022-08-25 07:00 | 2022-09-15 17:00 | [12 empty] | 2 | 6 | hyRZ9oFkjU2C1qnX5RMWDQ | xio9yxyqn0mQxQblPSiolA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.5.4 | 41906804 | 41905473 | Pour 05 to +74'-6" | 45 |  |  |  | day | 2022-09-16 07:00 | 2022-09-19 17:00 | [12 empty] | 3 | 6 | rR/UNlyGDkmzaEF9KnDT7w | xio9yxyqn0mQxQblPSiolA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.5.5 | 41906805 | 41905473 | Pour 06 to +83' | 42 |  |  |  | day | 2022-09-20 07:00 | 2022-09-27 17:00 | [12 empty] | 4 | 6 | Y4+maRJVIkWBcGlmLYkAEA | xio9yxyqn0mQxQblPSiolA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.6 | 41905474 | 41904253 | CORE 83-109 |  |  |  |  | day | 2022-09-29 07:00 | 2022-12-17 17:00 | [12 empty] | 5 | 5 | 2EqH7Hg9r0+1Tsy8atV50g | sZchiSLlkUSGEhHuiFwXFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.6.1 | 41906855 | 41905474 | CORE 83-90 | 44 |  |  |  | day | 2022-10-01 07:00 | 2022-11-04 17:00 | [12 empty] | 0 | 6 | kdFe2Vl0jEW+ptj1zJUnRw | 2EqH7Hg9r0+1Tsy8atV50g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.6.2 | 41906857 | 41905474 | CORE 90-96 | 17 |  |  |  | day | 2022-09-29 07:00 | 2022-11-14 17:00 | [12 empty] | 1 | 6 | YzB8ASPM2km621pNTswXBw | 2EqH7Hg9r0+1Tsy8atV50g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.6.3 | 41906856 | 41905474 | CORE 96-109 | 37 |  |  |  | day | 2022-11-15 07:00 | 2022-12-17 17:00 | [12 empty] | 2 | 6 | MJlOmlWrAU+YHVsLmhLO/Q | 2EqH7Hg9r0+1Tsy8atV50g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7 | 41905475 | 41904253 | CORE 109-Lvl 36 | 34 |  |  |  | day | 2022-12-19 07:00 | 2023-08-28 17:00 | [12 empty] | 6 | 5 | XsT8oLRC20OwaApUYzP23w | sZchiSLlkUSGEhHuiFwXFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.1 | 41905496 | 41905475 | Core 109 - Level 13 | 14 |  |  |  | day | [14 empty] | 0 | 6 | 2XCUk1q7EEiftRB/LAvqdA | XsT8oLRC20OwaApUYzP23w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2 | 41905586 | 41905475 | Core -09-19 |  |  |  |  | day | 2022-12-19 07:00 | 2023-04-24 17:00 | [12 empty] | 1 | 6 | Cbe5MBTvFEOAXFeok5rjZg | XsT8oLRC20OwaApUYzP23w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2.1 | 41905635 | 41905586 | Core - 09 | 36 |  |  |  | day | 2022-12-19 07:00 | 2023-01-06 17:00 | [12 empty] | 0 | 7 | Lokmv4rZDkqCYiVuWiiIhA | Cbe5MBTvFEOAXFeok5rjZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2.2 | 41904935 | 41905586 | Core -10 | 27 |  |  |  | day | 2023-01-09 07:00 | 2023-03-13 17:00 | [12 empty] | 1 | 7 | 50rHyIOto0+zs7iZ1BmfGQ | Cbe5MBTvFEOAXFeok5rjZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2.3 | 41904937 | 41905586 | Core -11 | 9 |  |  |  | day | 2023-01-27 07:00 | 2023-02-08 17:00 | [12 empty] | 2 | 7 | 8rk0pe5kcky6muuqWEMe+A | Cbe5MBTvFEOAXFeok5rjZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2.4 | 41904939 | 41905586 | Core - 12 |  |  |  |  | day | 2023-02-09 07:00 | 2023-02-17 17:00 | [12 empty] | 3 | 7 | 3s/qzBRH6U2DdP3vMPy9yA | Cbe5MBTvFEOAXFeok5rjZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2.5 | 41904941 | 41905586 | Core -13 | 16 |  |  |  | day | 2023-02-21 07:00 | 2023-03-02 17:00 | [12 empty] | 4 | 7 | Vkc6lGq3lUOzHNWnZZ7E5Q | Cbe5MBTvFEOAXFeok5rjZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2.6 | 41904943 | 41905586 | Core -14 |  |  |  |  | day | 2023-03-03 07:00 | 2023-03-09 17:00 | [12 empty] | 5 | 7 | wiqt2fjXQUqhFl6EQEpjzA | Cbe5MBTvFEOAXFeok5rjZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2.7 | 41904945 | 41905586 | Core -15 | 21 |  |  |  | day | 2023-03-10 07:00 | 2023-03-17 17:00 | [12 empty] | 6 | 7 | dAdiIQ+Fx06FPQ7ngoTSyw | Cbe5MBTvFEOAXFeok5rjZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2.8 | 41904947 | 41905586 | Core -16 | 25 |  |  |  | day | 2023-03-20 07:00 | 2023-03-24 17:00 | [12 empty] | 7 | 7 | r1/X6QGqgU+pEXwNODKe0w | Cbe5MBTvFEOAXFeok5rjZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2.9 | 41904949 | 41905586 | Core -17 |  |  |  |  | day | 2023-03-27 07:00 | 2023-04-03 17:00 | [12 empty] | 8 | 7 | eTIRJ7Cj5Ei/nZW4aTX7UA | Cbe5MBTvFEOAXFeok5rjZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2.10 | 41904951 | 41905586 | Core -18 | 24 |  |  |  | day | 2023-04-03 07:00 | 2023-04-14 17:00 | [12 empty] | 9 | 7 | WaaqIhLIrE6BUu9n86XIXA | Cbe5MBTvFEOAXFeok5rjZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.2.11 | 41904953 | 41905586 | Core -19 |  |  |  |  | day | 2023-04-18 07:00 | 2023-04-24 17:00 | [12 empty] | 10 | 7 | q9Yqkr/DVkCfcf3Th0MK2A | Cbe5MBTvFEOAXFeok5rjZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.3 | 41905587 | 41905475 | Core -20-29 | 12 |  |  |  | day | 2023-04-25 07:00 | 2023-06-13 17:00 | [12 empty] | 2 | 6 | bvGxymMOWUqywIGnXzI+Lw | XsT8oLRC20OwaApUYzP23w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.3.1 | 41904955 | 41905587 | Core -20 |  |  |  |  | day | 2023-04-25 07:00 | 2023-05-01 17:00 | [12 empty] | 0 | 7 | TQT2FEhZoE2NY/De+S1Hdw | bvGxymMOWUqywIGnXzI+Lw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.3.2 | 41904957 | 41905587 | Core -21 | 24 |  |  |  | day | 2023-05-02 07:00 | 2023-05-05 17:00 | [12 empty] | 1 | 7 | gURctJBsj0e697i5MXn73Q | bvGxymMOWUqywIGnXzI+Lw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.3.3 | 41904959 | 41905587 | Core -22 | 3 |  |  |  | day | 2023-05-08 07:00 | 2023-05-11 17:00 | [12 empty] | 2 | 7 | 3eJVn38xHUOMXCvu0KcKNQ | bvGxymMOWUqywIGnXzI+Lw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.3.4 | 41904961 | 41905587 | Core -23 | 9 |  |  |  | day | 2023-05-12 07:00 | 2023-05-17 17:00 | [12 empty] | 3 | 7 | 7uXk4nocEU6v8t5GgxelPw | bvGxymMOWUqywIGnXzI+Lw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.3.5 | 41904963 | 41905587 | Core -24 | 2 |  |  |  | day | 2023-05-18 07:00 | 2023-05-22 17:00 | [12 empty] | 4 | 7 | aOWqc8g5tECGzT5DN1+VWQ | bvGxymMOWUqywIGnXzI+Lw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.3.6 | 41904965 | 41905587 | Core -25 |  |  |  |  | day | 2023-05-23 07:00 | 2023-05-25 17:00 | [12 empty] | 5 | 7 | SMLYGpHXXUSckzjSDMLXJg | bvGxymMOWUqywIGnXzI+Lw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.3.7 | 41904967 | 41905587 | Core -26 | 44 |  |  |  | day | 2023-05-26 07:00 | 2023-05-31 17:00 | [12 empty] | 6 | 7 | vXpfTtkEAkSLLxqZmwpsoA | bvGxymMOWUqywIGnXzI+Lw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.3.8 | 41904969 | 41905587 | Core -27 | 17 |  |  |  | day | 2023-06-01 07:00 | 2023-06-05 17:00 | [12 empty] | 7 | 7 | JVVCttHXM0Kt5U+our41XQ | bvGxymMOWUqywIGnXzI+Lw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.3.9 | 41904971 | 41905587 | Core -28 | 46 |  |  |  | day | 2023-06-06 07:00 | 2023-06-08 17:00 | [12 empty] | 8 | 7 | oPAWN7On1kmaHl71dm4TFA | bvGxymMOWUqywIGnXzI+Lw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.3.10 | 41904973 | 41905587 | Core -29 | 35 |  |  |  | day | 2023-06-09 07:00 | 2023-06-13 17:00 | [12 empty] | 9 | 7 | czR4DV//2kahnXXtX7dLXg | bvGxymMOWUqywIGnXzI+Lw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.4 | 41905588 | 41905475 | Core -30-35 | 46 |  |  |  | day | 2023-06-14 07:00 | 2023-08-28 17:00 | [12 empty] | 3 | 6 | n+vPvLIP3U641UcMnVOEqQ | XsT8oLRC20OwaApUYzP23w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.4.1 | 41904975 | 41905588 | Core -30 | 21 |  |  |  | day | 2023-06-14 07:00 | 2023-06-16 17:00 | [12 empty] | 0 | 7 | ce1hW0Bo6U6CTlBhl519RQ | n+vPvLIP3U641UcMnVOEqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.4.2 | 41904977 | 41905588 | Core -31 | 33 |  |  |  | day | 2023-06-19 07:00 | 2023-06-21 17:00 | [12 empty] | 1 | 7 | zmU8CaWjNkGNbaFbL7HucA | n+vPvLIP3U641UcMnVOEqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.4.3 | 41904979 | 41905588 | Core -32 |  |  |  |  | day | 2023-06-22 07:00 | 2023-06-26 17:00 | [12 empty] | 2 | 7 | RkYittybakO1K0ClmcVt9Q | n+vPvLIP3U641UcMnVOEqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.4.4 | 41904981 | 41905588 | Core -33 | 7 |  |  |  | day | 2023-06-27 07:00 | 2023-06-29 17:00 | [12 empty] | 3 | 7 | CwXODY4tl0OWqKYbKL5S7g | n+vPvLIP3U641UcMnVOEqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.4.5 | 41904983 | 41905588 | Core -34 |  |  |  |  | day | 2023-06-30 07:00 | 2023-07-26 17:00 | [12 empty] | 4 | 7 | G4hm3V8UKk2Qcq8h1SEoqQ | n+vPvLIP3U641UcMnVOEqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.7.4.6 | 41904985 | 41905588 | Core -35 | 48 |  |  |  | day | 2023-07-26 07:00 | 2023-08-28 17:00 | [12 empty] | 5 | 7 | cUY3W7z3kk6a6EaQprOmgA | n+vPvLIP3U641UcMnVOEqQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8 | 41905476 | 41904253 | STEEL 83-Lvl 36 |  |  |  |  | day | 2023-01-03 07:00 | 2024-03-05 17:00 | [12 empty] | 7 | 5 | Zqc7C2i85EqlWHloce3sEg | sZchiSLlkUSGEhHuiFwXFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1 | 41905528 | 41905476 | 83-109 | 18 |  |  |  | day | 2023-01-03 07:00 | 2023-05-26 17:00 | [12 empty] | 0 | 6 | QMlEQQgfVESBQfuinyWLOg | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.1 | 41905477 | 41905528 | T3-T6 - East Core West |  |  |  |  | day | 2023-01-03 07:00 | 2023-05-04 17:00 | [12 empty] | 0 | 7 | x3WL0KuYukOREJJpfhz9UQ | QMlEQQgfVESBQfuinyWLOg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.1.1 | 41907013 | 41905477 | 83 | 40 |  |  |  | day | 2023-01-11 07:00 | 2023-04-23 17:00 | [12 empty] | 0 | 8 | jjl2aA53w0+UpyaNK7VCzg | x3WL0KuYukOREJJpfhz9UQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.1.1.1 | 41907016 | 41907013 | Erect | 36 |  |  |  | day | 2023-01-11 07:00 | 2023-04-18 17:00 | [12 empty] | 0 | 9 | 5pnZjPnFmUizFzQqBUeFdw | jjl2aA53w0+UpyaNK7VCzg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.1.1.2 | 41907019 | 41907013 | Detail | 5 |  |  |  | day | 2023-01-16 07:00 | 2023-04-23 17:00 | [12 empty] | 1 | 9 | j9mqarwuL0+L6M2hPuObww | jjl2aA53w0+UpyaNK7VCzg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.1.2 | 41907014 | 41905477 | 96 - | 25 |  |  |  | day | 2023-01-13 07:00 | 2023-03-31 17:00 | [12 empty] | 1 | 8 | YBFi+b1BjESXrDDilinQ8Q | x3WL0KuYukOREJJpfhz9UQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.1.2.1 | 41907017 | 41907014 | Erect | 33 |  |  |  | day | 2023-01-13 07:00 | 2023-03-09 17:00 | [12 empty] | 0 | 9 | EuvhV0gR1ky98ECX4j4z1w | YBFi+b1BjESXrDDilinQ8Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.1.2.2 | 41907020 | 41907014 | Detail | 44 |  |  |  | day | 2023-01-30 07:00 | 2023-03-31 17:00 | [12 empty] | 1 | 9 | QKnAflMfJkC+mdJrCPhC0A | YBFi+b1BjESXrDDilinQ8Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.1.3 | 41907015 | 41905477 | 109 |  |  |  |  | day | 2023-02-15 07:00 | 2023-05-01 17:00 | [12 empty] | 2 | 8 | UFTC7RnCBk+TXTNresLR7g | x3WL0KuYukOREJJpfhz9UQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.1.3.1 | 41907018 | 41907015 | Erect | 36 |  |  |  | day | 2023-02-15 07:00 | 2023-04-13 17:00 | [12 empty] | 0 | 9 | ISSHk4VCt0ajcxmCs8x9gQ | UFTC7RnCBk+TXTNresLR7g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.1.3.2 | 41907021 | 41907015 | Detail |  |  |  |  | day | 2023-04-12 07:00 | 2023-05-01 17:00 | [12 empty] | 1 | 9 | Yi/Rp4T9ZEqbQWLLXIDkug | UFTC7RnCBk+TXTNresLR7g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.2 | 41905478 | 41905528 | T1-T3 and T6-T9 - North South |  |  |  |  | day | 2023-03-14 07:00 | 2023-05-26 17:00 | [12 empty] | 1 | 7 | JYJ/h7voIk6Tg2uU1MqCaQ | QMlEQQgfVESBQfuinyWLOg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.3 | 41905529 | 41905528 | 109 | 20 |  |  |  | day | [14 empty] | 2 | 7 | tkmGWR3g6EGol0AgbPyitQ | QMlEQQgfVESBQfuinyWLOg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.3.1 | 41905530 | 41905529 | T3-T6 - East Core West | 5 |  |  |  | day | [14 empty] | 0 | 8 | Lt0jaOQMk0Shb8Qq1V+XkQ | tkmGWR3g6EGol0AgbPyitQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.1.3.2 | 41905541 | 41905529 | T1-T3 and T6-T9 - North South | 5 |  |  |  | day | [14 empty] | 1 | 8 | SwyogAHx30epsL6g0SAqtA | tkmGWR3g6EGol0AgbPyitQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.2 | 41905479 | 41905476 | Level 10 | 47 |  |  |  | day | 2023-02-13 07:00 | 2024-03-05 17:00 | [12 empty] | 1 | 6 | QtzmCbJ85E294c82Zo5zxw | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.2.1 | 41905531 | 41905479 | T3-T6 - Core | 3 |  |  |  | day | 2023-02-13 07:00 | 2023-05-01 17:00 | [12 empty] | 0 | 7 | Eckqa/9x8kWcLmTCw6WLtg | QtzmCbJ85E294c82Zo5zxw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.2.2 | 41905542 | 41905479 | T1-T3 and T6-T9 | 29 |  |  |  | day | 2023-04-27 07:00 | 2023-06-09 17:00 | [12 empty] | 1 | 7 | ozoyz3kovUO1PvmNwpXrvA | QtzmCbJ85E294c82Zo5zxw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.2.3 | 41907012 | 41905479 | COR170 | 10 |  |  |  | day | 2023-12-26 07:00 | 2024-03-05 17:00 | [12 empty] | 2 | 7 | 5179eTewyE6D/NQlI+pmNg | QtzmCbJ85E294c82Zo5zxw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.3 | 41905480 | 41905476 | Level 11 |  |  |  |  | day | 2023-02-24 07:00 | 2023-06-16 17:00 | [12 empty] | 2 | 6 | ntKKX+h11Eu9B6iCEnxhbA | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.3.1 | 41905532 | 41905480 | T3-T6 - Core | 30 |  |  |  | day | 2023-02-24 07:00 | 2023-05-04 17:00 | [12 empty] | 0 | 7 | UyQU7mSIHUKLl+6/znNBOg | ntKKX+h11Eu9B6iCEnxhbA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.3.2 | 41905543 | 41905480 | T1-T3 and T6-T9 - North South | 23 |  |  |  | day | 2023-04-29 07:00 | 2023-06-16 17:00 | [12 empty] | 1 | 7 | Fgo0Z2bs9UqSgxYh0vbEOA | ntKKX+h11Eu9B6iCEnxhbA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.4 | 41905481 | 41905476 | Level 12-13 | 8 |  |  |  | day | 2023-03-13 07:00 | 2023-07-11 17:00 | [12 empty] | 3 | 6 | IHJeKKVFh0mXVleFkVoZCQ | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.4.1 | 41905533 | 41905481 | 12 - T3-T6 - Core | 2 |  |  |  | day | 2023-03-13 07:00 | 2023-05-10 17:00 | [12 empty] | 0 | 7 | MFsSYVsS+E+7O7O1xj+nEw | IHJeKKVFh0mXVleFkVoZCQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.4.2 | 41905544 | 41905481 | 12 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-05-09 07:00 | 2023-06-28 17:00 | [12 empty] | 1 | 7 | 1HXy1/q2aEmFDU7iPg0ZFw | IHJeKKVFh0mXVleFkVoZCQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.4.3 | 41905534 | 41905481 | 13 - T3-T6 - Core | 39 |  |  |  | day | 2023-03-13 07:00 | 2023-05-17 17:00 | [12 empty] | 2 | 7 | YaYbCqff7kCZsVcoElz7dw | IHJeKKVFh0mXVleFkVoZCQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.4.4 | 41905545 | 41905481 | 13 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-05-16 07:00 | 2023-07-11 17:00 | [12 empty] | 3 | 7 | VGhG+wfdkUCkzOMjmWf6Eg | IHJeKKVFh0mXVleFkVoZCQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.5 | 41905482 | 41905476 | Level 14-15 |  |  |  |  | day | 2023-03-20 07:00 | 2023-07-18 17:00 | [12 empty] | 4 | 6 | XH60yDOYE0We9/I2D3FBug | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.5.1 | 41905535 | 41905482 | 14 - T3-T6 - Core | 23 |  |  |  | day | 2023-03-20 07:00 | 2023-05-25 17:00 | [12 empty] | 0 | 7 | FGYv08M09UOrEVqTebEeKg | XH60yDOYE0We9/I2D3FBug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.5.2 | 41905546 | 41905482 | 14 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-06-07 07:00 | 2023-07-13 17:00 | [12 empty] | 1 | 7 | RNRwxwS880a6WkSSWpCi7A | XH60yDOYE0We9/I2D3FBug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.5.3 | 41905536 | 41905482 | 15 - T3-T6 - Core | 5 |  |  |  | day | 2023-03-20 07:00 | 2023-05-31 17:00 | [12 empty] | 2 | 7 | 8H0DdYWjdkmH2hVGVTlMXA | XH60yDOYE0We9/I2D3FBug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.5.4 | 41905547 | 41905482 | 15 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-06-09 07:00 | 2023-07-18 17:00 | [12 empty] | 3 | 7 | EzSorjrhGU6sD4Bt6auNpg | XH60yDOYE0We9/I2D3FBug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.6 | 41905483 | 41905476 | Level 16-17 | 19 |  |  |  | day | 2023-03-29 07:00 | 2023-07-26 17:00 | [12 empty] | 5 | 6 | SlyUcptNr0eFfgq5S/xVZw | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.6.1 | 41905537 | 41905483 | 16 - T3-T6- Core |  |  |  |  | day | 2023-03-29 07:00 | 2023-06-16 17:00 | [12 empty] | 0 | 7 | jq6N3sDeKEmAT0dJuUZOTw | SlyUcptNr0eFfgq5S/xVZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.6.2 | 41905548 | 41905483 | 16 - T1-T3 and T6-T9 | 10 |  |  |  | day | 2023-06-16 07:00 | 2023-07-24 17:00 | [12 empty] | 1 | 7 | Aycge8KCtEylTeOKpt4XvA | SlyUcptNr0eFfgq5S/xVZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.6.3 | 41905538 | 41905483 | 17 - T3-T6- Core |  |  |  |  | day | 2023-04-13 07:00 | 2023-06-28 17:00 | [12 empty] | 2 | 7 | 33FbruEum02nVTrFjjY+TQ | SlyUcptNr0eFfgq5S/xVZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.6.4 | 41905549 | 41905483 | 17 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-06-22 07:00 | 2023-07-26 17:00 | [12 empty] | 3 | 7 | 8OGWigg10EeNqwUIwYOqlQ | SlyUcptNr0eFfgq5S/xVZw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.7 | 41905484 | 41905476 | Level 18-19- |  |  |  |  | day | 2023-04-19 07:00 | 2023-08-05 17:00 | [12 empty] | 6 | 6 | M54AzdQZlkSdBoVVxtr7+Q | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.7.1 | 41905539 | 41905484 | 18 - T3-T6 - Core |  |  |  |  | day | 2023-04-19 07:00 | 2023-07-18 17:00 | [12 empty] | 0 | 7 | DkPX8HSJkk2tOUjZjxDSQw | M54AzdQZlkSdBoVVxtr7+Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.7.2 | 41905550 | 41905484 | 18 - T1-T3 and T6-T9 | 29 |  |  |  | day | 2023-06-26 07:00 | 2023-07-31 17:00 | [12 empty] | 1 | 7 | vD+pnXGu5EOyMnnxC9Y9kQ | M54AzdQZlkSdBoVVxtr7+Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.7.3 | 41905540 | 41905484 | 19 - T3-T6 - Core | 37 |  |  |  | day | 2023-05-02 07:00 | 2023-07-24 17:00 | [12 empty] | 2 | 7 | oQXssHE4DUq3MVNpCZHORg | M54AzdQZlkSdBoVVxtr7+Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.7.4 | 41905551 | 41905484 | 19 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-06-30 07:00 | 2023-08-05 17:00 | [12 empty] | 3 | 7 | hYoAQdjU9EqaLrOeGywedg | M54AzdQZlkSdBoVVxtr7+Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.8 | 41905485 | 41905476 | Level 20-21- | 14 |  |  |  | day | 2023-05-08 07:00 | 2023-08-18 17:00 | [12 empty] | 7 | 6 | LDHE0LtJeEC1Or32D4OWUA | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.8.1 | 41905552 | 41905485 | 20 - T3-T6 - Core | 10 |  |  |  | day | 2023-05-08 07:00 | 2023-07-26 17:00 | [12 empty] | 0 | 7 | aRGBrqsFrkWK/bPCi5mkqg | LDHE0LtJeEC1Or32D4OWUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.8.2 | 41905553 | 41905485 | 20 - T1-T3 and T6-T9 | 7 |  |  |  | day | 2023-07-12 07:00 | 2023-08-11 17:00 | [12 empty] | 1 | 7 | 6QNQI6/GrECUnlN1k70jFg | LDHE0LtJeEC1Or32D4OWUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.8.3 | 41905554 | 41905485 | 21 - T3-T6 - Core | 25 |  |  |  | day | 2023-05-12 07:00 | 2023-07-31 17:00 | [12 empty] | 2 | 7 | a9TaQy4jEUmvKRy/UI7pdg | LDHE0LtJeEC1Or32D4OWUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.8.4 | 41905555 | 41905485 | 21 - T1-T3 and T6-T9 | 44 |  |  |  | day | 2023-07-18 07:00 | 2023-08-18 17:00 | [12 empty] | 3 | 7 | wnZqdVWieE+8+9ssXX+dSg | LDHE0LtJeEC1Or32D4OWUA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.9 | 41905486 | 41905476 | Level 22-23 |  |  |  |  | day | 2023-05-16 07:00 | 2023-08-31 17:00 | [12 empty] | 8 | 6 | zry15S2dpEaOSqUJ1sDT2w | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.9.1 | 41905556 | 41905486 | 22 - T3-T6 - Core | 4 |  |  |  | day | 2023-05-16 07:00 | 2023-08-07 17:00 | [12 empty] | 0 | 7 |  | zry15S2dpEaOSqUJ1sDT2w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.9.2 | 41905557 | 41905486 | 22 - T1-T3 and T6-T9 | 5 |  |  |  | day | 2023-07-24 07:00 | 2023-08-28 17:00 | [12 empty] | 1 | 7 | PWJEkc6qyUuqWvvgVVzNww | zry15S2dpEaOSqUJ1sDT2w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.9.3 | 41905558 | 41905486 | 23 - T3-T6 - Core | 25 |  |  |  | day | 2023-05-18 07:00 | 2023-08-14 17:00 | [12 empty] | 2 | 7 | 9u3VV9owmkKRhX7t2SIAKA | zry15S2dpEaOSqUJ1sDT2w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.9.4 | 41905559 | 41905486 | 23 - T1-T3 and T6-T9 | 3 |  |  |  | day | 2023-07-28 07:00 | 2023-08-31 17:00 | [12 empty] | 3 | 7 | 6GbZrU93xk2V48SCvOLlvQ | zry15S2dpEaOSqUJ1sDT2w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.10 | 41905487 | 41905476 | Level 24-25 | 18 |  |  |  | day | 2023-05-26 07:00 | 2023-09-14 17:00 | [12 empty] | 9 | 6 | Afewdm+pMkafUZBgYCzilg | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.10.1 | 41905560 | 41905487 | 24 - T3-T6 - Core |  |  |  |  | day | 2023-05-26 07:00 | 2023-08-29 17:00 | [12 empty] | 0 | 7 | 17W0iBjqlEqPorx8aibd0w | Afewdm+pMkafUZBgYCzilg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.10.2 | 41905561 | 41905487 | 24 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-08-08 07:00 | 2023-09-08 17:00 | [12 empty] | 1 | 7 | q34B9F7OPEGRTz8o51aZrw | Afewdm+pMkafUZBgYCzilg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.10.3 | 41905562 | 41905487 | 25 - T3-T6 - Core |  |  |  |  | day | 2023-06-01 07:00 | 2023-09-14 17:00 | [12 empty] | 2 | 7 | IUE+RlfxKUi8Nvbf8hBMmw | Afewdm+pMkafUZBgYCzilg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.10.4 | 41905563 | 41905487 | 25 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-08-11 07:00 | 2023-09-14 17:00 | [12 empty] | 3 | 7 | mTtbp2z+yk+vDJn/Euo0Ag | Afewdm+pMkafUZBgYCzilg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.11 | 41905488 | 41905476 | Level 26-27 | 11 |  |  |  | day | 2023-06-06 07:00 | 2023-09-29 17:00 | [12 empty] | 10 | 6 | EBPQP0710Ei2erbWojhjoA | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.11.1 | 41905564 | 41905488 | 26 - T3-T6 - Core | 46 |  |  |  | day | 2023-06-06 07:00 | 2023-09-21 17:00 | [12 empty] | 0 | 7 | DPQO/mYg6kWvQcu9MYH0wQ | EBPQP0710Ei2erbWojhjoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.11.2 | 41905565 | 41905488 | 26 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-08-18 07:00 | 2023-09-25 17:00 | [12 empty] | 1 | 7 | Ooc7hLaAU0u5QorrbTUHBQ | EBPQP0710Ei2erbWojhjoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.11.3 | 41905566 | 41905488 | 27 - T3-T6 - Core |  |  |  |  | day | 2023-06-09 07:00 | 2023-09-28 17:00 | [12 empty] | 2 | 7 | vC+xcwGBYk6PzpAeLRMOkw | EBPQP0710Ei2erbWojhjoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.11.4 | 41905567 | 41905488 | 27 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-08-29 07:00 | 2023-09-29 17:00 | [12 empty] | 3 | 7 | FlzI5S0eKU2P4OYgYOm3eQ | EBPQP0710Ei2erbWojhjoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.12 | 41905489 | 41905476 | Level 28-29 | 37 |  |  |  | day | 2023-06-14 07:00 | 2023-10-13 17:00 | [12 empty] | 11 | 6 | lkeZZ+ifHUK5aMV7aZ+t2A | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.12.1 | 41905568 | 41905489 | 28 - T3-T6 - Core | 36 |  |  |  | day | 2023-06-14 07:00 | 2023-10-04 17:00 | [12 empty] | 0 | 7 | siTGsCxZoEmTwwkyASmx5Q | lkeZZ+ifHUK5aMV7aZ+t2A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.12.2 | 41905569 | 41905489 | 28 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-09-13 07:00 | 2023-10-06 17:00 | [12 empty] | 1 | 7 | toqMg9seHUSn+qPqNT3fzg | lkeZZ+ifHUK5aMV7aZ+t2A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.12.3 | 41905570 | 41905489 | 29 - T3-T6 - Core |  |  |  |  | day | 2023-06-19 07:00 | 2023-10-10 17:00 | [12 empty] | 2 | 7 | D3z42WUKHUCLNED7AUUl6g | lkeZZ+ifHUK5aMV7aZ+t2A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.12.4 | 41905571 | 41905489 | 29 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-09-20 07:00 | 2023-10-13 17:00 | [12 empty] | 3 | 7 | kiVZcpX8Tk2p45NNsv7Xag | lkeZZ+ifHUK5aMV7aZ+t2A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.13 | 41905490 | 41905476 | Level 30-31 | 42 |  |  |  | day | 2023-06-23 07:00 | 2023-10-27 17:00 | [12 empty] | 12 | 6 | Os0I8P+0xkOj6DCzYZ4v8A | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.13.1 | 41905572 | 41905490 | 30 - T3-T6 - Core |  |  |  |  | day | 2023-06-23 07:00 | 2023-10-20 17:00 | [12 empty] | 0 | 7 | A7DMs83TpUuxDA/e9x92Mg | Os0I8P+0xkOj6DCzYZ4v8A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.13.2 | 41905573 | 41905490 | 30 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-09-26 07:00 | 2023-10-20 17:00 | [12 empty] | 1 | 7 | 8pEwTw7YS0uMl7Qpmx8qpQ | Os0I8P+0xkOj6DCzYZ4v8A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.13.3 | 41905574 | 41905490 | 31 - T3-T6 - Core | 5 |  |  |  | day | 2023-06-28 07:00 | 2023-10-27 17:00 | [12 empty] | 2 | 7 | mZFDqMieJE++ncFDkvi52A | Os0I8P+0xkOj6DCzYZ4v8A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.13.4 | 41905575 | 41905490 | 31 - T1-T3 and T6-T9 | 49 |  |  |  | day | 2023-10-03 07:00 | 2023-10-27 17:00 | [12 empty] | 3 | 7 | s6Wzgq9TvUeBEtR5vW9k5A | Os0I8P+0xkOj6DCzYZ4v8A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.14 | 41905491 | 41905476 | Level 32-33 |  |  |  |  | day | 2023-06-30 07:00 | 2023-11-13 17:00 | [12 empty] | 13 | 6 | cdvP8xTg9EmfW0xecrYndw | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.14.1 | 41905576 | 41905491 | 32 - T3-T6 - Core | 4 |  |  |  | day | 2023-06-30 07:00 | 2023-10-11 17:00 | [12 empty] | 0 | 7 | n2CYC8BhaU2moJh3Rwl2Vg | cdvP8xTg9EmfW0xecrYndw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.14.2 | 41905577 | 41905491 | 32 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-10-04 07:00 | 2023-11-06 17:00 | [12 empty] | 1 | 7 | /I8q0u2n+EiOjYtLGcX6yA | cdvP8xTg9EmfW0xecrYndw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.14.3 | 41905578 | 41905491 | 33 - T3-T6 - Core |  |  |  |  | day | 2023-07-06 07:00 | 2023-11-13 17:00 | [12 empty] | 2 | 7 | TZnZHr8oI0CUt7q5c/IXcg | cdvP8xTg9EmfW0xecrYndw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.14.4 | 41905579 | 41905491 | 33 - T1-T3 and T6-T9 | 43 |  |  |  | day | 2023-10-11 07:00 | 2023-10-20 17:00 | [12 empty] | 3 | 7 | mH4Jwr5RD0e/RexTqmWinA | cdvP8xTg9EmfW0xecrYndw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.15 | 41905492 | 41905476 | Level 34-36 |  |  |  |  | day | 2023-07-11 07:00 | 2023-11-28 17:00 | [12 empty] | 14 | 6 | kWqE+ZpLoEinqcAQH0uf/A | Zqc7C2i85EqlWHloce3sEg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.15.1 | 41905580 | 41905492 | 34 - T3-T6 - Core | 12 |  |  |  | day | 2023-07-11 07:00 | 2023-10-18 17:00 | [12 empty] | 0 | 7 | VDPR0L3PLUiA9aioZczA2Q | kWqE+ZpLoEinqcAQH0uf/A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.15.2 | 41905581 | 41905492 | 34 - T1-T3 and T6-T9 | 39 |  |  |  | day | 2023-10-23 07:00 | 2023-11-17 17:00 | [12 empty] | 1 | 7 | MPocSpHKaE2iGzK1xF2K7w | kWqE+ZpLoEinqcAQH0uf/A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.15.3 | 41905582 | 41905492 | 35 - T3-T6 - Core |  |  |  |  | day | 2023-08-01 07:00 | 2023-11-27 17:00 | [12 empty] | 2 | 7 | mWCYkYz+X06r/FpeQv8Q3w | kWqE+ZpLoEinqcAQH0uf/A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.15.4 | 41905583 | 41905492 | 35 - T1-T3 and T6-T9 | 19 |  |  |  | day | [14 empty] | 3 | 7 | YH3Gl6SnHEW5bpYvbCIDwQ | kWqE+ZpLoEinqcAQH0uf/A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.15.5 | 41905584 | 41905492 | 36 - T3-T6 - Core |  |  |  |  | day | [14 empty] | 4 | 7 | AJkfGiSLTUqkxaqAEAm7Tg | kWqE+ZpLoEinqcAQH0uf/A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.8.15.6 | 41905585 | 41905492 | 35/36 - T1-T3 and T6-T9 |  |  |  |  | day | 2023-10-27 07:00 | 2023-11-28 17:00 | [12 empty] | 5 | 7 | 2Np6EQkN8067nTodzDxHzQ | kWqE+ZpLoEinqcAQH0uf/A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9 | 41904469 | 41904253 | SOMDs Office Structure - Lvl 10 (El +122') to Lvl 36 (El +469') |  |  |  |  | day | 2023-02-10 07:00 | 2024-02-21 17:00 | [12 empty] | 8 | 5 | Mz/uQ1Ln1kKm6mNNqi7fcA | sZchiSLlkUSGEhHuiFwXFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.1 | 41905593 | 41904469 | Office Lvl Mech - Elev 83 | 16 |  |  |  | day | 2023-02-10 07:00 | 2023-08-04 17:00 | [12 empty] | 0 | 6 | pjqkuIB+jUOk7ARq6JXyMQ | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.1.1 | 41905594 | 41905593 | Decks and Outer Columns |  |  |  |  | day | 2023-02-10 07:00 | 2023-08-04 17:00 | [12 empty] | 0 | 7 | gw+bSsSOf0Kx6xZ9XYibVw | pjqkuIB+jUOk7ARq6JXyMQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.2 | 41905591 | 41904469 | Office Lvl Mezz - Elev 96 | 10 |  |  |  | day | 2023-04-06 07:00 | 2023-09-22 17:00 | [12 empty] | 1 | 6 | FOqK8xXqdEqTYr6bLZjdkg | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.2.1 | 41905592 | 41905591 | Decks and Outer Columns | 14 |  |  |  | day | 2023-04-06 07:00 | 2023-09-22 17:00 | [12 empty] | 0 | 7 | p07MfHN9aE2yalxmF2L04g | FOqK8xXqdEqTYr6bLZjdkg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.3 | 41905589 | 41904469 | Office Lvl 09 - Elev 109 | 23 |  |  |  | day | 2023-07-03 07:00 | 2023-09-18 17:00 | [12 empty] | 2 | 6 | ouROH61nzEWsa8w9pxEnIw | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.3.1 | 41905590 | 41905589 | Decks and Outer Columns | 37 |  |  |  | day | 2023-07-03 07:00 | 2023-09-18 17:00 | [12 empty] | 0 | 7 | BIBsHF31q0iUusiBEERwdg | ouROH61nzEWsa8w9pxEnIw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.4 | 41904553 | 41904469 | Office Lvl 10 - Elev 122- (Deck Pour) |  |  |  |  | day | 2023-09-16 07:00 | 2023-09-25 17:00 | [12 empty] | 3 | 6 | Bku/M2hMGUuiRoXND5yN0g | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.4.1 | 41904936 | 41904553 | Decks and Outer Columns | 29 |  |  |  | day | 2023-09-16 07:00 | 2023-09-25 17:00 | [12 empty] | 0 | 7 | inoMxoltDUW8AtlNoPrINA | Bku/M2hMGUuiRoXND5yN0g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.5 | 41904554 | 41904469 | Office Lvl 11 - (Residential Sky Street)- (Deck Pour) | 30 |  |  |  | day | 2023-09-14 07:00 | 2023-09-26 17:00 | [12 empty] | 4 | 6 | AkTO869YPkej3Y7sWTOV5w | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.5.1 | 41904938 | 41904554 | Decks and Outer Columns | 48 |  |  |  | day | 2023-09-14 07:00 | 2023-09-26 17:00 | [12 empty] | 0 | 7 | 0ZpUsxlWBUy1GqDmLM1MXQ | AkTO869YPkej3Y7sWTOV5w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.6 | 41904555 | 41904469 | Office Lvl 12 - (Deck Pour) | 4 |  |  |  | day | 2023-09-15 07:00 | 2023-09-27 17:00 | [12 empty] | 5 | 6 | dpvpGxGmYk6CBmVrWo/ANQ | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.6.1 | 41904940 | 41904555 | Decks and Outer Columns |  |  |  |  | day | 2023-09-15 07:00 | 2023-09-27 17:00 | [12 empty] | 0 | 7 | OGgaDT4CdECco3RJb5GFrg | dpvpGxGmYk6CBmVrWo/ANQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.7 | 41904556 | 41904469 | Office Lvl 13 - (Deck Pour) | 49 |  |  |  | day | 2023-09-18 07:00 | 2023-09-28 17:00 | [12 empty] | 6 | 6 | bK/XZAe9bkeENzANPsSlfA | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.7.1 | 41904942 | 41904556 | Decks and Outer Columns | 13 |  |  |  | day | 2023-09-18 07:00 | 2023-09-28 17:00 | [12 empty] | 0 | 7 | oi/x76gP+EWqbt7yjFsxvg | bK/XZAe9bkeENzANPsSlfA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.8 | 41904557 | 41904469 | Office Lvl 14 - (Deck Pour) |  |  |  |  | day | 2023-09-20 07:00 | 2023-09-29 17:00 | [12 empty] | 7 | 6 | SOXstiq7KEaVwgXWwMl2rw | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.8.1 | 41904944 | 41904557 | Decks and Outer Columns | 8 |  |  |  | day | 2023-09-20 07:00 | 2023-09-29 17:00 | [12 empty] | 0 | 7 | iX7QWJLmQ0uc6S9KvgabbQ | SOXstiq7KEaVwgXWwMl2rw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.9 | 41904558 | 41904469 | Office Lvl 15 - (Deck Pour) |  |  |  |  | day | 2023-09-21 07:00 | 2023-10-02 17:00 | [12 empty] | 8 | 6 | T+VJNntHIkmO6QtOzvDr6A | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.9.1 | 41904946 | 41904558 | Decks and Outer Columns | 11 |  |  |  | day | 2023-09-21 07:00 | 2023-10-02 17:00 | [12 empty] | 0 | 7 | oj3UWzdlf0yIIcGpI4qX5g | T+VJNntHIkmO6QtOzvDr6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.10 | 41904559 | 41904469 | Office Lvl 16 | 34 |  |  |  | day | 2023-09-22 07:00 | 2023-10-05 17:00 | [12 empty] | 9 | 6 | dOuQMxOo1keelPMfryJs3Q | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.10.1 | 41904948 | 41904559 | Decks and Outer Columns | 34 |  |  |  | day | 2023-09-22 07:00 | 2023-10-05 17:00 | [12 empty] | 0 | 7 | LzmefILZDE2PhhrW43W2lg | dOuQMxOo1keelPMfryJs3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.11 | 41904560 | 41904469 | Office Lvl 17 | 0 |  |  |  | day | 2023-10-03 07:00 | 2023-10-13 17:00 | [12 empty] | 10 | 6 | b33neShBvkSeSNn6s+m54g | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.11.1 | 41904950 | 41904560 | Decks and Outer Columns | 39 |  |  |  | day | 2023-10-03 07:00 | 2023-10-13 17:00 | [12 empty] | 0 | 7 | F+8UOhh8Y0WXxtRBNYEKxw | b33neShBvkSeSNn6s+m54g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.12 | 41904561 | 41904469 | Office Lvl 18 | 21 |  |  |  | day | 2023-10-04 07:00 | 2023-10-16 17:00 | [12 empty] | 11 | 6 | 7USJ6h71KU2H6Jwb19t3Cw | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.12.1 | 41904952 | 41904561 | Decks and Outer Columns | 28 |  |  |  | day | 2023-10-04 07:00 | 2023-10-16 17:00 | [12 empty] | 0 | 7 | FOVdlRtAGUqYbXusNl4spw | 7USJ6h71KU2H6Jwb19t3Cw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.13 | 41904562 | 41904469 | Office Lvl 19 Structural Steel & Truss Triangle | 7 |  |  |  | day | 2023-08-07 07:00 | 2023-10-17 17:00 | [12 empty] | 12 | 6 | zrMkQkZrNk+JoKDgFycncQ | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.13.1 | 41904954 | 41904562 | Decks and Outer Columns | 10 |  |  |  | day | 2023-08-07 07:00 | 2023-10-17 17:00 | [12 empty] | 0 | 7 | yervt+hgOEGnXXzrQzlUtA | zrMkQkZrNk+JoKDgFycncQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.14 | 41904563 | 41904469 | Office Lvl 20 |  |  |  |  | day | 2023-10-05 07:00 | 2023-10-19 17:00 | [12 empty] | 13 | 6 | 9lYwwXGstEmbH7ina4YcWA | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.14.1 | 41904956 | 41904563 | Decks and Outer Columns | 36 |  |  |  | day | 2023-10-05 07:00 | 2023-10-19 17:00 | [12 empty] | 0 | 7 | 1H2K6DJh/EqnF13YoDjDvQ | 9lYwwXGstEmbH7ina4YcWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.15 | 41904564 | 41904469 | Office Lvl 21 | 13 |  |  |  | day | 2023-10-10 07:00 | 2023-10-23 17:00 | [12 empty] | 14 | 6 | b3q+GnXpr0eWVlzMPn+JXw | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.15.1 | 41904958 | 41904564 | Decks and Outer Columns | 29 |  |  |  | day | 2023-10-10 07:00 | 2023-10-23 17:00 | [12 empty] | 0 | 7 | JZz3gb5MdESvyGdrKtsW3Q | b3q+GnXpr0eWVlzMPn+JXw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.16 | 41904565 | 41904469 | Office Lvl 22 |  |  |  |  | day | 2023-10-12 07:00 | 2023-10-24 17:00 | [12 empty] | 15 | 6 | Mjk7NcQbcE2UcEodaVaaVw | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.16.1 | 41904960 | 41904565 | Decks and Outer Columns | 20 |  |  |  | day | 2023-10-12 07:00 | 2023-10-24 17:00 | [12 empty] | 0 | 7 | IlLKYauVXEiTIn823tr00A | Mjk7NcQbcE2UcEodaVaaVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.17 | 41904574 | 41904469 | Office Lvl 23 |  |  |  |  | day | 2023-09-26 07:00 | 2023-10-25 17:00 | [12 empty] | 16 | 6 | 1B31kdjtqEiMPWqj2tTfiw | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.17.1 | 41904962 | 41904574 | Decks and Outer Columns | 4 |  |  |  | day | 2023-09-26 07:00 | 2023-10-25 17:00 | [12 empty] | 0 | 7 | gehaqNvFAUuiAF0PSEHAiw | 1B31kdjtqEiMPWqj2tTfiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.18 | 41904573 | 41904469 | Office Lvl 24 | 18 |  |  |  | day | 2023-09-27 07:00 | 2023-10-26 17:00 | [12 empty] | 17 | 6 | RJOBDv5p4UWJnE7eHCWeQA | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.18.1 | 41904964 | 41904573 | Decks and Outer Columns |  |  |  |  | day | 2023-09-27 07:00 | 2023-10-26 17:00 | [12 empty] | 0 | 7 | f7Sme7P+zEyKpBLax+MA0w | RJOBDv5p4UWJnE7eHCWeQA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.19 | 41904572 | 41904469 | Office Lvl 25 |  |  |  |  | day | 2023-09-28 07:00 | 2023-11-09 17:00 | [12 empty] | 18 | 6 | FBN43627H0e15+CSlUF0yA | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.19.1 | 41904966 | 41904572 | Decks and Outer Columns | 3 |  |  |  | day | 2023-09-28 07:00 | 2023-11-09 17:00 | [12 empty] | 0 | 7 | UFi5L2Tg1Ua59epQyPOG1g | FBN43627H0e15+CSlUF0yA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.20 | 41904571 | 41904469 | Office Lvl 26 |  |  |  |  | day | 2023-09-30 07:00 | 2023-11-06 17:00 | [12 empty] | 19 | 6 | sJ2PLrKjt0yfzhv6xXRz/A | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.20.1 | 41904968 | 41904571 | Decks and Outer Columns |  |  |  |  | day | 2023-09-30 07:00 | 2023-11-06 17:00 | [12 empty] | 0 | 7 | 98yxPHEf5Eyp8mQ2qkpR1g | sJ2PLrKjt0yfzhv6xXRz/A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.21 | 41904570 | 41904469 | Office Lvl 27 |  |  |  |  | day | 2023-10-13 07:00 | 2023-11-08 17:00 | [12 empty] | 20 | 6 | BfW7KIRctEyXdAa/agisFw | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.21.1 | 41904970 | 41904570 | Decks and Outer Columns |  |  |  |  | day | 2023-10-13 07:00 | 2023-11-08 17:00 | [12 empty] | 0 | 7 | 6B67p5mDWUS/3qxAPm5eaw | BfW7KIRctEyXdAa/agisFw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.22 | 41904569 | 41904469 | Office Lvl 28 |  |  |  |  | day | 2023-10-18 07:00 | 2023-11-08 17:00 | [12 empty] | 21 | 6 | V0rXe3MkDkyo+Zn1m3holg | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.22.1 | 41904972 | 41904569 | Decks and Outer Columns |  |  |  |  | day | 2023-10-18 07:00 | 2023-11-08 17:00 | [12 empty] | 0 | 7 | 89bfrM4F4k2V5BgWeQHMSA | V0rXe3MkDkyo+Zn1m3holg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.23 | 41904568 | 41904469 | Office Lvl 29 | 7 |  |  |  | day | 2023-10-23 07:00 | 2023-11-10 17:00 | [12 empty] | 22 | 6 | wsZ5F4QSbUCKZOuhwq9EEw | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.23.1 | 41904974 | 41904568 | Decks and Outer Columns | 38 |  |  |  | day | 2023-10-23 07:00 | 2023-11-10 17:00 | [12 empty] | 0 | 7 | 462MVZv1fEuOQ+GlYECGow | wsZ5F4QSbUCKZOuhwq9EEw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.24 | 41904567 | 41904469 | Office Lvl 30 | 39 |  |  |  | day | 2023-10-31 07:00 | 2023-11-14 17:00 | [12 empty] | 23 | 6 | Fta2MNOym0e9mqJdwspueQ | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.24.1 | 41904976 | 41904567 | Decks and Outer Columns |  |  |  |  | day | 2023-10-31 07:00 | 2023-11-14 17:00 | [12 empty] | 0 | 7 | Tf2es1C2x0SmdQ8hFu4X3w | Fta2MNOym0e9mqJdwspueQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.25 | 41904566 | 41904469 | Office Lvl 31 | 31 |  |  |  | day | 2023-11-06 07:00 | 2023-11-15 17:00 | [12 empty] | 24 | 6 | ViKTv/DRSka1rmSvfBUhGQ | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.25.1 | 41904978 | 41904566 | Decks and Outer Columns | 37 |  |  |  | day | 2023-11-06 07:00 | 2023-11-15 17:00 | [12 empty] | 0 | 7 | Wqjr1/GvGk+Phrbtl5gkIw | ViKTv/DRSka1rmSvfBUhGQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.26 | 41904575 | 41904469 | Office Lvl 32 | 32 |  |  |  | day | 2023-11-10 07:00 | 2023-11-28 17:00 | [12 empty] | 25 | 6 | YfHf8DHD70iLhG7+a+BVQw | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.26.1 | 41904980 | 41904575 | Decks and Outer Columns | 22 |  |  |  | day | 2023-11-10 07:00 | 2023-11-28 17:00 | [12 empty] | 0 | 7 | jTDl4m5Kbk6AwKBoepCbvA | YfHf8DHD70iLhG7+a+BVQw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.27 | 41904576 | 41904469 | Office Lvl 33 |  |  |  |  | day | 2023-11-17 07:00 | 2023-12-19 17:00 | [12 empty] | 26 | 6 | dBeS+lUyy02tY+XYfqSAaQ | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.27.1 | 41904982 | 41904576 | Decks and Outer Columns |  |  |  |  | day | 2023-11-17 07:00 | 2023-12-19 17:00 | [12 empty] | 0 | 7 | 40L+JpZ4ekOXc2f4N4ngqg | dBeS+lUyy02tY+XYfqSAaQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.28 | 41904577 | 41904469 | Office Lvl 34 |  |  |  |  | day | 2023-12-01 07:00 | 2023-12-12 17:00 | [12 empty] | 27 | 6 | DxjALYP6A0GUdvkDkcgTSA | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.28.1 | 41904984 | 41904577 | Decks and Outer Columns |  |  |  |  | day | 2023-12-01 07:00 | 2023-12-12 17:00 | [12 empty] | 0 | 7 | jXo6eWtDmkePgsH10Zzeyw | DxjALYP6A0GUdvkDkcgTSA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.29 | 41904578 | 41904469 | Office Lvl 35 Mechanical | 32 |  |  |  | day | 2023-11-13 07:00 | 2023-12-15 17:00 | [12 empty] | 28 | 6 | mtd0TS0cck+adjANLfWu8w | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.29.1 | 41904986 | 41904578 | Decks and Outer Columns | 46 |  |  |  | day | 2023-11-13 07:00 | 2023-12-15 17:00 | [12 empty] | 0 | 7 | N6zv6K6bakmJYIa2XmX9qg | mtd0TS0cck+adjANLfWu8w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.9.30 | 41904579 | 41904469 | Office Lvl 36 Amenities (Concrete Structure Start) | 1 |  |  |  | day | 2023-12-01 07:00 | 2024-02-21 17:00 | [12 empty] | 29 | 6 | 0vEJuQVmK0+WXrk9X7ZT3g | Mz/uQ1Ln1kKm6mNNqi7fcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10 | 41904470 | 41904253 | CIP Resi Structure - Lvl 37 (El +486') to Lvl 51 (El +641') | 13 |  |  |  | day | 2024-01-17 07:00 | 2024-06-12 17:00 | [12 empty] | 9 | 5 | 5Wz6Rt8rqkKfzGy8hA0d5Q | sZchiSLlkUSGEhHuiFwXFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.1 | 41904580 | 41904470 | Residential Lvl 37 | 39 |  |  |  | day | 2024-01-17 07:00 | 2024-02-28 17:00 | [12 empty] | 0 | 6 | 42K+SKdggU+BSTDWZAECyQ | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.2 | 41904581 | 41904470 | Residential Lvl 38 |  |  |  |  | day | 2024-01-25 07:00 | 2024-03-07 17:00 | [12 empty] | 1 | 6 | kv5rGlgrkEC/+ulorN+J3w | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.3 | 41904582 | 41904470 | Residential Lvl 39 | 38 |  |  |  | day | 2024-02-02 07:00 | 2024-03-15 17:00 | [12 empty] | 2 | 6 | QEFgxLhrTUaRnMveeRwbbg | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.4 | 41904583 | 41904470 | Residential Lvl 40 | 5 |  |  |  | day | 2024-02-12 07:00 | 2024-03-22 17:00 | [12 empty] | 3 | 6 | H+aD1sNs1UWxQomuE4cPpA | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.5 | 41904584 | 41904470 | Residential Lvl 41 | 5 |  |  |  | day | 2024-02-20 07:00 | 2024-03-29 17:00 | [12 empty] | 4 | 6 | E4UTb0XD+E6E0ow0uL3J3Q | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.6 | 41904585 | 41904470 | Residential Lvl 42 | 2 |  |  |  | day | 2024-02-27 07:00 | 2024-04-05 17:00 | [12 empty] | 5 | 6 | wys/yh1Bv0SST4ED+4paeQ | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.7 | 41904586 | 41904470 | Residential Lvl 43 | 6 |  |  |  | day | 2024-03-05 07:00 | 2024-04-12 17:00 | [12 empty] | 6 | 6 | VXnog96lS0+Vj17Cw/Y8QQ | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.8 | 41904587 | 41904470 | Residential Lvl 44 | 7 |  |  |  | day | 2024-03-12 07:00 | 2024-04-22 17:00 | [12 empty] | 7 | 6 | P+eELesB20e7nEYcgZOgDA | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.9 | 41904588 | 41904470 | Residential Lvl 45 | 41 |  |  |  | day | 2024-03-19 07:00 | 2024-04-29 17:00 | [12 empty] | 8 | 6 | ZSrgMwYIpkuYm0edyQfNWw | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.10 | 41904589 | 41904470 | Residential Lvl 46 |  |  |  |  | day | 2024-03-26 07:00 | 2024-05-06 17:00 | [12 empty] | 9 | 6 | NMB5MbaStEGdW7+fw6I8Fw | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.11 | 41904590 | 41904470 | Residential Lvl 47 |  |  |  |  | day | 2024-04-02 07:00 | 2024-05-14 17:00 | [12 empty] | 10 | 6 | Hi7wBUklTUmi1uxDM7BXZg | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.12 | 41904591 | 41904470 | Residential Lvl 48 | 28 |  |  |  | day | 2024-04-10 07:00 | 2024-05-22 17:00 | [12 empty] | 11 | 6 | rN7tgkmwtEqIrvzfg9NdHg | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.13 | 41904592 | 41904470 | Residential Lvl 49 |  |  |  |  | day | 2024-04-19 07:00 | 2024-05-31 17:00 | [12 empty] | 12 | 6 | ktnvxDwivkqgB9yXH2n2xQ | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.14 | 41904593 | 41904470 | Residential Lvl 50 |  |  |  |  | day | 2024-04-29 07:00 | 2024-06-06 17:00 | [12 empty] | 13 | 6 | 1YwPebOfO0m7aoHLxa+Ohg | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.10.15 | 41904594 | 41904470 | Residential Lvl 51 | 38 |  |  |  | day | 2024-05-07 07:00 | 2024-06-12 17:00 | [12 empty] | 14 | 6 | 4ofFqr2vGEmWT4ZNkmyi+Q | 5Wz6Rt8rqkKfzGy8hA0d5Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.4.11 | 41904377 | 41904253 | Roof Lvl 52 | 26 |  |  |  | day | 2024-05-15 07:00 | 2024-06-18 17:00 | [12 empty] | 10 | 5 | OiI7rgAk10SuM3PimmI9gQ | sZchiSLlkUSGEhHuiFwXFA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.5 | 41904254 | 41904236 | TOWER FACADE | 35 |  |  |  | day | 2023-10-09 07:00 | 2024-09-27 17:00 | [12 empty] | 4 | 4 | PPY4WCZrw0WMsKObjxjJcA | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.5.1 | 41905626 | 41904254 | Office - 07-35 | 28 |  |  |  | day | 2023-10-09 07:00 | 2024-04-12 17:00 | [12 empty] | 0 | 5 | tvYOYn/DwEiWlSJHG99HsA | PPY4WCZrw0WMsKObjxjJcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.5.1.1 | 41905642 | 41905626 | Metal Panel | 37 |  |  |  | day | 2023-10-09 07:00 | 2024-03-06 17:00 | [12 empty] | 0 | 6 | 05bZXYSEREaSJAczV7zxfA | tvYOYn/DwEiWlSJHG99HsA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.5.1.2 | 41905643 | 41905626 | Curtainwall | 32 |  |  |  | day | 2023-10-16 07:00 | 2024-04-12 17:00 | [12 empty] | 1 | 6 | 7vndFVT9x02fna18yNkqPQ | tvYOYn/DwEiWlSJHG99HsA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.5.2 | 41905627 | 41904254 | Residential - 36 - TOH | 36 |  |  |  | day | 2024-04-02 07:00 | 2024-09-27 17:00 | [12 empty] | 1 | 5 | smMIYOk+oEe3ffl6umgD1w | PPY4WCZrw0WMsKObjxjJcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.5.3 | 41906991 | 41904254 | Deflection Comeback | 26 |  |  |  | day | 2024-03-26 07:00 | 2024-06-11 17:00 | [12 empty] | 2 | 5 | ETNTXuPcpkeou5PK9quxLg | PPY4WCZrw0WMsKObjxjJcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.5.3.1 | 41906992 | 41906991 | 1935-08-01 | 32 |  |  |  | day | 2024-03-26 07:00 | 2024-06-11 17:00 | [12 empty] | 0 | 6 | /dVrz8SN80mMpRUefQLg6w | ETNTXuPcpkeou5PK9quxLg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.5.3.2 | 41906993 | 41906991 | 36-TOH | 3 |  |  |  | day | [14 empty] | 1 | 6 | r2LR0iYyw0+cU/xzclCebQ | ETNTXuPcpkeou5PK9quxLg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.6 | 41904291 | 41904236 | TOWER HOIST | 21 |  |  |  | day | 2023-07-03 07:00 | 2025-03-14 17:00 | [12 empty] | 5 | 4 | S6t9vItH6EaPOTQ6hoGmlQ | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.6.1 | 41904453 | 41904291 | Hoist #1 (Tower - P1 to Top) | 1 |  |  |  | day | 2023-07-03 07:00 | 2025-03-14 17:00 | [12 empty] | 0 | 5 | URlNNPWT9kKt/wo18BZuXA | S6t9vItH6EaPOTQ6hoGmlQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.6.1.1 | 41906181 | 41904453 | Hoist install | 9 |  |  |  | day | 2023-07-03 07:00 | 2024-12-03 17:00 | [12 empty] | 0 | 6 | oMO+72MZy0KVXOuSrTZUaA | URlNNPWT9kKt/wo18BZuXA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.6.1.2 | 41906182 | 41904453 | Hoist Comeback | 4 |  |  |  | day | 2024-12-04 07:00 | 2025-03-14 17:00 | [12 empty] | 1 | 6 | u3NPKuJa9UOHwpnZUb6ouQ | URlNNPWT9kKt/wo18BZuXA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.6.1.2.1 | 41906183 | 41906182 | Office |  |  |  |  | day | 2024-12-26 07:00 | 2025-03-14 17:00 | [12 empty] | 0 | 7 | 2HgVmJjRfUS2Myft7smI5w | u3NPKuJa9UOHwpnZUb6ouQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.6.1.2.2 | 41906184 | 41906182 | Resi | 32 |  |  |  | day | 2024-12-04 07:00 | 2025-03-07 17:00 | [12 empty] | 1 | 7 | WcWo6sPAHU+W7I0ibM/2bQ | u3NPKuJa9UOHwpnZUb6ouQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.6.2 | 41904452 | 41904291 | Hoist #3 (Tower - Ground to Lvl 36 @ Summer) | 37 |  |  |  | day | [14 empty] | 1 | 5 | uKv9wnysFkWFKw1F/l2+CQ | S6t9vItH6EaPOTQ6hoGmlQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.7 | 41904255 | 41904236 | TOWER ROOF | 12 |  |  |  | day | 2023-10-30 07:00 | 2024-12-13 17:00 | [12 empty] | 6 | 4 | psGo7zUtx0iTcjqFSVjtdw | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.8 | 41904257 | 41904236 | TOWER INTERIOR ROUGH-IN | 30 |  |  |  | day | [14 empty] | 7 | 4 | x5C47WDPaU6L2w9t+VEOAw | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.9 | 41904545 | 41904236 | Great Space and Basement (El +18.25') | 46 |  |  |  | day | 2023-08-28 07:00 | 2024-12-06 17:00 | [12 empty] | 8 | 4 | 1DjGyU/1h0quKCXCgFJD+w | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.9.1 | 41904800 | 41904545 | Structure |  |  |  |  | day | 2023-12-26 07:00 | 2024-05-07 17:00 | [12 empty] | 0 | 5 | Z9SqDqTl70S1lQJwRCUSuw | 1DjGyU/1h0quKCXCgFJD+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.9.2 | 41907072 | 41904545 | RCP of Great Space | 44 |  |  |  | day | 2023-08-28 07:00 | 2024-11-05 17:00 | [12 empty] | 1 | 5 | YwMh7zs4ZE2tYVHVbLbG9A | 1DjGyU/1h0quKCXCgFJD+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.9.2.1 | 46578717 | 41907072 | Structure and Precast Panel Scope | 23 |  |  |  | day | 2024-01-16 07:00 | 2024-04-24 17:00 | [12 empty] | 0 | 6 | Xf+KoyE/VEiyqKpHlPzpmw | YwMh7zs4ZE2tYVHVbLbG9A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.9.2.1.1 | 46578714 | 46578717 | SEQUENCE 2 - Green | 14 |  |  |  | day | 2024-01-16 07:00 | 2024-03-26 17:00 | [12 empty] | 0 | 7 | 6raAYSQR+UOCqGDq12+kTw | Xf+KoyE/VEiyqKpHlPzpmw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.9.2.1.2 | 46578715 | 46578717 | SEQUENCE 1 - Blue | 28 |  |  |  | day | 2024-02-01 07:00 | 2024-04-09 17:00 | [12 empty] | 1 | 7 | z2jGbvsT2UChOkrgNbTbiQ | Xf+KoyE/VEiyqKpHlPzpmw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.9.2.1.3 | 46578716 | 46578717 | SEQUENCE 3 - Red |  |  |  |  | day | 2024-03-01 07:00 | 2024-04-24 17:00 | [12 empty] | 2 | 7 | lkBSjb0yy02EuNuGlI6gaw | Xf+KoyE/VEiyqKpHlPzpmw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.9.2.2 | 46578718 | 41907072 | Dome Scope |  |  |  |  | day | 2024-04-25 07:00 | 2024-11-05 17:00 | [12 empty] | 1 | 6 | 7fGjHnpGV0i6eK51TacH0g | YwMh7zs4ZE2tYVHVbLbG9A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.9.3 | 41904801 | 41904545 | RCP of Great Space - Bulletin 71R1 | 28 |  |  |  | day | [14 empty] | 2 | 5 | EHo966ipiEaM09NHaw1dpA | 1DjGyU/1h0quKCXCgFJD+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.9.4 | 41904802 | 41904545 | Ground Finishes/Pavers |  |  |  |  | day | 2024-11-06 07:00 | 2024-12-06 17:00 | [12 empty] | 3 | 5 | 4WjFiASxsU+J4E6SVQ4pkQ | 1DjGyU/1h0quKCXCgFJD+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.9.5 | 41904803 | 41904545 | Escalator Vestibule | 3 |  |  |  | day | 2024-11-07 07:00 | 2024-12-06 17:00 | [12 empty] | 4 | 5 | ZxyM6p3in0+0G97gATDIvg | 1DjGyU/1h0quKCXCgFJD+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.10 | 41905598 | 41904236 | TOWER STAIR | 11 |  |  |  | day | 2023-07-03 07:00 | 2024-03-13 17:00 | [12 empty] | 9 | 4 | CbZnn9m1j0mew2DGDV1fXg | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.10.1 | 41905599 | 41905598 | Stair 2A - Level 09-36 | 44 |  |  |  | day | 2023-07-03 07:00 | 2024-03-13 17:00 | [12 empty] | 0 | 5 | yuKF6f61FkOdYysGH9pP6w | CbZnn9m1j0mew2DGDV1fXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.10.2 | 41905769 | 41905598 | Stair 1A - Level 09-36 |  |  |  |  | day | 2023-07-03 07:00 | 2024-03-04 17:00 | [12 empty] | 1 | 5 | Vdb1PmgvjEqX6EY/mXEvuw | CbZnn9m1j0mew2DGDV1fXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.10.2.1 | 41906154 | 41905769 | Stair 1A - TC#1 Comeback | 26 |  |  |  | day | 2023-12-26 07:00 | 2024-01-23 17:00 | [12 empty] | 0 | 6 | eMTc9rgT70m17+BOUdmVKA | Vdb1PmgvjEqX6EY/mXEvuw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.10.2.2 | 41905768 | 41905769 | Stair 1A - Interiors - Level 11 to Level 17 | 30 |  |  |  | day | 2023-12-26 07:00 | 2024-03-04 17:00 | [12 empty] | 1 | 6 | Oml0R/3ycEyxabnTOy5AjA | Vdb1PmgvjEqX6EY/mXEvuw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.10.3 | 41905600 | 41905598 | Temp Stair PE-03 83-36 | 35 |  |  |  | day | 2023-12-26 07:00 | 2024-02-05 17:00 | [12 empty] | 2 | 5 | oPY6Xj4JPkKv1BTgtyeGYw | CbZnn9m1j0mew2DGDV1fXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11 | 41905607 | 41904236 | Tower - Office | 0 | 2023-09-07 08:00 | 2023-10-12 17:00 | 26 | day | 2023-07-05 07:00 | 2024-11-07 17:00 | [12 empty] | 10 | 4 | ZOM53F2XL0OCZjx9Q7JeVg | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.1 | 41904466 | 41905607 | Office - Rough |  |  |  |  | day | [14 empty] | 0 | 5 | WrmrGkcl30yxP2Nzb4tEHg | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.2 | 41904467 | 41905607 | Office - Finishes |  |  |  |  | day | [14 empty] | 1 | 5 | vvYPvRJ4VEW+gD4ae/TQtA | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.3 | 41904468 | 41905607 | Office - Punchlist |  |  |  |  | day | [14 empty] | 2 | 5 | lcB97Y6M10WY46Lw0L9jHg | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.4 | 41905628 | 41905607 | Level +74 - +109 - Mechanical Rooms | 4 |  |  |  | day | 2023-12-26 07:00 | 2024-07-15 17:00 | [12 empty] | 3 | 5 | ir6x3Tk1qUKIq3gKel8keA | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.5 | 41906997 | 41905607 | Level Mechanical Floor (+83) |  |  |  |  | day | 2023-07-05 07:00 | 2024-07-29 17:00 | [12 empty] | 4 | 5 | i4YqsLCLpEK81zG3qqKPZA | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.5.1 | 41907000 | 41906997 | Interior Summary & Milestones |  |  |  |  | day | 2023-07-05 07:00 | 2024-06-21 17:00 | [12 empty] | 0 | 6 | yZz7aT/si0WVx0wU4ARBmw | i4YqsLCLpEK81zG3qqKPZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.5.2 | 45117407 | 41906997 | COR#242 - Hold Area for Bulletin 136 |  |  |  |  | day | 2023-10-04 07:00 | 2024-07-29 17:00 | [12 empty] | 1 | 6 | vj/7ssxEakWxXs20Zn+MBQ | i4YqsLCLpEK81zG3qqKPZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.5.3 | 41907002 | 41906997 | Pre-Facde Scope | 39 |  |  |  | day | 2023-11-27 07:00 | 2024-01-02 17:00 | [12 empty] | 2 | 6 | uw1COzqEA0SaWtUZgfJhsA | i4YqsLCLpEK81zG3qqKPZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.5.4 | 41907003 | 41906997 | Rough Controls | 37 |  |  |  | day | 2023-11-20 07:00 | 2024-07-29 17:00 | [12 empty] | 3 | 6 | 1OGcrXZQDkWOWWfaaoiBAA | i4YqsLCLpEK81zG3qqKPZA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.6 | 41906998 | 41905607 | Level Service Corridor (+96') | 5 |  |  |  | day | 2023-07-12 07:00 | 2024-04-25 17:00 | [12 empty] | 5 | 5 | QixUBEt39k272c6aK8KdtA | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.6.1 | 41907001 | 41906998 | Interior Summary & Milestones | 7 |  |  |  | day | 2023-07-12 07:00 | 2024-04-25 17:00 | [12 empty] | 0 | 6 | 40PvVovsP0y8i1LuyLYZcg | QixUBEt39k272c6aK8KdtA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.7 | 41905630 | 41905607 | Level 09 - Sky Street Lobby (+109') | 22 |  |  |  | day | 2023-09-16 07:00 | 2024-08-05 17:00 | [12 empty] | 6 | 5 | bGIvVbcJaEWOV+Xrt0DLbQ | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.7.1 | 41906999 | 41905630 | Interior Summary & Milestones | 46 |  |  |  | day | 2023-09-16 07:00 | 2024-08-05 17:00 | [12 empty] | 0 | 6 | kXihetXrO028Wtf3l80ssg | bGIvVbcJaEWOV+Xrt0DLbQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8 | 41905629 | 41905607 | Level 10 |  |  |  |  | day | 2023-09-14 07:00 | 2024-07-01 17:00 | [12 empty] | 7 | 5 | t6DU0i78hkeWDArr9E8Bwg | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1 | 41905753 | 41905629 | Level 10 - Core | 45 |  |  |  | day | 2023-09-14 07:00 | 2024-04-25 17:00 | [12 empty] | 0 | 6 | wnsOHs96G0KK2DeqSoYlAg | t6DU0i78hkeWDArr9E8Bwg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.1 | 41905754 | 41905753 | Interior Summary & Milestones | 42 |  |  |  | day | 2023-09-14 07:00 | 2024-04-25 17:00 | [12 empty] | 0 | 7 | M2x+evSEDU+Om08gxRlWuA | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.2 | 41905755 | 41905753 | Core Risers | 11 |  |  |  | day | 2023-10-30 07:00 | 2023-11-13 17:00 | [12 empty] | 1 | 7 | oBmP2NGLhUGsOzeRqorsSw | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.3 | 41905756 | 41905753 | Layout, Critical Walls, Duct, Plumbing, FP | 25 |  |  |  | day | 2023-11-06 07:00 | 2023-12-26 17:00 | [12 empty] | 2 | 7 | VzjzJNawikSQbC3y0Jik/Q | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.4 | 41905757 | 41905753 | FA and Tele Data Rooms | 12 |  |  |  | day | 2023-12-26 07:00 | 2024-01-23 17:00 | [12 empty] | 3 | 7 |  | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.4.1 | 41905758 | 41905757 | Tele Data | 39 |  |  |  | day | 2023-12-26 07:00 | 2024-01-17 17:00 | [12 empty] | 0 | 8 | wcStQdF9CUyDZ2eM10Xm4w |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.4.2 | 41905759 | 41905757 | FA (Near ST1A) | 17 |  |  |  | day | 2023-12-28 07:00 | 2024-01-23 17:00 | [12 empty] | 1 | 8 | tDcOKpKWr0So9cunqQzStA |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.5 | 41905760 | 41905753 | Framing |  |  |  |  | day | 2023-11-20 07:00 | 2024-01-02 17:00 | [12 empty] | 4 | 7 | Uz259IDPgU2HTJpCOWBaiQ | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.6 | 41905761 | 41905753 | In-Wall Rough | 32 |  |  |  | day | 2024-01-03 07:00 | 2024-01-15 17:00 | [12 empty] | 5 | 7 | VrGOhxDyDEO4KUQZfhkz1Q | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.7 | 41905762 | 41905753 | Inspections |  |  |  |  | day | 2024-01-10 07:00 | 2024-01-16 17:00 | [12 empty] | 6 | 7 | h31Ewg8iVkSXObaLq6oGJw | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.8 | 41905763 | 41905753 | Bathroom Finishes | 39 |  |  |  | day | 2024-01-17 07:00 | 2024-03-27 17:00 | [12 empty] | 7 | 7 |  | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.9 | 41905764 | 41905753 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 42 |  |  |  | day | 2024-01-26 07:00 | 2024-02-16 17:00 | [12 empty] | 8 | 7 | 86H7gqI390GwcKW9PoHNgw | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.10 | 41905765 | 41905753 | Elevator Vestibule B - (PE-04--13) |  |  |  |  | day | 2024-01-30 07:00 | 2024-02-21 17:00 | [12 empty] | 9 | 7 | yVqdxs70HEex4GpdSRFunQ | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.11 | 41905766 | 41905753 | Worklist/Punchlist | 43 |  |  |  | day | 2024-03-28 07:00 | 2024-04-25 17:00 | [12 empty] | 10 | 7 | KpWHSOXduE6Y/sTo2LOd4g | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.1.12 | 41905767 | 41905753 | Start Up/Testing |  |  |  |  | day | 2024-04-23 07:00 | 2024-04-24 17:00 | [12 empty] | 11 | 7 | 2ybRO/KV+Euun0sIgej7bg | wnsOHs96G0KK2DeqSoYlAg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.8.2 | 43171926 | 41905629 | Level 10 - Outer | 47 |  |  |  | day | 2023-12-26 07:00 | 2024-06-06 17:00 | [12 empty] | 1 | 6 | m+YAdc4a4Em1DpLD3fotBQ | t6DU0i78hkeWDArr9E8Bwg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9 | 41905631 | 41905607 | Level 11 |  |  |  |  | day | 2023-09-15 07:00 | 2024-05-24 17:00 | [12 empty] | 8 | 5 | EEtwpfJ3wk+FRFCg3BWo8Q | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1 | 41905794 | 41905631 | Level 11 - Core | 4 |  |  |  | day | 2023-09-15 07:00 | 2024-05-02 17:00 | [12 empty] | 0 | 6 | P+gQ8SR/KUm+0TvcFanEPg | EEtwpfJ3wk+FRFCg3BWo8Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.1 | 41905795 | 41905794 | Interior Summary & Milestones |  |  |  |  | day | 2023-09-15 07:00 | 2024-05-02 17:00 | [12 empty] | 0 | 7 | CVRGN9pdm0ujE2pcGgGbiw | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.2 | 41905796 | 41905794 | Core Risers | 7 |  |  |  | day | 2023-11-06 07:00 | 2023-11-17 17:00 | [12 empty] | 1 | 7 | vJgqv19B7E6/l/2iEvdfeQ | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.3 | 41905797 | 41905794 | Layout, Critical Walls, Duct, Plumbing, FP | 41 |  |  |  | day | 2023-11-20 07:00 | 2024-01-02 17:00 | [12 empty] | 2 | 7 | JyX7aPCeXEqvwlTj+bSccQ | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.4 | 41905798 | 41905794 | FA and Tele Data Rooms | 48 |  |  |  | day | 2023-12-26 07:00 | 2024-01-23 17:00 | [12 empty] | 3 | 7 | dwwrshwbCUi3eQRHdNXKfg | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.4.1 | 41905799 | 41905798 | Tele Data | 27 |  |  |  | day | 2023-12-26 07:00 | 2024-01-17 17:00 | [12 empty] | 0 | 8 | 1mFlLom6akCPqVhG1RCsew | dwwrshwbCUi3eQRHdNXKfg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.4.2 | 41905800 | 41905798 | FA (Near ST1A) | 30 |  |  |  | day | 2023-12-28 07:00 | 2024-01-23 17:00 | [12 empty] | 1 | 8 | GfemoGqEwUuqnj0Amc9FHA | dwwrshwbCUi3eQRHdNXKfg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.5 | 41905801 | 41905794 | Framing |  |  |  |  | day | 2023-12-04 07:00 | 2024-01-02 17:00 | [12 empty] | 4 | 7 | WmHmTRjmvkOCG6NQIyG5hA | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.6 | 41905802 | 41905794 | In-Wall Rough | 28 |  |  |  | day | 2024-01-03 07:00 | 2024-01-15 17:00 | [12 empty] | 5 | 7 | CVzESkYjx0CrGOs+Y//E9w | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.7 | 41905803 | 41905794 | Inspections | 13 |  |  |  | day | 2024-01-10 07:00 | 2024-01-16 17:00 | [12 empty] | 6 | 7 | FZco4AOl3UuAoQ/PzdNRSA | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.8 | 41905804 | 41905794 | Bathroom Finishes |  |  |  |  | day | 2024-01-17 07:00 | 2024-03-27 17:00 | [12 empty] | 7 | 7 | h1kbSSnMWUi1wWShA1bi1w | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.9 | 41905805 | 41905794 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) |  |  |  |  | day | 2024-01-26 07:00 | 2024-02-16 17:00 | [12 empty] | 8 | 7 | /4O+ociqhUS8RnZ3/vyxXg | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.10 | 41905806 | 41905794 | Elevator Vestibule B - (PE-04--13) | 21 |  |  |  | day | 2024-01-30 07:00 | 2024-02-21 17:00 | [12 empty] | 9 | 7 | UGZiJjamsUKh6sFgUbIDEg | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.11 | 41905807 | 41905794 | Worklist/Punchlist |  |  |  |  | day | 2024-03-28 07:00 | 2024-04-25 17:00 | [12 empty] | 10 | 7 | 0QFqqbn6zUqyEhBZhqcqLA | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.9.1.12 | 41905808 | 41905794 | Start Up/Testing | 22 |  |  |  | day | 2024-04-25 07:00 | 2024-04-26 17:00 | [12 empty] | 11 | 7 | tMX3BWd7WU2z4o4dL716UA | P+gQ8SR/KUm+0TvcFanEPg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10 | 41905632 | 41905607 | Level 12 | 0 |  |  |  | day | 2023-09-19 07:00 | 2024-06-03 17:00 | [12 empty] | 9 | 5 | mVOIeIvl6k+4eqspMCl2tw | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1 | 41905809 | 41905632 | Level 12 - Core | 45 |  |  |  | day | 2023-09-19 07:00 | 2024-05-09 17:00 | [12 empty] | 0 | 6 | 4DCEownaqEiMvlP7gjMmnA | mVOIeIvl6k+4eqspMCl2tw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.1 | 41905810 | 41905809 | Interior Summary & Milestones | 36 |  |  |  | day | 2023-09-19 07:00 | 2024-05-09 17:00 | [12 empty] | 0 | 7 |  | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.2 | 41905811 | 41905809 | Core Risers | 20 |  |  |  | day | 2023-11-13 07:00 | 2023-11-27 17:00 | [12 empty] | 1 | 7 | V/cNZhJtMES+jujKAEqLMA | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.3 | 41905812 | 41905809 | Layout, Critical Walls, Duct, Plumbing, FP | 25 |  |  |  | day | 2023-11-28 07:00 | 2024-01-09 17:00 | [12 empty] | 2 | 7 | 0uSKj90QKk2IRgRQVeuJOg | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.4 | 41905813 | 41905809 | FA and Tele Data Rooms | 45 |  |  |  | day | 2023-12-26 07:00 | 2024-01-23 17:00 | [12 empty] | 3 | 7 | aA5DJejDwUOQmW714ZV3HQ | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.4.1 | 41905814 | 41905813 | Tele Data |  |  |  |  | day | 2023-12-26 07:00 | 2024-01-17 17:00 | [12 empty] | 0 | 8 | aaDWi5cN6UebY7KOkcE5AQ | aA5DJejDwUOQmW714ZV3HQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.4.2 | 41905815 | 41905813 | FA (Near ST1A) | 22 |  |  |  | day | 2023-12-28 07:00 | 2024-01-23 17:00 | [12 empty] | 1 | 8 | tfC4ZGsmBUmUNA0GoQer+g | aA5DJejDwUOQmW714ZV3HQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.5 | 41905816 | 41905809 | Framing | 0 |  |  |  | day | 2023-12-11 07:00 | 2024-01-09 17:00 | [12 empty] | 4 | 7 | MQ7uiKl6tUyrDinH6JO4wg | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.6 | 41905817 | 41905809 | In-Wall Rough |  |  |  |  | day | 2024-01-10 07:00 | 2024-01-22 17:00 | [12 empty] | 5 | 7 | Rz7C4ZJpEEi5qEpjpe93rQ | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.7 | 41905818 | 41905809 | Inspections | 14 |  |  |  | day | 2024-01-17 07:00 | 2024-01-23 17:00 | [12 empty] | 6 | 7 | Ufr5GCYH9kGiOgu5iag7cQ | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.8 | 41905819 | 41905809 | Bathroom Finishes | 20 |  |  |  | day | 2024-01-24 07:00 | 2024-04-03 17:00 | [12 empty] | 7 | 7 | aeOuhFldLkmG/vPszR/jiA | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.9 | 41905820 | 41905809 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 46 |  |  |  | day | 2024-02-02 07:00 | 2024-02-26 17:00 | [12 empty] | 8 | 7 | oUfYLvLYjkq8F9xk7s7GlA | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.10 | 41905821 | 41905809 | Elevator Vestibule B - (PE-04--13) | 8 |  |  |  | day | 2024-02-06 07:00 | 2024-02-28 17:00 | [12 empty] | 9 | 7 | 7jL9U6xbtEaw0LvDb294mA | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.11 | 41905822 | 41905809 | Worklist/Punchlist | 8 |  |  |  | day | 2024-04-04 07:00 | 2024-05-02 17:00 | [12 empty] | 10 | 7 | dLOA8OmUGEmHesDOqNIA9g | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.10.1.12 | 41905823 | 41905809 | Start Up/Testing | 9 |  |  |  | day | 2024-04-30 07:00 | 2024-05-01 17:00 | [12 empty] | 11 | 7 | VRNorrwqkkCIF3j+5vO2cA | 4DCEownaqEiMvlP7gjMmnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11 | 41905633 | 41905607 | Level 13 | 9 | 2023-09-07 08:00 | 2023-10-12 17:00 | 26 | day | 2023-09-20 07:00 | 2024-06-10 17:00 | [12 empty] | 10 | 5 | hcpqTSyOR0u2Uq4VjtcxKQ | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1 | 41905824 | 41905633 | Level 13 - Core | 14 | 2023-09-08 08:00 | 2023-10-12 17:00 | 26 | day | 2023-09-20 07:00 | 2024-05-16 17:00 | [12 empty] | 0 | 6 | EKabo/YYW02gLbewQDgEiw | hcpqTSyOR0u2Uq4VjtcxKQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.1 | 86533 | 41905824 | New task 1 | 10 | 2023-09-12 08:00 | 2023-10-14 17:00 | 26 | day | [14 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2 | 85237 | 41905824 | Rough | 15 | 2023-09-10 08:00 | 2023-09-24 17:00 | 5 | day | [14 empty] | 1 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.1 | 85278 | 85237 | BMCS Controls | 0 | 2023-09-08 08:00 | 2023-09-18 17:00 | 5 | day | [14 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.1.1 | 85283 | 85278 | New task 40 | 0 | 2023-09-08 08:00 | 2023-09-22 17:00 | 5 | day | [14 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.1.2 | 85282 | 85278 | New task 39 | 0 | 2023-09-07 08:00 | 2023-09-13 17:00 | 5 | day | [14 empty] | 1 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.1.3 | 85281 | 85278 | New task 38 | 14 | 2023-09-13 08:00 | 2023-09-15 17:00 | 5 | day | [14 empty] | 2 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.1.4 | 85279 | 85278 | New task 36 | 0 | 2023-09-07 08:00 | 2023-09-13 17:00 | 5 | day | [14 empty] | 3 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.2 | 85248 | 85237 | Fire Protection | 0 | 2023-09-07 08:00 | 2023-09-26 17:00 | 5 | day |  |  |  |  | Carlysle Engineering, Inc. (CAR255) | #E8331A | [8 empty] | 1 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.2.1 | 85252 | 85248 | New task 15 | 0 | 2023-09-07 08:00 | 2023-09-26 17:00 | 5 | day |  |  |  |  | Carlysle Engineering, Inc. (CAR255) | #E8331A | [8 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.2.2 | 85251 | 85248 | New task 14 | 0 | 2023-09-07 08:00 | 2023-09-22 17:00 | 5 | day |  |  |  |  | Carlysle Engineering, Inc. (CAR255) | #E8331A | [8 empty] | 1 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.2.3 | 85250 | 85248 | New task 13 | 0 | 2023-09-11 08:00 | 2023-09-14 17:00 | 5 | day |  |  |  |  | Carlysle Engineering, Inc. (CAR255) | #E8331A | [8 empty] | 2 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.2.4 | 85249 | 85248 | New task 12 | 7 | 2023-09-07 08:00 | 2023-09-26 17:00 | 5 | day |  |  |  |  | Carlysle Engineering, Inc. (CAR255) | #E8331A | [8 empty] | 3 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.3 | 85246 | 85237 | Duct | 16 | 2023-09-11 08:00 | 2023-09-21 17:00 | 5 | day |  |  |  |  | McCusker-Gill, Inc. (HINGHAM) | #48A925 | [8 empty] | 2 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.3.1 | 85254 | 85246 | New task 17 | 0 | 2023-09-07 08:00 | 2023-09-13 17:00 | 5 | day |  |  |  |  | McCusker-Gill, Inc. (HINGHAM) | #48A925 | [8 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.3.2 | 85253 | 85246 | New task 16 | 16 | 2023-09-13 08:00 | 2023-09-17 17:00 | 5 | day |  |  |  |  | McCusker-Gill, Inc. (HINGHAM) | #48A925 | [8 empty] | 1 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.3.3 | 85247 | 85246 | New task 10 | 0 | 2023-09-07 08:00 | 2023-09-13 17:00 | 5 | day |  |  |  |  | McCusker-Gill, Inc. (HINGHAM) | #48A925 | [8 empty] | 2 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.4 | 85244 | 85237 | Electrical | 0 | 2023-09-09 08:00 | 2023-09-20 17:00 | 5 | day |  |  |  |  | McDonald Electrical Corp. (HINGHAM) | #ED7D77 | [8 empty] | 3 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.4.1 | 85271 | 85244 | New task 34 | 0 | 2023-09-07 08:00 | 2023-09-13 17:00 | 5 | day |  |  |  |  | McDonald Electrical Corp. (HINGHAM) | #ED7D77 | [8 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.4.2 | 85270 | 85244 | New task 33 | 1 | 2023-09-08 08:00 | 2023-09-18 17:00 | 5 | day |  |  |  |  | McDonald Electrical Corp. (HINGHAM) | #ED7D77 | [8 empty] | 1 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.4.3 | 85269 | 85244 | New task 32 | 16 | 2023-09-11 08:00 | 2023-09-24 17:00 | 5 | day |  |  |  |  | McDonald Electrical Corp. (HINGHAM) | #ED7D77 | [8 empty] | 2 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.4.4 | 85245 | 85244 | New task 8 | 8 | 2023-09-12 08:00 | 2023-09-17 17:00 | 5 | day |  |  |  |  | McDonald Electrical Corp. (HINGHAM) | #ED7D77 | [8 empty] | 3 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.5 | 85242 | 85237 | HVAC | 11 | 2023-09-12 08:00 | 2023-09-25 17:00 | 5 | day |  |  |  |  | J.C. Higgins Corp. (JCH100) | #0025F7 | [8 empty] | 4 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.5.1 | 85266 | 85242 | Test and Inspect | 13 | 2023-09-10 08:00 | 2023-09-22 17:00 | 5 | day |  |  |  |  | J.C. Higgins Corp. (JCH100) | #0025F7 | [8 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.5.2 | 85265 | 85242 | New task 28 | 14 | 2023-09-12 08:00 | 2023-09-21 17:00 | 5 | day |  |  |  |  | J.C. Higgins Corp. (JCH100) | #0025F7 | [8 empty] | 1 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.5.3 | 85243 | 85242 | New task 6 | 0 | 2023-09-07 08:00 | 2023-09-13 17:00 | 5 | day |  |  |  |  | J.C. Higgins Corp. (JCH100) | #0025F7 | [8 empty] | 2 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.6 | 85240 | 85237 | Plumbing | 9 | 2023-09-12 08:00 | 2023-09-17 17:00 | 5 | day |  |  |  |  | American Plumbing & Heating (NORWELL) | #E73FF9 | [8 empty] | 5 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.6.1 | 85261 | 85240 | New task 24 | 0 | 2023-09-08 08:00 | 2023-09-14 17:00 | 5 | day |  |  |  |  | American Plumbing & Heating (NORWELL) | #E73FF9 | [8 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.6.2 | 85241 | 85240 | New task 4 | 10 | 2023-09-08 08:00 | 2023-09-17 17:00 | 5 | day |  |  |  |  | American Plumbing & Heating (NORWELL) | #E73FF9 | [8 empty] | 1 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.7 | 85238 | 85237 | Framing | 13 | 2023-09-11 08:00 | 2023-09-24 17:00 | 5 | day |  |  |  |  | Century Drywall, Inc. (LINCOLN) | #F4A460 | [8 empty] | 6 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.2.7.1 | 86534 | 85238 | Elev | 0 | 2023-09-07 08:00 | 2023-09-13 17:00 | 5 | day |  |  |  |  | Century Drywall, Inc. (LINCOLN) | #F4A460 | [8 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.3 | 41905825 | 41905824 | Interior Summary & Milestones |  |  |  |  | day | 2023-09-20 07:00 | 2024-05-16 17:00 | [12 empty] | 2 | 7 | UV5OTHd6vESFZQgWPIUYIg | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.4 | 41905826 | 41905824 | Core Risers | 18 | 2023-09-13 08:00 | 2023-10-13 17:00 | 19 | day | 2023-11-20 07:00 | 2023-12-01 17:00 | [12 empty] | 3 | 7 | RKiInDq8O0STbi/K0/ilLA | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.4.1 | 83498 | 41905826 | Core 13 Pull Plan | 0 | 2023-09-09 08:00 | 2023-10-09 17:00 | 19 | day | [14 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.4.1.1 | 85259 | 83498 | Top Track | 11 | 2023-09-11 08:00 | 2023-09-18 17:00 | 5 | day |  |  |  |  | Century Drywall, Inc. (LINCOLN) | #F4A460 | [8 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.4.1.2 | 85357 | 83498 | High Horizontals | 0 | 2023-09-14 08:00 | 2023-10-03 17:00 | 14 | day |  |  |  |  | Carlysle Engineering, Inc. (CAR255) | #E8331A | [8 empty] | 1 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.4.1.3 | 85263 | 83498 | Riser | 17 | 2023-09-11 08:00 | 2023-09-16 17:00 | 5 | day |  |  |  |  | American Plumbing & Heating (NORWELL) | #E73FF9 | [8 empty] | 2 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.4.1.3.1 | 85267 | 85263 | Install Risers (By Floor) | 0 | 2023-09-11 08:00 | 2023-09-14 17:00 | 4 | day |  |  |  |  | J.C. Higgins Corp. (JCH100) | #0025F7 | [8 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.4.1.3.2 | 85262 | 85263 | SE 3 Risers | 0 | 2023-09-11 08:00 | 2023-09-15 17:00 | 5 | day |  |  |  |  | American Plumbing & Heating (NORWELL) | #E73FF9 | [8 empty] | 1 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.4.1.4 | 85258 | 83498 | Shafts | 6 | 2023-09-24 08:00 | 2023-10-02 17:00 | 5 | day |  |  |  |  | Century Drywall, Inc. (LINCOLN) | #F4A460 | [8 empty] | 3 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.4.1.4.1 | 85257 | 85258 | Stair Press Shafts T Shape | 0 | 2023-09-18 08:00 | 2023-09-20 17:00 | 3 | day |  |  |  |  | Century Drywall, Inc. (LINCOLN) | #F4A460 | [8 empty] | 0 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.4.1.4.2 | 85239 | 85258 | SE 3 Shaft Framing (Swing Drop On SE 5+6) | 6 | 2023-09-22 08:00 | 2023-09-26 17:00 | 5 | day |  |  |  |  | Century Drywall, Inc. (LINCOLN) | #F4A460 | [8 empty] | 1 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.4.1.5 | 85255 | 83498 | Install Stair Press Ducts 1A+2A | 9 | 2023-09-27 08:00 | 2023-09-28 17:00 | 2 | day |  |  |  |  | McCusker-Gill, Inc. (HINGHAM) | #48A925 | [8 empty] | 4 |  |  |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.5 | 41905827 | 41905824 | Layout, Critical Walls, Duct, Plumbing, FP |  |  |  |  | day | 2023-12-04 07:00 | 2024-01-16 17:00 | [12 empty] | 4 | 7 | BU+OQbI/AUO+kvxU/ylbXg | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.6 | 41905828 | 41905824 | FA and Tele Data Rooms | 48 |  |  |  | day | 2023-12-26 07:00 | 2024-01-23 17:00 | [12 empty] | 5 | 7 | LXolcbZoN0SEVjE9mJgkww | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.6.1 | 41905829 | 41905828 | Tele Data | 19 |  |  |  | day | 2023-12-26 07:00 | 2024-01-17 17:00 | [12 empty] | 0 | 8 | e3+Sf+M3OEKLi8ewWh3mRA | LXolcbZoN0SEVjE9mJgkww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.6.2 | 41905830 | 41905828 | FA (Near ST1A) | 21 |  |  |  | day | 2023-12-28 07:00 | 2024-01-23 17:00 | [12 empty] | 1 | 8 | pbU2V1htZUeFe6HJ+Cv8HQ | LXolcbZoN0SEVjE9mJgkww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.7 | 41905831 | 41905824 | Framing |  |  |  |  | day | 2023-12-18 07:00 | 2024-01-16 17:00 | [12 empty] | 6 | 7 | WNcSUj9uzUeZHNMH15nxtA | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.8 | 41905832 | 41905824 | In-Wall Rough | 39 |  |  |  | day | 2024-01-17 07:00 | 2024-01-29 17:00 | [12 empty] | 7 | 7 | uTB+H8BlFUW9kNW6DOA9Sg | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.9 | 41905833 | 41905824 | Inspections | 48 |  |  |  | day | 2024-01-24 07:00 | 2024-01-30 17:00 | [12 empty] | 8 | 7 | LZ4ayaSg/0aizXe9y7f4Ag | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.10 | 41905834 | 41905824 | Bathroom Finishes | 6 |  |  |  | day | 2024-01-31 07:00 | 2024-04-10 17:00 | [12 empty] | 9 | 7 | HzlRKe7mNkO3+byV99G11A | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.11 | 41905835 | 41905824 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 0 |  |  |  | day | 2024-02-09 07:00 | 2024-03-04 17:00 | [12 empty] | 10 | 7 | ySLuvr9xq0C6q74ONc7iog | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.12 | 41905836 | 41905824 | Elevator Vestibule B - (PE-04--13) | 31 |  |  |  | day | 2024-02-13 07:00 | 2024-03-06 17:00 | [12 empty] | 11 | 7 | gtm4PcktK0yRb6fUVYkeYA | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.13 | 41905837 | 41905824 | Worklist/Punchlist | 12 |  |  |  | day | 2024-04-11 07:00 | 2024-05-09 17:00 | [12 empty] | 12 | 7 | mRcsmViZLkWFsEQR8DAA7g | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.11.1.14 | 41905838 | 41905824 | Start Up/Testing | 29 |  |  |  | day | 2024-05-07 07:00 | 2024-05-08 17:00 | [12 empty] | 13 | 7 | AmtSDOFep0SmkriCuEuE5w | EKabo/YYW02gLbewQDgEiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12 | 41905644 | 41905607 | Level 14 |  |  |  |  | day | 2023-09-21 07:00 | 2024-06-17 17:00 | [12 empty] | 11 | 5 | UnBXvcDaT02IFnF8mG/VRg | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1 | 41905839 | 41905644 | Level 14 - Core |  |  |  |  | day | 2023-09-21 07:00 | 2024-05-23 17:00 | [12 empty] | 0 | 6 | 9NLdVC1aYkisySx3MKBxyQ | UnBXvcDaT02IFnF8mG/VRg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.1 | 41905840 | 41905839 | Interior Summary & Milestones | 31 |  |  |  | day | 2023-09-21 07:00 | 2024-05-23 17:00 | [12 empty] | 0 | 7 | SaLvDh1Iu0unW6s91XFiKQ | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.2 | 41905841 | 41905839 | Core Risers | 29 |  |  |  | day | 2023-11-28 07:00 | 2023-12-08 17:00 | [12 empty] | 1 | 7 | IZZWoO3VgEKQH42zznX1PQ | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.3 | 41905842 | 41905839 | Layout, Critical Walls, Duct, Plumbing, FP | 28 |  |  |  | day | 2023-12-11 07:00 | 2024-01-16 17:00 | [12 empty] | 2 | 7 | wAg2LwFv3UGa/61KGD9+VQ | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.4 | 41905843 | 41905839 | FA and Tele Data Rooms |  |  |  |  | day | 2023-12-26 07:00 | 2024-01-23 17:00 | [12 empty] | 3 | 7 | HzqzY3OkSEegOJOTUs/euQ | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.4.1 | 41905844 | 41905843 | Tele Data | 44 |  |  |  | day | 2023-12-26 07:00 | 2024-01-17 17:00 | [12 empty] | 0 | 8 | vvPiAm2n0Ey/ogxjc4Scgw | HzqzY3OkSEegOJOTUs/euQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.4.2 | 41905845 | 41905843 | FA (Near ST1A) | 28 |  |  |  | day | 2023-12-28 07:00 | 2024-01-23 17:00 | [12 empty] | 1 | 8 | en7PITGlnUmMRnjPG5m2Xw | HzqzY3OkSEegOJOTUs/euQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.5 | 41905846 | 41905839 | Framing |  |  |  |  | day | 2023-12-26 07:00 | 2024-01-16 17:00 | [12 empty] | 4 | 7 | F5jX1s0zUkGzdkBPO0FwhQ | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.6 | 41905847 | 41905839 | In-Wall Rough |  |  |  |  | day | 2024-01-17 07:00 | 2024-01-29 17:00 | [12 empty] | 5 | 7 | enWNrwnNl0mLxfmihlieWQ | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.7 | 41905848 | 41905839 | Inspections |  |  |  |  | day | 2024-01-24 07:00 | 2024-01-30 17:00 | [12 empty] | 6 | 7 | tp2Buj50yUG/NgsGoMFAxg | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.8 | 41905849 | 41905839 | Bathroom Finishes | 18 |  |  |  | day | 2024-01-31 07:00 | 2024-04-10 17:00 | [12 empty] | 7 | 7 | P3yH/bIfd0WNafb0znTFeg | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.9 | 41905850 | 41905839 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 17 |  |  |  | day | 2024-02-09 07:00 | 2024-03-04 17:00 | [12 empty] | 8 | 7 | VxhxjtPaCE6cJkKEtm80QQ | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.10 | 41905851 | 41905839 | Elevator Vestibule B - (PE-04--13) | 0 |  |  |  | day | 2024-02-13 07:00 | 2024-03-06 17:00 | [12 empty] | 9 | 7 | bc//GUlf6E6nbW1K9Thg/w | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.11 | 41905852 | 41905839 | Worklist/Punchlist | 13 |  |  |  | day | 2024-04-11 07:00 | 2024-05-09 17:00 | [12 empty] | 10 | 7 | gsVxXMRnKE+hbEE+QBYPSg | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.12.1.12 | 41905853 | 41905839 | Start Up/Testing | 46 |  |  |  | day | 2024-05-09 07:00 | 2024-05-10 17:00 | [12 empty] | 11 | 7 | WcgRKCeiJUWZHruZiGxq3A | 9NLdVC1aYkisySx3MKBxyQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13 | 41905647 | 41905607 | Level 15 | 49 |  |  |  | day | 2023-09-22 07:00 | 2024-06-24 17:00 | [12 empty] | 12 | 5 | ZpD3bxLk0Emda278NiGL3A | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1 | 41905854 | 41905647 | Level 15 - Core | 1 |  |  |  | day | 2023-09-22 07:00 | 2024-05-31 17:00 | [12 empty] | 0 | 6 | aEeRspAIvECtdQymmsu6IQ | ZpD3bxLk0Emda278NiGL3A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.1 | 41905855 | 41905854 | Interior Summary & Milestones |  |  |  |  | day | 2023-09-22 07:00 | 2024-05-31 17:00 | [12 empty] | 0 | 7 | OMU/zwBTjEKmqYWlcSZ5ew | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.2 | 41905856 | 41905854 | Core Risers |  |  |  |  | day | 2023-12-04 07:00 | 2023-12-15 17:00 | [12 empty] | 1 | 7 | KOlNevcMgEWqZ/naYpicJw | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.3 | 41905857 | 41905854 | Layout, Critical Walls, Duct, Plumbing, FP | 49 |  |  |  | day | 2023-12-18 07:00 | 2024-01-30 17:00 | [12 empty] | 2 | 7 | vDI7ThtQeUi/fLk9miDGUA | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.4 | 41905858 | 41905854 | FA and Tele Data Rooms | 29 |  |  |  | day | 2023-12-26 07:00 | 2024-01-23 17:00 | [12 empty] | 3 | 7 | urRBcf48DUKzMzmwga7rgA | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.4.1 | 41905859 | 41905858 | Tele Data |  |  |  |  | day | 2023-12-26 07:00 | 2024-01-17 17:00 | [12 empty] | 0 | 8 | ghjhc/sZGkeHxZzwLHHVSg | urRBcf48DUKzMzmwga7rgA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.4.2 | 41905860 | 41905858 | FA (Near ST1A) |  |  |  |  | day | 2023-12-28 07:00 | 2024-01-23 17:00 | [12 empty] | 1 | 8 | 3mYIaGrM9EW7Kf/LqjhTww | urRBcf48DUKzMzmwga7rgA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.5 | 41905861 | 41905854 | Framing |  |  |  |  | day | 2024-01-03 07:00 | 2024-01-16 17:00 | [12 empty] | 4 | 7 | TIUx7LHq40mAywf24gBfmg | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.6 | 41905862 | 41905854 | In-Wall Rough | 7 |  |  |  | day | 2024-01-17 07:00 | 2024-02-12 17:00 | [12 empty] | 5 | 7 | LTcPlMNIeE2Xht0ALxLGHA | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.7 | 41905863 | 41905854 | Inspections |  |  |  |  | day | 2024-01-24 07:00 | 2024-02-13 17:00 | [12 empty] | 6 | 7 | MqEm49oeMkuJAE4optwieg | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.8 | 41905864 | 41905854 | Bathroom Finishes |  |  |  |  | day | 2024-02-14 07:00 | 2024-04-25 17:00 | [12 empty] | 7 | 7 | wUcBnHCTpUuDCSbhfJgGgQ | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.9 | 41905865 | 41905854 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) |  |  |  |  | day | 2024-02-26 07:00 | 2024-03-18 17:00 | [12 empty] | 8 | 7 | u2a18Fng402B7JzHYjtT0A | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.10 | 41905866 | 41905854 | Elevator Vestibule B - (PE-04--13) | 31 |  |  |  | day | 2024-02-28 07:00 | 2024-03-20 17:00 | [12 empty] | 9 | 7 | AZWsEVM5RkGnnwxsFQ2IWw | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.11 | 41905867 | 41905854 | Worklist/Punchlist | 9 |  |  |  | day | 2024-04-26 07:00 | 2024-05-23 17:00 | [12 empty] | 10 | 7 | A7JIJk6FrkC0yiS05gpKKg | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.1.12 | 41905868 | 41905854 | Start Up/Testing | 9 |  |  |  | day | 2024-05-21 07:00 | 2024-05-22 17:00 | [12 empty] | 11 | 7 | xfdRN+hDHkuSDFcNX1sH5w | aEeRspAIvECtdQymmsu6IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.13.2 | 45048707 | 41905647 | Level 15 - Outer | 18 |  |  |  | day | 2023-12-06 07:00 | 2024-01-16 17:00 | [12 empty] | 1 | 6 | xP3PjMrJeEycMdpzdrIlQw | ZpD3bxLk0Emda278NiGL3A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14 | 41905646 | 41905607 | Level 16 |  |  |  |  | day | 2023-10-03 07:00 | 2024-07-01 17:00 | [12 empty] | 13 | 5 | saEmEx7QqkqlTBW/Kz39NQ | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1 | 41905869 | 41905646 | Level 16 - Core | 33 |  |  |  | day | 2023-10-03 07:00 | 2024-06-07 17:00 | [12 empty] | 0 | 6 | Cn3p3yu85Um2s669G0SBVw | saEmEx7QqkqlTBW/Kz39NQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.1 | 41905870 | 41905869 | Interior Summary & Milestones |  |  |  |  | day | 2023-10-03 07:00 | 2024-06-07 17:00 | [12 empty] | 0 | 7 | LBs2lm1Gik2JaBEJD+RE9w | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.2 | 41905871 | 41905869 | Core Risers |  |  |  |  | day | 2023-12-11 07:00 | 2023-12-22 17:00 | [12 empty] | 1 | 7 | k8borCZtwUOQo1AzCbmlCQ | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.3 | 41905872 | 41905869 | Layout, Critical Walls, Duct, Plumbing, FP | 27 |  |  |  | day | 2023-12-26 07:00 | 2024-02-06 17:00 | [12 empty] | 2 | 7 | Iro9KGUEjUi2BYBeRlibZQ | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.4 | 41905873 | 41905869 | FA and Tele Data Rooms | 31 |  |  |  | day | 2024-01-03 07:00 | 2024-01-30 17:00 | [12 empty] | 3 | 7 | zMvj9kCZekaO59FZRvpEIA | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.4.1 | 41905874 | 41905873 | Tele Data | 49 |  |  |  | day | 2024-01-03 07:00 | 2024-01-24 17:00 | [12 empty] | 0 | 8 | n38s/jPAWkyOUtDT1dHmVA | zMvj9kCZekaO59FZRvpEIA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.4.2 | 41905875 | 41905873 | FA (Near ST1A) |  |  |  |  | day | 2024-01-05 07:00 | 2024-01-30 17:00 | [12 empty] | 1 | 8 | 3bQjAsZ9D0yHSre1iIyE1A | zMvj9kCZekaO59FZRvpEIA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.5 | 41905876 | 41905869 | Framing | 28 |  |  |  | day | 2024-01-10 07:00 | 2024-02-06 17:00 | [12 empty] | 4 | 7 | mQRuDpYvAkaJ2A8ZGJ07BA | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.6 | 41905877 | 41905869 | In-Wall Rough |  |  |  |  | day | 2024-02-07 07:00 | 2024-02-20 17:00 | [12 empty] | 5 | 7 | kKdROEjTT0GPEAYnIzeS1w | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.7 | 41905878 | 41905869 | Inspections | 0 |  |  |  | day | 2024-02-14 07:00 | 2024-02-21 17:00 | [12 empty] | 6 | 7 | 8GtcOt4gaEStrcBmb+wxgw | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.8 | 41905879 | 41905869 | Bathroom Finishes |  |  |  |  | day | 2024-02-22 07:00 | 2024-05-02 17:00 | [12 empty] | 7 | 7 | fSsp9YV+eUORzkgeIMRlhw | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.9 | 41905880 | 41905869 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 23 |  |  |  | day | 2024-03-04 07:00 | 2024-03-25 17:00 | [12 empty] | 8 | 7 | 0DMQjmpE50a7eVPv1LnYFQ | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.10 | 41905881 | 41905869 | Elevator Vestibule B - (PE-04--13) | 22 |  |  |  | day | 2024-03-06 07:00 | 2024-03-27 17:00 | [12 empty] | 9 | 7 | u8Tl6ezVdk2g7YV/tKrjTw | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.11 | 41905882 | 41905869 | Worklist/Punchlist | 7 |  |  |  | day | 2024-05-03 07:00 | 2024-05-31 17:00 | [12 empty] | 10 | 7 | VGT6w6jXhUur/Wdf8DfJyA | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.14.1.12 | 41905883 | 41905869 | Start Up/Testing | 46 |  |  |  | day | 2024-05-29 07:00 | 2024-05-30 17:00 | [12 empty] | 11 | 7 | yPYclJWWKEqHPP79ZrQkXA | Cn3p3yu85Um2s669G0SBVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15 | 41905645 | 41905607 | Level 17 | 36 |  |  |  | day | 2023-10-04 07:00 | 2024-07-09 17:00 | [12 empty] | 14 | 5 | 3UzCfFRNIkuNS9jJ+uWsRg | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1 | 41905884 | 41905645 | Level 17 - Core |  |  |  |  | day | 2023-10-04 07:00 | 2024-06-14 17:00 | [12 empty] | 0 | 6 | nlLyfKjXiUWNpFxwgMV71g | 3UzCfFRNIkuNS9jJ+uWsRg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.1 | 41905885 | 41905884 | Interior Summary & Milestones | 32 |  |  |  | day | 2023-10-04 07:00 | 2024-06-14 17:00 | [12 empty] | 0 | 7 | 7R6yjl3H5EmWg63tC3LsZg | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.2 | 41905886 | 41905884 | Core Risers | 27 |  |  |  | day | 2023-12-18 07:00 | 2024-01-02 17:00 | [12 empty] | 1 | 7 | mhxXLTqLhUGk4sfZvTHvqA | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.3 | 41905887 | 41905884 | Layout, Critical Walls, Duct, Plumbing, FP | 46 |  |  |  | day | 2024-01-03 07:00 | 2024-02-13 17:00 | [12 empty] | 2 | 7 | SxPt8NOxn0q4/mKP/Akg4g | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.4 | 41905888 | 41905884 | FA and Tele Data Rooms | 7 |  |  |  | day | 2024-01-10 07:00 | 2024-02-06 17:00 | [12 empty] | 3 | 7 | KIW89uKxzkGLZPDgc45R4w | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.4.1 | 41905889 | 41905888 | Tele Data | 33 |  |  |  | day | 2024-01-10 07:00 | 2024-01-31 17:00 | [12 empty] | 0 | 8 | 68UHexmpj0i/0VxKPQpxeQ | KIW89uKxzkGLZPDgc45R4w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.4.2 | 41905890 | 41905888 | FA (Near ST1A) | 34 |  |  |  | day | 2024-01-12 07:00 | 2024-02-06 17:00 | [12 empty] | 1 | 8 | QI/6G2YlTk6+8DXm0I7EcA | KIW89uKxzkGLZPDgc45R4w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.5 | 41905891 | 41905884 | Framing |  |  |  |  | day | 2024-01-17 07:00 | 2024-02-13 17:00 | [12 empty] | 4 | 7 | RI8v6Wq/m0aj5ev8ASZDPw | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.6 | 41905892 | 41905884 | In-Wall Rough | 23 |  |  |  | day | 2024-02-14 07:00 | 2024-02-27 17:00 | [12 empty] | 5 | 7 | G6NrhavwE0Wqd285rpKw1A | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.7 | 41905893 | 41905884 | Inspections | 13 |  |  |  | day | 2024-02-22 07:00 | 2024-02-28 17:00 | [12 empty] | 6 | 7 | os0B07/Q6k+ZZSuVcz64xQ | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.8 | 41905894 | 41905884 | Bathroom Finishes | 31 |  |  |  | day | 2024-02-29 07:00 | 2024-05-09 17:00 | [12 empty] | 7 | 7 | cqGNIIcdY0e4chrkdndrqw | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.9 | 41905895 | 41905884 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 45 |  |  |  | day | 2024-03-11 07:00 | 2024-04-01 17:00 | [12 empty] | 8 | 7 | pPszJaM7+kK6UqcXk+oEkA | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.10 | 41905896 | 41905884 | Elevator Vestibule B - (PE-04--13) |  |  |  |  | day | 2024-03-13 07:00 | 2024-04-03 17:00 | [12 empty] | 9 | 7 | hoEjDAmlNkaocK7J3NGD/Q | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.11 | 41905897 | 41905884 | Worklist/Punchlist | 15 |  |  |  | day | 2024-05-10 07:00 | 2024-06-07 17:00 | [12 empty] | 10 | 7 | e3BhPUfDMEmajy/uE79cUw | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.15.1.12 | 41905898 | 41905884 | Start Up/Testing | 3 |  |  |  | day | 2024-06-05 07:00 | 2024-06-06 17:00 | [12 empty] | 11 | 7 | jTKFyqgEW06HBx2mct6GBQ | nlLyfKjXiUWNpFxwgMV71g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16 | 41905648 | 41905607 | Level 18 |  |  |  |  | day | 2023-09-08 07:00 | 2024-07-16 17:00 | [12 empty] | 15 | 5 | nXzUyDBdGkmbhvAqvjSIug | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1 | 41905899 | 41905648 | Level 18 - Core |  |  |  |  | day | 2023-09-08 07:00 | 2024-06-21 17:00 | [12 empty] | 0 | 6 | da+DKVGQMkewD9y4ULN2wA | nXzUyDBdGkmbhvAqvjSIug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.1 | 41905900 | 41905899 | Interior Summary & Milestones | 13 |  |  |  | day | 2023-09-08 07:00 | 2024-06-21 17:00 | [12 empty] | 0 | 7 | LzMuMjPFCUavMI1SP18G+w | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.2 | 41905901 | 41905899 | Core Risers | 30 |  |  |  | day | 2023-12-26 07:00 | 2024-01-09 17:00 | [12 empty] | 1 | 7 | atRa6J36skuwZlcg86xK2A | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.3 | 41905902 | 41905899 | Layout, Critical Walls, Duct, Plumbing, FP | 47 |  |  |  | day | 2024-01-10 07:00 | 2024-02-21 17:00 | [12 empty] | 2 | 7 | YxOWNFSGL0+UICuWIRr2/A | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.4 | 41905903 | 41905899 | FA and Tele Data Rooms | 17 |  |  |  | day | 2024-01-17 07:00 | 2024-02-13 17:00 | [12 empty] | 3 | 7 | mqLW5eyeFkq/anA0ZaHIEA | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.4.1 | 41905904 | 41905903 | Tele Data | 6 |  |  |  | day | 2024-01-17 07:00 | 2024-02-07 17:00 | [12 empty] | 0 | 8 | yl3bg3NzAEyIWNF3cyzrpw | mqLW5eyeFkq/anA0ZaHIEA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.4.2 | 41905905 | 41905903 | FA (Near ST1A) | 9 |  |  |  | day | 2024-01-19 07:00 | 2024-02-13 17:00 | [12 empty] | 1 | 8 | uMYUIJQ6IEKdByy3f21ILA | mqLW5eyeFkq/anA0ZaHIEA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.5 | 41905906 | 41905899 | Framing |  |  |  |  | day | 2024-01-24 07:00 | 2024-02-21 17:00 | [12 empty] | 4 | 7 | PkJpumS8+kK6GlzC6odDPA | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.6 | 41905907 | 41905899 | In-Wall Rough | 32 |  |  |  | day | 2024-02-22 07:00 | 2024-03-05 17:00 | [12 empty] | 5 | 7 | ppJBNEoSJEmj9mqAMsb12A | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.7 | 41905908 | 41905899 | Inspections | 22 |  |  |  | day | 2024-02-29 07:00 | 2024-03-06 17:00 | [12 empty] | 6 | 7 | dfUj4NOBf0ankpWwl1rDkQ | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.8 | 41905909 | 41905899 | Bathroom Finishes | 20 |  |  |  | day | 2024-03-07 07:00 | 2024-05-16 17:00 | [12 empty] | 7 | 7 | T4i4bvBhK0W6500CsazT+A | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.9 | 41905910 | 41905899 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 18 |  |  |  | day | 2024-03-18 07:00 | 2024-04-08 17:00 | [12 empty] | 8 | 7 | 7SXIQ/SdZkisFcMGdKLyqQ | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.10 | 41905911 | 41905899 | Elevator Vestibule B - (PE-04--13) | 47 |  |  |  | day | 2024-03-20 07:00 | 2024-04-10 17:00 | [12 empty] | 9 | 7 | Xyy175F40kqLPogKf4sEUg | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.11 | 41905912 | 41905899 | Worklist/Punchlist | 18 |  |  |  | day | 2024-05-17 07:00 | 2024-06-14 17:00 | [12 empty] | 10 | 7 | yLuStXuu20iAVtKWthoysA | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.16.1.12 | 41905913 | 41905899 | Start Up/Testing | 35 |  |  |  | day | 2024-06-12 07:00 | 2024-06-13 17:00 | [12 empty] | 11 | 7 | ilVco9FM/UCpe4a4ZYwzvA | da+DKVGQMkewD9y4ULN2wA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17 | 41905649 | 41905607 | Level 19 | 28 |  |  |  | day | 2023-10-06 07:00 | 2024-07-23 17:00 | [12 empty] | 16 | 5 | OWyAP/VDKkua9l2nxVmkAA | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1 | 41905914 | 41905649 | Level 19 - Core | 17 |  |  |  | day | 2023-10-06 07:00 | 2024-06-28 17:00 | [12 empty] | 0 | 6 | OT9gGaQlRk2hc6Kfn1Ccbw | OWyAP/VDKkua9l2nxVmkAA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.1 | 41905915 | 41905914 | Interior Summary & Milestones |  |  |  |  | day | 2023-10-06 07:00 | 2024-06-28 17:00 | [12 empty] | 0 | 7 | OKAgPkbZN02FquoCWHunjg | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.2 | 41905916 | 41905914 | Core Risers |  |  |  |  | day | 2024-01-03 07:00 | 2024-01-16 17:00 | [12 empty] | 1 | 7 | 4uzO+9Vat06HfXzTpV7BvA | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.3 | 41905917 | 41905914 | Layout, Critical Walls, Duct, Plumbing, FP | 46 |  |  |  | day | 2024-01-17 07:00 | 2024-02-28 17:00 | [12 empty] | 2 | 7 | oGzXXUwX70yMCFezi5jBhA | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.4 | 41905918 | 41905914 | FA and Tele Data Rooms | 4 |  |  |  | day | 2024-01-24 07:00 | 2024-02-21 17:00 | [12 empty] | 3 | 7 | I76kvvSsUUujf6/JNrilzA | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.4.1 | 41905919 | 41905918 | Tele Data | 19 |  |  |  | day | 2024-01-24 07:00 | 2024-02-14 17:00 | [12 empty] | 0 | 8 | rKU4hJDlaUeiQDh+QP7uFw | I76kvvSsUUujf6/JNrilzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.4.2 | 41905920 | 41905918 | FA (Near ST1A) |  |  |  |  | day | 2024-01-26 07:00 | 2024-02-21 17:00 | [12 empty] | 1 | 8 | ytguBmg9i0eudcCA/d6NeQ | I76kvvSsUUujf6/JNrilzA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.5 | 41905921 | 41905914 | Framing |  |  |  |  | day | 2024-01-31 07:00 | 2024-02-28 17:00 | [12 empty] | 4 | 7 | 9uDJ3KsXWUicL7+j7YhQVg | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.6 | 41905922 | 41905914 | In-Wall Rough | 1 |  |  |  | day | 2024-02-29 07:00 | 2024-03-12 17:00 | [12 empty] | 5 | 7 | qN5lBZYPAk6uVFyIK+09NQ | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.7 | 41905923 | 41905914 | Inspections |  |  |  |  | day | 2024-03-07 07:00 | 2024-03-13 17:00 | [12 empty] | 6 | 7 | aCm92m2fSUmCb4R7CGYI5g | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.8 | 41905924 | 41905914 | Bathroom Finishes | 22 |  |  |  | day | 2024-03-14 07:00 | 2024-05-23 17:00 | [12 empty] | 7 | 7 | 4rcB84v5U0mPLdlDpnLdZw | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.9 | 41905925 | 41905914 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 11 |  |  |  | day | 2024-03-25 07:00 | 2024-04-16 17:00 | [12 empty] | 8 | 7 | zdAZtJ/5ME+4fdYkXZfE2g | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.10 | 41905926 | 41905914 | Elevator Vestibule B - (PE-04--13) | 19 |  |  |  | day | 2024-03-27 07:00 | 2024-04-18 17:00 | [12 empty] | 9 | 7 | BS6cf6NWc0qbWGObIoNtFQ | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.11 | 41905927 | 41905914 | Worklist/Punchlist | 4 |  |  |  | day | 2024-05-24 07:00 | 2024-06-21 17:00 | [12 empty] | 10 | 7 | kCyKgg+PkE+E1Z7Aiou/lw | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.17.1.12 | 41905928 | 41905914 | Start Up/Testing |  |  |  |  | day | 2024-06-19 07:00 | 2024-06-20 17:00 | [12 empty] | 11 | 7 | CSXHPFWy6Euksof4320Wug | OT9gGaQlRk2hc6Kfn1Ccbw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18 | 41905650 | 41905607 | Level 20 |  |  |  |  | day | 2023-10-11 07:00 | 2024-07-30 17:00 | [12 empty] | 17 | 5 | DH4ZvVwHmEuuz6W7eGEjVw | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1 | 41905929 | 41905650 | Level 20 - Core | 29 |  |  |  | day | 2023-10-11 07:00 | 2024-07-08 17:00 | [12 empty] | 0 | 6 | JWUd+gMl2UG/sTxoRbOpqw | DH4ZvVwHmEuuz6W7eGEjVw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.1 | 41905930 | 41905929 | Interior Summary & Milestones | 8 |  |  |  | day | 2023-10-11 07:00 | 2024-07-08 17:00 | [12 empty] | 0 | 7 | C0XBaEoNIEqaJHiDyLFKmw | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.2 | 41905931 | 41905929 | Core Risers | 33 |  |  |  | day | 2024-01-10 07:00 | 2024-01-23 17:00 | [12 empty] | 1 | 7 | p7Hzmj2gPEG/3FcDvl44Jg | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.3 | 41905932 | 41905929 | Layout, Critical Walls, Duct, Plumbing, FP | 43 |  |  |  | day | 2024-01-24 07:00 | 2024-03-06 17:00 | [12 empty] | 2 | 7 | 3Gyi2SzIkUG0FvdjT2Mltg | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.4 | 41905933 | 41905929 | FA and Tele Data Rooms | 34 |  |  |  | day | 2024-01-31 07:00 | 2024-02-28 17:00 | [12 empty] | 3 | 7 | NOQDDLRkVkWknDV/yZsUwA | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.4.1 | 41905934 | 41905933 | Tele Data | 21 |  |  |  | day | 2024-01-31 07:00 | 2024-02-22 17:00 | [12 empty] | 0 | 8 | YPxB+KOKfU+qxJDRYqmWrg | NOQDDLRkVkWknDV/yZsUwA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.4.2 | 41905935 | 41905933 | FA (Near ST1A) |  |  |  |  | day | 2024-02-02 07:00 | 2024-02-28 17:00 | [12 empty] | 1 | 8 | AfxEJ9Jc+ECJemiKa5ocRQ | NOQDDLRkVkWknDV/yZsUwA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.5 | 41905936 | 41905929 | Framing | 23 |  |  |  | day | 2024-02-07 07:00 | 2024-03-06 17:00 | [12 empty] | 4 | 7 | wj8RDWd1b0KWzpa1TPUd4A | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.6 | 41905937 | 41905929 | In-Wall Rough |  |  |  |  | day | 2024-03-07 07:00 | 2024-03-19 17:00 | [12 empty] | 5 | 7 | LC1sg2p3WECsnZKjK767Xw | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.7 | 41905938 | 41905929 | Inspections | 9 |  |  |  | day | 2024-03-14 07:00 | 2024-03-20 17:00 | [12 empty] | 6 | 7 | GFOF/6OMNU+TxdpNN/Y2ow | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.8 | 41905939 | 41905929 | Bathroom Finishes |  |  |  |  | day | 2024-03-21 07:00 | 2024-05-31 17:00 | [12 empty] | 7 | 7 | oFXAA/SIRU6ZVNRdIShm+A | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.9 | 41905940 | 41905929 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 45 |  |  |  | day | 2024-04-01 07:00 | 2024-04-23 17:00 | [12 empty] | 8 | 7 | NK2fJbUSXkmRriMejMX0KQ | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.10 | 41905941 | 41905929 | Elevator Vestibule B - (PE-04--13) |  |  |  |  | day | 2024-04-03 07:00 | 2024-04-25 17:00 | [12 empty] | 9 | 7 | dunFtztFpES62MzQICucDw | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.11 | 41905942 | 41905929 | Worklist/Punchlist | 31 |  |  |  | day | 2024-06-03 07:00 | 2024-06-28 17:00 | [12 empty] | 10 | 7 | Tm2tx08nzkKY8I+qVJyAsQ | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.18.1.12 | 41905943 | 41905929 | Start Up/Testing | 16 |  |  |  | day | 2024-06-26 07:00 | 2024-06-27 17:00 | [12 empty] | 11 | 7 | tCmiiIktnU6u8nuhfUErxQ | JWUd+gMl2UG/sTxoRbOpqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19 | 41905651 | 41905607 | Level 21 |  |  |  |  | day | 2023-10-12 07:00 | 2024-08-06 17:00 | [12 empty] | 18 | 5 | O3KacFq810mu9Ya6ksCJfg | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1 | 41905944 | 41905651 | Level 21 - Core | 16 |  |  |  | day | 2023-10-12 07:00 | 2024-07-15 17:00 | [12 empty] | 0 | 6 | 8GSzKKEBZU+W8DswrgmNmQ | O3KacFq810mu9Ya6ksCJfg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.1 | 41905945 | 41905944 | Interior Summary & Milestones | 13 |  |  |  | day | 2023-10-12 07:00 | 2024-07-15 17:00 | [12 empty] | 0 | 7 | qtQoXHy8lUqAJ3+Rwo/EWA | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.2 | 41905946 | 41905944 | Core Risers | 8 |  |  |  | day | 2024-01-17 07:00 | 2024-01-30 17:00 | [12 empty] | 1 | 7 | bcdPL3WroE68LsrTyqgyzQ | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.3 | 41905947 | 41905944 | Layout, Critical Walls, Duct, Plumbing, FP | 39 |  |  |  | day | 2024-01-31 07:00 | 2024-03-13 17:00 | [12 empty] | 2 | 7 | g2F7OpzU3k6mpvydegO0Xw | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.4 | 41905948 | 41905944 | FA and Tele Data Rooms | 1 |  |  |  | day | 2024-02-07 07:00 | 2024-03-06 17:00 | [12 empty] | 3 | 7 | FvSU1IzUkUWF5p8zOVi3xA | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.4.1 | 41905949 | 41905948 | Tele Data | 44 |  |  |  | day | 2024-02-07 07:00 | 2024-02-29 17:00 | [12 empty] | 0 | 8 |  | FvSU1IzUkUWF5p8zOVi3xA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.4.2 | 41905950 | 41905948 | FA (Near ST1A) | 24 |  |  |  | day | 2024-02-09 07:00 | 2024-03-06 17:00 | [12 empty] | 1 | 8 | LLmng7Kv+0exFIMKnHbMwQ | FvSU1IzUkUWF5p8zOVi3xA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.5 | 41905951 | 41905944 | Framing |  |  |  |  | day | 2024-02-14 07:00 | 2024-03-13 17:00 | [12 empty] | 4 | 7 | /rBAwaruHUy6Y4o9B6Tn/g | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.6 | 41905952 | 41905944 | In-Wall Rough | 8 |  |  |  | day | 2024-03-14 07:00 | 2024-03-26 17:00 | [12 empty] | 5 | 7 | Sz5VnJMO2E2HAWQn8KC1pg | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.7 | 41905953 | 41905944 | Inspections | 21 |  |  |  | day | 2024-03-21 07:00 | 2024-03-27 17:00 | [12 empty] | 6 | 7 |  | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.8 | 41905954 | 41905944 | Bathroom Finishes | 42 |  |  |  | day | 2024-03-28 07:00 | 2024-06-07 17:00 | [12 empty] | 7 | 7 | uRut7rQz00aFbQGlZubkkw | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.9 | 41905955 | 41905944 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 45 |  |  |  | day | 2024-04-08 07:00 | 2024-04-30 17:00 | [12 empty] | 8 | 7 | TDT1XzE8nk+nnYLwvuNwSw | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.10 | 41905956 | 41905944 | Elevator Vestibule B - (PE-04--13) | 3 |  |  |  | day | 2024-04-10 07:00 | 2024-05-02 17:00 | [12 empty] | 9 | 7 | CtVgcDOQmkqux2ghXX11pg | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.11 | 41905957 | 41905944 | Worklist/Punchlist |  |  |  |  | day | 2024-06-10 07:00 | 2024-07-08 17:00 | [12 empty] | 10 | 7 | fsmCaP7Xy0O0JXgx2GC0QQ | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.19.1.12 | 41905958 | 41905944 | Start Up/Testing |  |  |  |  | day | 2024-07-03 07:00 | 2024-07-05 17:00 | [12 empty] | 11 | 7 | Jq660vnXdU65oY80WqhqfA | 8GSzKKEBZU+W8DswrgmNmQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20 | 41905652 | 41905607 | Level 22 |  |  |  |  | day | 2023-09-26 07:00 | 2024-08-13 17:00 | [12 empty] | 19 | 5 | hZlMXM/e6kCCLS3QBKTbVA | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1 | 41905959 | 41905652 | Level 22 - Core | 33 |  |  |  | day | 2023-09-26 07:00 | 2024-07-22 17:00 | [12 empty] | 0 | 6 | ogJko6m6fUi3t5iacP6xyA | hZlMXM/e6kCCLS3QBKTbVA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.1 | 41905960 | 41905959 | Interior Summary & Milestones |  |  |  |  | day | 2023-09-26 07:00 | 2024-07-22 17:00 | [12 empty] | 0 | 7 | pQcuzOEdvEe8PeNh7O5Hlw | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.2 | 41905961 | 41905959 | Core Risers | 36 |  |  |  | day | 2024-01-24 07:00 | 2024-02-06 17:00 | [12 empty] | 1 | 7 | LyB9hHBbJUy5qxxLT59LWg | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.3 | 41905962 | 41905959 | Layout, Critical Walls, Duct, Plumbing, FP | 10 |  |  |  | day | 2024-02-07 07:00 | 2024-03-20 17:00 | [12 empty] | 2 | 7 | KjY2zx4vU0iFpHz1WTZlRw | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.4 | 41905963 | 41905959 | FA and Tele Data Rooms | 5 |  |  |  | day | 2024-02-14 07:00 | 2024-03-13 17:00 | [12 empty] | 3 | 7 | aaedet+BB06Zm9WAlMrWZg | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.4.1 | 41905964 | 41905963 | Tele Data |  |  |  |  | day | 2024-02-14 07:00 | 2024-03-07 17:00 | [12 empty] | 0 | 8 | NpMyun+7gUGUFKJig+Jedw | aaedet+BB06Zm9WAlMrWZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.4.2 | 41905965 | 41905963 | FA (Near ST1A) | 20 |  |  |  | day | 2024-02-16 07:00 | 2024-03-13 17:00 | [12 empty] | 1 | 8 | A45S297ZmUeAJGRajfyuDA | aaedet+BB06Zm9WAlMrWZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.5 | 41905966 | 41905959 | Framing | 41 |  |  |  | day | 2024-02-22 07:00 | 2024-03-20 17:00 | [12 empty] | 4 | 7 | /NaHFN/yGkWQqHp9b5u9YA | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.6 | 41905967 | 41905959 | In-Wall Rough | 35 |  |  |  | day | 2024-03-21 07:00 | 2024-04-02 17:00 | [12 empty] | 5 | 7 | tASG3w+8Y0avyhFjIPvUEA | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.7 | 41905968 | 41905959 | Inspections | 40 |  |  |  | day | 2024-03-28 07:00 | 2024-04-03 17:00 | [12 empty] | 6 | 7 | uoqvrMr5/Eet76I6wtiu9g | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.8 | 41905969 | 41905959 | Bathroom Finishes | 37 |  |  |  | day | 2024-04-04 07:00 | 2024-06-14 17:00 | [12 empty] | 7 | 7 | jZMh1QeNa0SzMRz7M2nG1g | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.9 | 41905970 | 41905959 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 33 |  |  |  | day | 2024-04-16 07:00 | 2024-05-07 17:00 | [12 empty] | 8 | 7 | SBOCnqHU5UO/59kLYEptYw | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.10 | 41905971 | 41905959 | Elevator Vestibule B - (PE-04--13) |  |  |  |  | day | 2024-04-18 07:00 | 2024-05-09 17:00 | [12 empty] | 9 | 7 | 0ID7jONkAke1iHRGThjZrQ | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.11 | 41905972 | 41905959 | Worklist/Punchlist | 36 |  |  |  | day | 2024-06-17 07:00 | 2024-07-15 17:00 | [12 empty] | 10 | 7 | 8Ddv5Odiq0mDhHR5UDIyMQ | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.20.1.12 | 41905973 | 41905959 | Start Up/Testing | 24 |  |  |  | day | 2024-07-11 07:00 | 2024-07-12 17:00 | [12 empty] | 11 | 7 | 5Bw8bYbD1kezZud6ApaPJA | ogJko6m6fUi3t5iacP6xyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21 | 41905653 | 41905607 | Level 23 |  |  |  |  | day | 2023-09-27 07:00 | 2024-08-20 17:00 | [12 empty] | 20 | 5 | kNthvQUa8kuMiaLwgZAZ0A | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1 | 41905974 | 41905653 | Level 23 - Core | 11 |  |  |  | day | 2023-09-27 07:00 | 2024-07-29 17:00 | [12 empty] | 0 | 6 |  | kNthvQUa8kuMiaLwgZAZ0A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.1 | 41905975 | 41905974 | Interior Summary & Milestones | 22 |  |  |  | day | 2023-09-27 07:00 | 2024-07-29 17:00 | [12 empty] | 0 | 7 | g8gZg7S98UO7EB1D2YdcLw |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.2 | 41905976 | 41905974 | Core Risers |  |  |  |  | day | 2024-01-31 07:00 | 2024-02-13 17:00 | [12 empty] | 1 | 7 | ynKXnNCmlkeV6P9J2WkwsA |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.3 | 41905977 | 41905974 | Layout, Critical Walls, Duct, Plumbing, FP |  |  |  |  | day | 2024-02-14 07:00 | 2024-03-27 17:00 | [12 empty] | 2 | 7 | 2HFy9sIrgESzvReTUKdxeg |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.4 | 41905978 | 41905974 | FA and Tele Data Rooms | 20 |  |  |  | day | 2024-02-22 07:00 | 2024-03-20 17:00 | [12 empty] | 3 | 7 | ByYL3Oew4E6Xwxs1SPt4IQ |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.4.1 | 41905979 | 41905978 | Tele Data |  |  |  |  | day | 2024-02-22 07:00 | 2024-03-14 17:00 | [12 empty] | 0 | 8 | O1Gn9TmA2UyB91JyooCnCg | ByYL3Oew4E6Xwxs1SPt4IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.4.2 | 41905980 | 41905978 | FA (Near ST1A) | 30 |  |  |  | day | 2024-02-26 07:00 | 2024-03-20 17:00 | [12 empty] | 1 | 8 | zLSKBaQEnkSGtjMEO0XjHg | ByYL3Oew4E6Xwxs1SPt4IQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.5 | 41905981 | 41905974 | Framing | 5 |  |  |  | day | 2024-02-29 07:00 | 2024-03-27 17:00 | [12 empty] | 4 | 7 | IdOJFIzMoU+UVr/SnGsxjQ |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.6 | 41905982 | 41905974 | In-Wall Rough | 26 |  |  |  | day | 2024-03-28 07:00 | 2024-04-09 17:00 | [12 empty] | 5 | 7 | yBvhhsxNoUunY4mNJpQ3Pg |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.7 | 41905983 | 41905974 | Inspections | 39 |  |  |  | day | 2024-04-04 07:00 | 2024-04-10 17:00 | [12 empty] | 6 | 7 | D3JxSty6WECJN+/U/KYTiw |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.8 | 41905984 | 41905974 | Bathroom Finishes |  |  |  |  | day | 2024-04-11 07:00 | 2024-06-21 17:00 | [12 empty] | 7 | 7 | /F6Qqo83AUSy9jlaOuxD7Q |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.9 | 41905985 | 41905974 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 11 |  |  |  | day | 2024-04-23 07:00 | 2024-05-14 17:00 | [12 empty] | 8 | 7 | PszuXjAuaUaJo83EKw46Og |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.10 | 41905986 | 41905974 | Elevator Vestibule B - (PE-04--13) | 44 |  |  |  | day | 2024-04-25 07:00 | 2024-05-16 17:00 | [12 empty] | 9 | 7 | 03VdP3x4TEqNL+99ver9NA |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.11 | 41905987 | 41905974 | Worklist/Punchlist | 6 |  |  |  | day | 2024-06-24 07:00 | 2024-07-22 17:00 | [12 empty] | 10 | 7 | 8LZat0oLj0W8CIoWMwGwRQ |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.21.1.12 | 41905988 | 41905974 | Start Up/Testing | 9 |  |  |  | day | 2024-07-18 07:00 | 2024-07-19 17:00 | [12 empty] | 11 | 7 | cTBm3SPhjUKld3djf0nKcA |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22 | 41905654 | 41905607 | Level 24 |  |  |  |  | day | 2023-09-28 07:00 | 2024-08-27 17:00 | [12 empty] | 21 | 5 | CPWiWkBTzUeRGOMICPOnzw | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1 | 41905989 | 41905654 | Level 24 - Core | 16 |  |  |  | day | 2023-09-28 07:00 | 2024-08-05 17:00 | [12 empty] | 0 | 6 | FNmShKNM/U2MgBnsO6QqXg | CPWiWkBTzUeRGOMICPOnzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.1 | 41905990 | 41905989 | Interior Summary & Milestones |  |  |  |  | day | 2023-09-28 07:00 | 2024-08-05 17:00 | [12 empty] | 0 | 7 | M9bv8L3b0ku4yoCRL+vvvA | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.2 | 41905991 | 41905989 | Core Risers | 20 |  |  |  | day | 2024-02-07 07:00 | 2024-02-21 17:00 | [12 empty] | 1 | 7 | EHTf1L20IkSTzRFsdLWegA | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.3 | 41905992 | 41905989 | Layout, Critical Walls, Duct, Plumbing, FP |  |  |  |  | day | 2024-02-22 07:00 | 2024-04-03 17:00 | [12 empty] | 2 | 7 | LpyS/tB9Ske4b25hsfAbcQ | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.4 | 41905993 | 41905989 | FA and Tele Data Rooms |  |  |  |  | day | 2024-02-29 07:00 | 2024-03-27 17:00 | [12 empty] | 3 | 7 | MTPOlJA5AUaljKI2rxLm+A | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.4.1 | 41905994 | 41905993 | Tele Data |  |  |  |  | day | 2024-02-29 07:00 | 2024-03-21 17:00 | [12 empty] | 0 | 8 | ju+YGiIj7kieq212ZJhkgA | MTPOlJA5AUaljKI2rxLm+A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.4.2 | 41905995 | 41905993 | FA (Near ST1A) | 42 |  |  |  | day | 2024-03-04 07:00 | 2024-03-27 17:00 | [12 empty] | 1 | 8 | 6oRN5BM3LUSvcU2FzPZd4w | MTPOlJA5AUaljKI2rxLm+A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.5 | 41905996 | 41905989 | Framing |  |  |  |  | day | 2024-03-07 07:00 | 2024-04-03 17:00 | [12 empty] | 4 | 7 | 3W9wHBPqo06BgB541j2sVw | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.6 | 41905997 | 41905989 | In-Wall Rough | 35 |  |  |  | day | 2024-04-04 07:00 | 2024-04-17 17:00 | [12 empty] | 5 | 7 | SOlYUlrcskSsLaXu/24UxA | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.7 | 41905998 | 41905989 | Inspections | 25 |  |  |  | day | 2024-04-11 07:00 | 2024-04-18 17:00 | [12 empty] | 6 | 7 | 37/SmoqCj0O4dWtTrVXStg | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.8 | 41905999 | 41905989 | Bathroom Finishes | 28 |  |  |  | day | 2024-04-19 07:00 | 2024-06-28 17:00 | [12 empty] | 7 | 7 | 2MSUfKTrO0uhpcjPmall1w | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.9 | 41906000 | 41905989 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) |  |  |  |  | day | 2024-04-30 07:00 | 2024-05-21 17:00 | [12 empty] | 8 | 7 | vWtkhkDu80SYEgJFBKsSpg | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.10 | 41906001 | 41905989 | Elevator Vestibule B - (PE-04--13) |  |  |  |  | day | 2024-05-02 07:00 | 2024-05-23 17:00 | [12 empty] | 9 | 7 | QqXGw8Dzi06j7aUmB+9flg | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.11 | 41906002 | 41905989 | Worklist/Punchlist | 39 |  |  |  | day | 2024-07-01 07:00 | 2024-07-29 17:00 | [12 empty] | 10 | 7 | IDDZDjNaB0CrRaxNHrUg1g | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.22.1.12 | 41906003 | 41905989 | Start Up/Testing | 10 |  |  |  | day | 2024-07-25 07:00 | 2024-07-26 17:00 | [12 empty] | 11 | 7 | Mm/nmygzLUuYti8jv6jauQ | FNmShKNM/U2MgBnsO6QqXg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23 | 41905655 | 41905607 | Level 25 | 35 |  |  |  | day | 2023-09-30 07:00 | 2024-09-04 17:00 | [12 empty] | 22 | 5 | rT2ZrkXnL068eelb9ZN/hQ | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1 | 41906004 | 41905655 | Level 25 - Core | 48 |  |  |  | day | 2023-09-30 07:00 | 2024-08-12 17:00 | [12 empty] | 0 | 6 | vj2gww6qoEaMnJk3VFjS4A | rT2ZrkXnL068eelb9ZN/hQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.1 | 41906005 | 41906004 | Interior Summary & Milestones | 38 |  |  |  | day | 2023-09-30 07:00 | 2024-08-12 17:00 | [12 empty] | 0 | 7 | 1ALEFa5hjk6LKoaHy9X8VA | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.2 | 41906006 | 41906004 | Core Risers | 39 |  |  |  | day | 2024-02-14 07:00 | 2024-02-28 17:00 | [12 empty] | 1 | 7 | BKrtaeVd+U2JuYVZFgG7ow | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.3 | 41906007 | 41906004 | Layout, Critical Walls, Duct, Plumbing, FP | 34 |  |  |  | day | 2024-02-29 07:00 | 2024-04-10 17:00 | [12 empty] | 2 | 7 | crqCdplIzEWl5+UEIuYLaw | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.4 | 41906008 | 41906004 | FA and Tele Data Rooms | 33 |  |  |  | day | 2024-03-07 07:00 | 2024-04-03 17:00 | [12 empty] | 3 | 7 | +615iAwKwUWIv59O8jF2pQ | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.4.1 | 41906009 | 41906008 | Tele Data | 46 |  |  |  | day | 2024-03-07 07:00 | 2024-03-28 17:00 | [12 empty] | 0 | 8 | bWsGiJ3OIUWYf5EyRWBxpQ | +615iAwKwUWIv59O8jF2pQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.4.2 | 41906010 | 41906008 | FA (Near ST1A) | 23 |  |  |  | day | 2024-03-11 07:00 | 2024-04-03 17:00 | [12 empty] | 1 | 8 | +3PlZr5AdkyhxuMRr6zQog | +615iAwKwUWIv59O8jF2pQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.5 | 41906011 | 41906004 | Framing | 21 |  |  |  | day | 2024-03-14 07:00 | 2024-04-10 17:00 | [12 empty] | 4 | 7 | 7yHTozgBFECS7uzNanke/w | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.6 | 41906012 | 41906004 | In-Wall Rough |  |  |  |  | day | 2024-04-11 07:00 | 2024-04-24 17:00 | [12 empty] | 5 | 7 | oH8z/G3dyUm18Id3l2kZ+Q | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.7 | 41906013 | 41906004 | Inspections | 32 |  |  |  | day | 2024-04-19 07:00 | 2024-04-25 17:00 | [12 empty] | 6 | 7 | s4soa7usLUuv4c0u05zOHQ | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.8 | 41906014 | 41906004 | Bathroom Finishes |  |  |  |  | day | 2024-04-26 07:00 | 2024-07-08 17:00 | [12 empty] | 7 | 7 | v1KZEHFvTU2iLryFpQ/YVA | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.9 | 41906015 | 41906004 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 46 |  |  |  | day | 2024-05-07 07:00 | 2024-05-29 17:00 | [12 empty] | 8 | 7 | 8kiD20hyB0K35Zq98hv1GA | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.10 | 41906016 | 41906004 | Elevator Vestibule B - (PE-04--13) | 19 |  |  |  | day | 2024-05-09 07:00 | 2024-05-31 17:00 | [12 empty] | 9 | 7 | VoRm9SortUCDSKetjdVDjg | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.11 | 41906017 | 41906004 | Worklist/Punchlist | 18 |  |  |  | day | 2024-07-09 07:00 | 2024-08-05 17:00 | [12 empty] | 10 | 7 | 8r5XqvOkNkyS/yqm8xa7oA | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.23.1.12 | 41906018 | 41906004 | Start Up/Testing |  |  |  |  | day | 2024-08-01 07:00 | 2024-08-02 17:00 | [12 empty] | 11 | 7 | FHyYcjhLhUatG/rj6RMO4A | vj2gww6qoEaMnJk3VFjS4A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24 | 41905656 | 41905607 | Level 26 | 42 |  |  |  | day | 2023-10-13 07:00 | 2024-09-11 17:00 | [12 empty] | 23 | 5 | i3GW66BF70i+qfyFoocRUQ | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1 | 41906019 | 41905656 | Level 26 - Core | 16 |  |  |  | day | 2023-10-13 07:00 | 2024-08-19 17:00 | [12 empty] | 0 | 6 | fty7jaZI2ESo9lCQDkXg+w | i3GW66BF70i+qfyFoocRUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.1 | 41906020 | 41906019 | Interior Summary & Milestones |  |  |  |  | day | 2023-10-13 07:00 | 2024-08-19 17:00 | [12 empty] | 0 | 7 | ZHJIvQEcKka4sdyxWyLZdg | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.2 | 41906021 | 41906019 | Core Risers | 42 |  |  |  | day | 2024-02-22 07:00 | 2024-03-06 17:00 | [12 empty] | 1 | 7 | Z1I7h1zf1UWntYGJ5Zl+Yw | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.3 | 41906022 | 41906019 | Layout, Critical Walls, Duct, Plumbing, FP | 33 |  |  |  | day | 2024-03-07 07:00 | 2024-04-18 17:00 | [12 empty] | 2 | 7 | Dl5iOvRRr0y6VkncCuiupA | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.4 | 41906023 | 41906019 | FA and Tele Data Rooms |  |  |  |  | day | 2024-03-14 07:00 | 2024-04-10 17:00 | [12 empty] | 3 | 7 | S9X6pyyA5kaxBUilBXawiA | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.4.1 | 41906024 | 41906023 | Tele Data | 25 |  |  |  | day | 2024-03-14 07:00 | 2024-04-04 17:00 | [12 empty] | 0 | 8 | je1PG+DiOkaDlV8iGQavHA | S9X6pyyA5kaxBUilBXawiA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.4.2 | 41906025 | 41906023 | FA (Near ST1A) | 1 |  |  |  | day | 2024-03-18 07:00 | 2024-04-10 17:00 | [12 empty] | 1 | 8 | hQaDxAii0UKfidIUdkmHgA | S9X6pyyA5kaxBUilBXawiA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.5 | 41906026 | 41906019 | Framing | 8 |  |  |  | day | 2024-03-21 07:00 | 2024-04-18 17:00 | [12 empty] | 4 | 7 | T6nT/SQGSEaqxdrLvTi5lA | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.6 | 41906027 | 41906019 | In-Wall Rough |  |  |  |  | day | 2024-04-19 07:00 | 2024-05-01 17:00 | [12 empty] | 5 | 7 | nyLj5y8ndkqjcC4XxzhjLw | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.7 | 41906028 | 41906019 | Inspections | 39 |  |  |  | day | 2024-04-26 07:00 | 2024-05-02 17:00 | [12 empty] | 6 | 7 | hfY4v8koC0GWeijSteSWCQ | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.8 | 41906029 | 41906019 | Bathroom Finishes | 16 |  |  |  | day | 2024-05-03 07:00 | 2024-07-15 17:00 | [12 empty] | 7 | 7 | OKq7nLM32E2xqD4DKg1kGQ | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.9 | 41906030 | 41906019 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 0 |  |  |  | day | 2024-05-14 07:00 | 2024-06-05 17:00 | [12 empty] | 8 | 7 | IhT2G1Y/8UWJYy7Vw0e9ow | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.10 | 41906031 | 41906019 | Elevator Vestibule B - (PE-10--15) | 24 |  |  |  | day | 2024-05-16 07:00 | 2024-06-07 17:00 | [12 empty] | 9 | 7 | Z2DNOnY9nkq3pNmqT+c7LA | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.11 | 41906032 | 41906019 | Worklist/Punchlist |  |  |  |  | day | 2024-07-16 07:00 | 2024-08-12 17:00 | [12 empty] | 10 | 7 | zVfYX+4tOUKrwwtJ1+dpEg | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.24.1.12 | 41906033 | 41906019 | Start Up/Testing | 39 |  |  |  | day | 2024-08-08 07:00 | 2024-08-09 17:00 | [12 empty] | 11 | 7 | fZhprpQQPk6kL8ut0mkC/A | fty7jaZI2ESo9lCQDkXg+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25 | 41905657 | 41905607 | Level 27 | 41 |  |  |  | day | 2023-10-18 07:00 | 2024-09-18 17:00 | [12 empty] | 24 | 5 | 5RJRsE7EKkiy+q8UyD/fiw | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1 | 41906034 | 41905657 | Level 27 - Core | 24 |  |  |  | day | 2023-10-18 07:00 | 2024-08-26 17:00 | [12 empty] | 0 | 6 | gpOL4kmP90OrCSdkMWvtrw | 5RJRsE7EKkiy+q8UyD/fiw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.1 | 41906035 | 41906034 | Interior Summary & Milestones |  |  |  |  | day | 2023-10-18 07:00 | 2024-08-26 17:00 | [12 empty] | 0 | 7 | JBgKleGBjkG/Q7ILGToO2w | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.2 | 41906036 | 41906034 | Core Risers | 34 |  |  |  | day | 2024-02-29 07:00 | 2024-03-13 17:00 | [12 empty] | 1 | 7 | VGr6GF4HFkqR0Ct/HhFFAA | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.3 | 41906037 | 41906034 | Layout, Critical Walls, Duct, Plumbing, FP |  |  |  |  | day | 2024-03-14 07:00 | 2024-04-25 17:00 | [12 empty] | 2 | 7 | iWi94Nk8eU+6GdRS8B5Yzw | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.4 | 41906038 | 41906034 | FA and Tele Data Rooms | 49 |  |  |  | day | 2024-03-21 07:00 | 2024-04-18 17:00 | [12 empty] | 3 | 7 | 5x33WD/jGkaB/UVsHrEFwA | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.4.1 | 41906039 | 41906038 | Tele Data | 36 |  |  |  | day | 2024-03-21 07:00 | 2024-04-11 17:00 | [12 empty] | 0 | 8 | e/4A9C7SH02A9hDWDoODjQ | 5x33WD/jGkaB/UVsHrEFwA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.4.2 | 41906040 | 41906038 | FA (Near ST1A) | 43 |  |  |  | day | 2024-03-25 07:00 | 2024-04-18 17:00 | [12 empty] | 1 | 8 | 3tm3yfuUJkq+MLi0gUM9wQ | 5x33WD/jGkaB/UVsHrEFwA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.5 | 41906041 | 41906034 | Framing | 43 |  |  |  | day | 2024-03-28 07:00 | 2024-04-25 17:00 | [12 empty] | 4 | 7 | z1cTiytnHEycbWhE0DFOtA | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.6 | 41906042 | 41906034 | In-Wall Rough | 29 |  |  |  | day | 2024-04-26 07:00 | 2024-05-08 17:00 | [12 empty] | 5 | 7 | zRaLOwJKYkyFw8LBqUhbKw | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.7 | 41906043 | 41906034 | Inspections |  |  |  |  | day | 2024-05-03 07:00 | 2024-05-09 17:00 | [12 empty] | 6 | 7 | qLA9NfcSJEi0VDXxelCEHA | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.8 | 41906044 | 41906034 | Bathroom Finishes |  |  |  |  | day | 2024-05-10 07:00 | 2024-07-22 17:00 | [12 empty] | 7 | 7 | vdk7HpR6z0eVhwBqQ/6Gqg | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.9 | 41906045 | 41906034 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) |  |  |  |  | day | 2024-05-21 07:00 | 2024-06-12 17:00 | [12 empty] | 8 | 7 | amB2zaXvAUObqq5D2TtHpg | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.10 | 41906046 | 41906034 | Elevator Vestibule B - (PE-10--15) | 18 |  |  |  | day | 2024-05-23 07:00 | 2024-06-14 17:00 | [12 empty] | 9 | 7 |  | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.11 | 41906047 | 41906034 | Worklist/Punchlist | 36 |  |  |  | day | 2024-07-23 07:00 | 2024-08-19 17:00 | [12 empty] | 10 | 7 | zhRHMbqTX0O66BgURY/ztQ | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.25.1.12 | 41906048 | 41906034 | Start Up/Testing | 43 |  |  |  | day | 2024-08-15 07:00 | 2024-08-16 17:00 | [12 empty] | 11 | 7 | cm/tm3oaUUCK/6QHWNV+cw | gpOL4kmP90OrCSdkMWvtrw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26 | 41905658 | 41905607 | Level 28 | 48 |  |  |  | day | 2023-10-23 07:00 | 2024-09-25 17:00 | [12 empty] | 25 | 5 | zNpOwqYlWUyzjxG0gQH8Jw | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1 | 41906049 | 41905658 | Level 28 - Core | 16 |  |  |  | day | 2023-10-23 07:00 | 2024-09-03 17:00 | [12 empty] | 0 | 6 | mTO9Ak7A6EWBNMhBPat++A | zNpOwqYlWUyzjxG0gQH8Jw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.1 | 41906050 | 41906049 | Interior Summary & Milestones | 9 |  |  |  | day | 2023-10-23 07:00 | 2024-09-03 17:00 | [12 empty] | 0 | 7 | T2RP6zugzky65/oT4qzXQQ | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.2 | 41906051 | 41906049 | Core Risers |  |  |  |  | day | 2024-03-07 07:00 | 2024-03-20 17:00 | [12 empty] | 1 | 7 | GYqLp6e7lUKPpg4IIf14YA | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.3 | 41906052 | 41906049 | Layout, Critical Walls, Duct, Plumbing, FP |  |  |  |  | day | 2024-03-21 07:00 | 2024-05-02 17:00 | [12 empty] | 2 | 7 | SlfmmAmCO0qs7SHAi/t8Cg | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.4 | 41906053 | 41906049 | FA and Tele Data Rooms | 11 |  |  |  | day | 2024-03-28 07:00 | 2024-04-25 17:00 | [12 empty] | 3 | 7 | 8sKCcd+QQ0ai9ldkVsWldg | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.4.1 | 41906054 | 41906053 | Tele Data |  |  |  |  | day | 2024-03-28 07:00 | 2024-04-19 17:00 | [12 empty] | 0 | 8 | 62ZaiHqd2kK25+EntVckxA | 8sKCcd+QQ0ai9ldkVsWldg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.4.2 | 41906055 | 41906053 | FA (Near ST1A) |  |  |  |  | day | 2024-04-01 07:00 | 2024-04-25 17:00 | [12 empty] | 1 | 8 |  | 8sKCcd+QQ0ai9ldkVsWldg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.5 | 41906056 | 41906049 | Framing | 18 |  |  |  | day | 2024-04-04 07:00 | 2024-05-02 17:00 | [12 empty] | 4 | 7 | A4Q2eWHq2kGazfYJjd3uoQ | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.6 | 41906057 | 41906049 | In-Wall Rough | 7 |  |  |  | day | 2024-05-03 07:00 | 2024-05-15 17:00 | [12 empty] | 5 | 7 | 1LIo0jQ7xEy2L1HTf+mzUw | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.7 | 41906058 | 41906049 | Inspections | 30 |  |  |  | day | 2024-05-10 07:00 | 2024-05-16 17:00 | [12 empty] | 6 | 7 | aP8UCcZfA0a1Jn9eo0WnHQ | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.8 | 41906059 | 41906049 | Bathroom Finishes | 20 |  |  |  | day | 2024-05-17 07:00 | 2024-07-29 17:00 | [12 empty] | 7 | 7 | M+kPqOKbSk6bRRCILvbZtQ | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.9 | 41906060 | 41906049 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 16 |  |  |  | day | 2024-05-29 07:00 | 2024-06-19 17:00 | [12 empty] | 8 | 7 | +m7bjX93/0GArPe0TTdWXA | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.10 | 41906061 | 41906049 | Elevator Vestibule B - (PE-10--15) | 22 |  |  |  | day | 2024-05-31 07:00 | 2024-06-21 17:00 | [12 empty] | 9 | 7 | rbHTYwXvQ0GI7icJyUphGA | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.11 | 41906062 | 41906049 | Worklist/Punchlist |  |  |  |  | day | 2024-07-30 07:00 | 2024-08-26 17:00 | [12 empty] | 10 | 7 | bNXhikPYekCPsAZ9LbsvsQ | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.26.1.12 | 41906063 | 41906049 | Start Up/Testing | 15 |  |  |  | day | 2024-08-22 07:00 | 2024-08-23 17:00 | [12 empty] | 11 | 7 | yKUAzFUxp0Gp88+vShdkQQ | mTO9Ak7A6EWBNMhBPat++A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27 | 41905659 | 41905607 | Level 29 | 5 |  |  |  | day | 2023-10-31 07:00 | 2024-10-02 17:00 | [12 empty] | 26 | 5 | z3tyPdbb/EaFNEHaDKCFSg | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1 | 41906064 | 41905659 | Level 29 - Core | 7 |  |  |  | day | 2023-10-31 07:00 | 2024-09-10 17:00 | [12 empty] | 0 | 6 | tWlOOucuck69wD/3Y/VxkQ | z3tyPdbb/EaFNEHaDKCFSg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.1 | 41906065 | 41906064 | Interior Summary & Milestones | 24 |  |  |  | day | 2023-10-31 07:00 | 2024-09-10 17:00 | [12 empty] | 0 | 7 | MWF/+KvI4Em2jJWytKli9Q | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.2 | 41906066 | 41906064 | Core Risers | 17 |  |  |  | day | 2024-03-14 07:00 | 2024-03-27 17:00 | [12 empty] | 1 | 7 | Q/fh/7yEskid+yiZ+RrIYA | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.3 | 41906067 | 41906064 | Layout, Critical Walls, Duct, Plumbing, FP | 24 |  |  |  | day | 2024-03-28 07:00 | 2024-05-09 17:00 | [12 empty] | 2 | 7 | GGN7bwAerUCgv3Fxv7XCTQ | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.4 | 41906068 | 41906064 | FA and Tele Data Rooms | 11 |  |  |  | day | 2024-04-04 07:00 | 2024-05-02 17:00 | [12 empty] | 3 | 7 | 7lfBrq3XoUyrhnucipxLNQ | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.4.1 | 41906069 | 41906068 | Tele Data | 14 |  |  |  | day | 2024-04-04 07:00 | 2024-04-26 17:00 | [12 empty] | 0 | 8 | swsQLqkhWEyeHxgZLSPA1A | 7lfBrq3XoUyrhnucipxLNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.4.2 | 41906070 | 41906068 | FA (Near ST1A) | 25 |  |  |  | day | 2024-04-08 07:00 | 2024-05-02 17:00 | [12 empty] | 1 | 8 | mr0wFrbNG0K6zoF2QmsqkA | 7lfBrq3XoUyrhnucipxLNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.5 | 41906071 | 41906064 | Framing | 40 |  |  |  | day | 2024-04-11 07:00 | 2024-05-09 17:00 | [12 empty] | 4 | 7 | dt4gi2StJk28/suUY7J5mQ | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.6 | 41906072 | 41906064 | In-Wall Rough | 44 |  |  |  | day | 2024-05-10 07:00 | 2024-05-22 17:00 | [12 empty] | 5 | 7 | aZAo/hLYJE6JmgdxGVZ5+A | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.7 | 41906073 | 41906064 | Inspections |  |  |  |  | day | 2024-05-17 07:00 | 2024-05-23 17:00 | [12 empty] | 6 | 7 | P93ZqRrd+0W3HvPEkWea5g | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.8 | 41906074 | 41906064 | Bathroom Finishes |  |  |  |  | day | 2024-05-24 07:00 | 2024-08-05 17:00 | [12 empty] | 7 | 7 | ZHsx55VlYkWyUYSgMixmFw | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.9 | 41906075 | 41906064 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 31 |  |  |  | day | 2024-06-05 07:00 | 2024-06-26 17:00 | [12 empty] | 8 | 7 | vNjfdhlVDUih1tzl8ixiGA | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.10 | 41906076 | 41906064 | Elevator Vestibule B - (PE-10--15) | 9 |  |  |  | day | 2024-06-07 07:00 | 2024-06-28 17:00 | [12 empty] | 9 | 7 | KAurHOISpkOo6DcUbUb8ng | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.11 | 41906077 | 41906064 | Worklist/Punchlist | 15 |  |  |  | day | 2024-08-06 07:00 | 2024-09-03 17:00 | [12 empty] | 10 | 7 | B6Vj+t4QpEmy6wKpYpo/2A | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.27.1.12 | 41906078 | 41906064 | Start Up/Testing |  |  |  |  | day | 2024-08-29 07:00 | 2024-08-30 17:00 | [12 empty] | 11 | 7 | R8doRBGQCUOsai/eZRMdpg | tWlOOucuck69wD/3Y/VxkQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28 | 41905660 | 41905607 | Level 30 | 16 |  |  |  | day | 2023-11-06 07:00 | 2024-10-09 17:00 | [12 empty] | 27 | 5 | Scko8SDAVEmFl0vy91D7Dw | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1 | 41906079 | 41905660 | Level 30 - Core | 22 |  |  |  | day | 2023-11-06 07:00 | 2024-09-17 17:00 | [12 empty] | 0 | 6 | e5V+wnWkzkeKcTefX8N/SA | Scko8SDAVEmFl0vy91D7Dw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.1 | 41906080 | 41906079 | Interior Summary & Milestones |  |  |  |  | day | 2023-11-06 07:00 | 2024-09-17 17:00 | [12 empty] | 0 | 7 | B9QeihWqTkmHspsZ+2TYVg | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.2 | 41906081 | 41906079 | Core Risers | 20 |  |  |  | day | 2024-03-21 07:00 | 2024-04-03 17:00 | [12 empty] | 1 | 7 | cUPtT90EfkiFHDyxW7HWFw | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.3 | 41906082 | 41906079 | Layout, Critical Walls, Duct, Plumbing, FP | 21 |  |  |  | day | 2024-04-04 07:00 | 2024-05-16 17:00 | [12 empty] | 2 | 7 | 0bfbiItrVUuK8oES7s4EIA | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.4 | 41906083 | 41906079 | FA and Tele Data Rooms | 6 |  |  |  | day | 2024-04-11 07:00 | 2024-05-09 17:00 | [12 empty] | 3 | 7 | S0uuwTu0wEq/hJRjDE3qgQ | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.4.1 | 41906084 | 41906083 | Tele Data | 13 |  |  |  | day | 2024-04-11 07:00 | 2024-05-03 17:00 | [12 empty] | 0 | 8 | GeZfVxdisU6fn9ms2Xl8+Q | S0uuwTu0wEq/hJRjDE3qgQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.4.2 | 41906085 | 41906083 | FA (Near ST1A) |  |  |  |  | day | 2024-04-16 07:00 | 2024-05-09 17:00 | [12 empty] | 1 | 8 | xTLvvR0YLU+PwM++ed059A | S0uuwTu0wEq/hJRjDE3qgQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.5 | 41906086 | 41906079 | Framing |  |  |  |  | day | 2024-04-19 07:00 | 2024-05-16 17:00 | [12 empty] | 4 | 7 | E5OMTCgcN0G7RlwWsoQ/Gw | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.6 | 41906087 | 41906079 | In-Wall Rough | 8 |  |  |  | day | 2024-05-17 07:00 | 2024-05-30 17:00 | [12 empty] | 5 | 7 | Dg5CxpJWUU6BliRpV2RQ9g | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.7 | 41906088 | 41906079 | Inspections |  |  |  |  | day | 2024-05-24 07:00 | 2024-05-31 17:00 | [12 empty] | 6 | 7 |  | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.8 | 41906089 | 41906079 | Bathroom Finishes | 7 |  |  |  | day | 2024-06-03 07:00 | 2024-08-12 17:00 | [12 empty] | 7 | 7 | ppJ9VQi+Fk+GlRkjyR+24w | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.9 | 41906090 | 41906079 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) |  |  |  |  | day | 2024-06-12 07:00 | 2024-07-03 17:00 | [12 empty] | 8 | 7 | z0aYCJgOd0GzZgOq+BhILw | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.10 | 41906091 | 41906079 | Elevator Vestibule B - (PE-10--15) | 22 |  |  |  | day | 2024-06-14 07:00 | 2024-07-08 17:00 | [12 empty] | 9 | 7 | Xdx6kh+Vw0Oa62zyuHAs5g | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.11 | 41906092 | 41906079 | Worklist/Punchlist | 28 |  |  |  | day | 2024-08-13 07:00 | 2024-09-10 17:00 | [12 empty] | 10 | 7 | jQdjvLWew0itmQHYEgCUmg | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.28.1.12 | 41906093 | 41906079 | Start Up/Testing | 17 |  |  |  | day | 2024-09-06 07:00 | 2024-09-09 17:00 | [12 empty] | 11 | 7 | bJnj/NAUfk6rYb+eHluReQ | e5V+wnWkzkeKcTefX8N/SA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29 | 41905661 | 41905607 | Level 31 |  |  |  |  | day | 2023-11-10 07:00 | 2024-10-17 17:00 | [12 empty] | 28 | 5 | DlX44YEeM0uw8rYQWeukAw | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1 | 41906094 | 41905661 | Level 31 - Core | 29 |  |  |  | day | 2023-11-10 07:00 | 2024-09-24 17:00 | [12 empty] | 0 | 6 | TXtMy18GY0+nWdyoZYB7zw | DlX44YEeM0uw8rYQWeukAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.1 | 41906095 | 41906094 | Interior Summary & Milestones |  |  |  |  | day | 2023-11-10 07:00 | 2024-09-24 17:00 | [12 empty] | 0 | 7 | CLK8fU0A60OFIwUkTNdUAg | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.2 | 41906096 | 41906094 | Core Risers |  |  |  |  | day | 2024-03-28 07:00 | 2024-04-10 17:00 | [12 empty] | 1 | 7 | meQzEaTxcUCeVn9Pw2XICw | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.3 | 41906097 | 41906094 | Layout, Critical Walls, Duct, Plumbing, FP | 17 |  |  |  | day | 2024-04-11 07:00 | 2024-05-23 17:00 | [12 empty] | 2 | 7 | JRU9CBfpRECUbuqLSCnJbw | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.4 | 41906098 | 41906094 | FA and Tele Data Rooms | 41 |  |  |  | day | 2024-04-19 07:00 | 2024-05-16 17:00 | [12 empty] | 3 | 7 | e7qmrXFPu0Gw8ZBNZHuBkg | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.4.1 | 41906099 | 41906098 | Tele Data | 38 |  |  |  | day | 2024-04-19 07:00 | 2024-05-10 17:00 | [12 empty] | 0 | 8 | mBYboBp020qPxv8fp7SUKQ | e7qmrXFPu0Gw8ZBNZHuBkg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.4.2 | 41906100 | 41906098 | FA (Near ST1A) | 16 |  |  |  | day | 2024-04-23 07:00 | 2024-05-16 17:00 | [12 empty] | 1 | 8 | qsbAl76or0W4tvK05BvbEw | e7qmrXFPu0Gw8ZBNZHuBkg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.5 | 41906101 | 41906094 | Framing | 13 |  |  |  | day | 2024-04-26 07:00 | 2024-05-23 17:00 | [12 empty] | 4 | 7 | qb/5C53seEmLnjFimta/Pw | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.6 | 41906102 | 41906094 | In-Wall Rough | 30 |  |  |  | day | 2024-05-24 07:00 | 2024-06-06 17:00 | [12 empty] | 5 | 7 | y3+8U9iKtEGHvOcx6KWKoA | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.7 | 41906103 | 41906094 | Inspections | 23 |  |  |  | day | 2024-06-03 07:00 | 2024-06-07 17:00 | [12 empty] | 6 | 7 | 3erdj7D650m16Pc1N00I4g | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.8 | 41906104 | 41906094 | Bathroom Finishes |  |  |  |  | day | 2024-06-10 07:00 | 2024-08-19 17:00 | [12 empty] | 7 | 7 | wSVk5fn440SojCqflBpY3w | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.9 | 41906105 | 41906094 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 43 |  |  |  | day | 2024-06-19 07:00 | 2024-07-11 17:00 | [12 empty] | 8 | 7 | rl/SMSfAtESQmCWr4F+PPw | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.10 | 41906106 | 41906094 | Elevator Vestibule B - (PE-10--15) |  |  |  |  | day | 2024-06-21 07:00 | 2024-07-15 17:00 | [12 empty] | 9 | 7 | pNJ6LQvFV0S6mjxZmBueaw | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.11 | 41906107 | 41906094 | Worklist/Punchlist |  |  |  |  | day | 2024-08-20 07:00 | 2024-09-17 17:00 | [12 empty] | 10 | 7 | 3itqgV90mUSWagDQIuORZQ | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.29.1.12 | 41906108 | 41906094 | Start Up/Testing | 2 |  |  |  | day | 2024-09-13 07:00 | 2024-09-16 17:00 | [12 empty] | 11 | 7 | k2LbWBbBGUa4wicVQSFLIA | TXtMy18GY0+nWdyoZYB7zw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30 | 41905662 | 41905607 | Level 32 |  |  |  |  | day | 2023-11-17 07:00 | 2024-10-24 17:00 | [12 empty] | 29 | 5 | L//wgU5rS060orpA80yThg | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1 | 41906109 | 41905662 | Level 32 - Core |  |  |  |  | day | 2023-11-17 07:00 | 2024-10-01 17:00 | [12 empty] | 0 | 6 | kRr9xr1siEWKCvkCJKCPAw | L//wgU5rS060orpA80yThg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.1 | 41906110 | 41906109 | Interior Summary & Milestones | 39 |  |  |  | day | 2023-11-17 07:00 | 2024-10-01 17:00 | [12 empty] | 0 | 7 | hrxuvYxvOUqutX3acx5cgg | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.2 | 41906111 | 41906109 | Core Risers | 25 |  |  |  | day | 2024-04-04 07:00 | 2024-04-18 17:00 | [12 empty] | 1 | 7 | YmAb3XE4tUWJs9Y3eb3Ekw | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.3 | 41906112 | 41906109 | Layout, Critical Walls, Duct, Plumbing, FP |  |  |  |  | day | 2024-04-19 07:00 | 2024-05-31 17:00 | [12 empty] | 2 | 7 | y6u1oQzz/ECYIh+nmWZDPA | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.4 | 41906113 | 41906109 | FA and Tele Data Rooms | 43 |  |  |  | day | 2024-04-26 07:00 | 2024-05-23 17:00 | [12 empty] | 3 | 7 | elfWQaeCGkKyswT6fhGi4g | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.4.1 | 41906114 | 41906113 | Tele Data | 38 |  |  |  | day | 2024-04-26 07:00 | 2024-05-17 17:00 | [12 empty] | 0 | 8 | WtGs5iaJDkeOf7SeLvDd7A | elfWQaeCGkKyswT6fhGi4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.4.2 | 41906115 | 41906113 | FA (Near ST1A) | 14 |  |  |  | day | 2024-04-30 07:00 | 2024-05-23 17:00 | [12 empty] | 1 | 8 | ZUYQ7r+6cUqH6tDyaIPhRA | elfWQaeCGkKyswT6fhGi4g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.5 | 41906116 | 41906109 | Framing | 48 |  |  |  | day | 2024-05-03 07:00 | 2024-05-31 17:00 | [12 empty] | 4 | 7 | MGwC19etvEeepKeOuFqg7g | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.6 | 41906117 | 41906109 | In-Wall Rough | 3 |  |  |  | day | 2024-06-03 07:00 | 2024-06-13 17:00 | [12 empty] | 5 | 7 | y4Ics2WcbkGV1sIFomljeA | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.7 | 41906118 | 41906109 | Inspections | 28 |  |  |  | day | 2024-06-10 07:00 | 2024-06-14 17:00 | [12 empty] | 6 | 7 | MD1CXTIYukGT6+0lpaCUcA | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.8 | 41906119 | 41906109 | Bathroom Finishes |  |  |  |  | day | 2024-06-17 07:00 | 2024-08-26 17:00 | [12 empty] | 7 | 7 | j+GFHGwFXU6+I2+G6tUtJg | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.9 | 41906120 | 41906109 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 24 |  |  |  | day | 2024-06-26 07:00 | 2024-07-18 17:00 | [12 empty] | 8 | 7 | iDdDbQGlpUa/pYF7lE/wmg | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.10 | 41906121 | 41906109 | Elevator Vestibule B - (PE-10--15) | 12 |  |  |  | day | 2024-06-28 07:00 | 2024-07-22 17:00 | [12 empty] | 9 | 7 | O23vsqR7XkCs3xSXaE9YnQ | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.11 | 41906122 | 41906109 | Worklist/Punchlist | 17 |  |  |  | day | 2024-08-27 07:00 | 2024-09-24 17:00 | [12 empty] | 10 | 7 | 8h23q47UkEWOv6MxK+6iRA | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.30.1.12 | 41906123 | 41906109 | Start Up/Testing | 32 |  |  |  | day | 2024-09-20 07:00 | 2024-09-23 17:00 | [12 empty] | 11 | 7 | WolKjjaeu0i81ZJNg4AvcA | kRr9xr1siEWKCvkCJKCPAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31 | 41905663 | 41905607 | Level 33 | 15 |  |  |  | day | 2023-12-26 07:00 | 2024-10-31 17:00 | [12 empty] | 30 | 5 | 0MbIxTy10kmEiUzJjHN+kw | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1 | 41906124 | 41905663 | Level 33 - Core | 44 |  |  |  | day | 2023-12-26 07:00 | 2024-10-08 17:00 | [12 empty] | 0 | 6 | Ix9lBMUDlEeCtGZtBup1uw | 0MbIxTy10kmEiUzJjHN+kw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.1 | 41906125 | 41906124 | Interior Summary & Milestones | 41 |  |  |  | day | 2023-12-26 07:00 | 2024-10-08 17:00 | [12 empty] | 0 | 7 | SNJmu3QsB0KcX0Mz5fQOgw | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.2 | 41906126 | 41906124 | Core Risers | 43 |  |  |  | day | 2024-04-11 07:00 | 2024-04-25 17:00 | [12 empty] | 1 | 7 | eR94EGkrrUGO6m3eL8jd/w | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.3 | 41906127 | 41906124 | Layout, Critical Walls, Duct, Plumbing, FP | 1 |  |  |  | day | 2024-04-26 07:00 | 2024-06-07 17:00 | [12 empty] | 2 | 7 | 23fUPbq6mkmwplD1Qy4zOA | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.4 | 41906128 | 41906124 | FA and Tele Data Rooms |  |  |  |  | day | 2024-05-03 07:00 | 2024-05-31 17:00 | [12 empty] | 3 | 7 |  | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.4.1 | 41906129 | 41906128 | Tele Data |  |  |  |  | day | 2024-05-03 07:00 | 2024-05-24 17:00 | [12 empty] | 0 | 8 | /yvskSKIkUSr3W1918sPTQ |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.4.2 | 41906130 | 41906128 | FA (Near ST1A) | 33 |  |  |  | day | 2024-05-07 07:00 | 2024-05-31 17:00 | [12 empty] | 1 | 8 | Vm1PoIOU/06CKtnEMV0E2w |  | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.5 | 41906131 | 41906124 | Framing | 29 |  |  |  | day | 2024-05-10 07:00 | 2024-06-07 17:00 | [12 empty] | 4 | 7 | noo4rwqvW0WBIPYJsX55+w | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.6 | 41906132 | 41906124 | In-Wall Rough | 12 |  |  |  | day | 2024-06-10 07:00 | 2024-06-20 17:00 | [12 empty] | 5 | 7 | u3lHpLHEeUegMPV940a5eg | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.7 | 41906133 | 41906124 | Inspections | 12 |  |  |  | day | 2024-06-17 07:00 | 2024-06-21 17:00 | [12 empty] | 6 | 7 | etKeKPcIak2MeBhKOB3qDg | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.8 | 41906134 | 41906124 | Bathroom Finishes | 17 |  |  |  | day | 2024-06-24 07:00 | 2024-09-03 17:00 | [12 empty] | 7 | 7 | qezb+Lz9lEKkOvy7YochVg | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.9 | 41906135 | 41906124 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) |  |  |  |  | day | 2024-07-03 07:00 | 2024-07-25 17:00 | [12 empty] | 8 | 7 | sxtjFhUpVE+Vop1bBZRzow | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.10 | 41906136 | 41906124 | Elevator Vestibule B - (PE-10--15) |  |  |  |  | day | 2024-07-08 07:00 | 2024-07-29 17:00 | [12 empty] | 9 | 7 | EEEXdtV4jUaPjH5CP4BIYw | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.11 | 41906137 | 41906124 | Worklist/Punchlist |  |  |  |  | day | 2024-09-04 07:00 | 2024-10-01 17:00 | [12 empty] | 10 | 7 | 2VxeOQauGUqwLECogau83g | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.31.1.12 | 41906138 | 41906124 | Start Up/Testing | 38 |  |  |  | day | 2024-09-27 07:00 | 2024-09-30 17:00 | [12 empty] | 11 | 7 | ZWntA9C8x0GfpqrA4xQutw | Ix9lBMUDlEeCtGZtBup1uw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32 | 41905664 | 41905607 | Level 34 | 45 |  |  |  | day | 2023-12-26 07:00 | 2024-11-07 17:00 | [12 empty] | 31 | 5 | erh5cT7ycUy4/dpFXIPdcA | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1 | 41906139 | 41905664 | Level 34 - Core | 28 |  |  |  | day | 2023-12-26 07:00 | 2024-10-16 17:00 | [12 empty] | 0 | 6 | xKDP3AXYIUai1b7ywbQJKA | erh5cT7ycUy4/dpFXIPdcA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.1 | 41906140 | 41906139 | Interior Summary & Milestones |  |  |  |  | day | 2023-12-26 07:00 | 2024-10-16 17:00 | [12 empty] | 0 | 7 | UIK1+y+m+ECQXIidi1narg | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.2 | 41906141 | 41906139 | Core Risers |  |  |  |  | day | 2024-04-19 07:00 | 2024-05-02 17:00 | [12 empty] | 1 | 7 | VP3Wdk4DOEa558REPxUrbw | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.3 | 41906142 | 41906139 | Layout, Critical Walls, Duct, Plumbing, FP | 43 |  |  |  | day | 2024-05-03 07:00 | 2024-06-14 17:00 | [12 empty] | 2 | 7 | Wd2Zm5h8QUGaALSje42w0g | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.4 | 41906143 | 41906139 | FA and Tele Data Rooms | 15 |  |  |  | day | 2024-05-10 07:00 | 2024-06-07 17:00 | [12 empty] | 3 | 7 | 8iE1AC4CskOrbJ+V8jn0vQ | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.4.1 | 41906144 | 41906143 | Tele Data |  |  |  |  | day | 2024-05-10 07:00 | 2024-06-03 17:00 | [12 empty] | 0 | 8 | R4rIvh0izE2FiexCDqUKYg | 8iE1AC4CskOrbJ+V8jn0vQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.4.2 | 41906145 | 41906143 | FA (Near ST1A) |  |  |  |  | day | 2024-05-14 07:00 | 2024-06-07 17:00 | [12 empty] | 1 | 8 | nbAox7IDHkKMj9Jbkz3jjQ | 8iE1AC4CskOrbJ+V8jn0vQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.5 | 41906146 | 41906139 | Framing |  |  |  |  | day | 2024-05-17 07:00 | 2024-06-14 17:00 | [12 empty] | 4 | 7 | f213itptBEi8e8iXc+bkNg | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.6 | 41906147 | 41906139 | In-Wall Rough | 29 |  |  |  | day | 2024-06-17 07:00 | 2024-06-27 17:00 | [12 empty] | 5 | 7 | zIKp2Pz9LUG3GTNsAUJOEA | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.7 | 41906148 | 41906139 | Inspections | 24 |  |  |  | day | 2024-06-24 07:00 | 2024-06-28 17:00 | [12 empty] | 6 | 7 | FqZcabWd8kOyBW2dZin3Tw | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.8 | 41906149 | 41906139 | Bathroom Finishes | 38 |  |  |  | day | 2024-07-01 07:00 | 2024-09-10 17:00 | [12 empty] | 7 | 7 | n1CYJROIzEyrfL6LgnzRBw | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.9 | 41906150 | 41906139 | Elevator Vestibule A - (SE-01,SE-02,SE-03) (PE-01,PE-02,PE-03) | 19 |  |  |  | day | 2024-07-11 07:00 | 2024-08-01 17:00 | [12 empty] | 8 | 7 | CKIOqkK60EK4xTIf8e3+cA | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.10 | 41906151 | 41906139 | Elevator Vestibule B - (PE-10--15) | 4 |  |  |  | day | 2024-07-15 07:00 | 2024-08-05 17:00 | [12 empty] | 9 | 7 | EP2+KlM+mU6itG17wpbxjw | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.11 | 41906152 | 41906139 | Worklist/Punchlist | 0 |  |  |  | day | 2024-09-11 07:00 | 2024-10-08 17:00 | [12 empty] | 10 | 7 | 3OAujAVrZ0Sq1kNzmVEbig | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.32.1.12 | 41906153 | 41906139 | Start Up/Testing | 29 |  |  |  | day | 2024-10-04 07:00 | 2024-10-07 17:00 | [12 empty] | 11 | 7 | tS4PkLOQcE2tBjnLuR1WxQ | xKDP3AXYIUai1b7ywbQJKA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.11.33 | 41905634 | 41905607 | Level 35 - Mechanical Rooms | 48 |  |  |  | day | 2024-02-29 07:00 | 2024-10-02 17:00 | [12 empty] | 32 | 5 | PVU7f9SUBUq6Zl9xdXQTbg | ZOM53F2XL0OCZjx9Q7JeVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12 | 41905448 | 41904236 | Tower Crane #1 Comeback |  |  |  |  | day | 2023-11-25 07:00 | 2024-09-27 17:00 | [12 empty] | 11 | 4 | RG/2Zj7DdEKtDB4eFSqbWg | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1 | 41905389 | 41905448 | TC#1 - Comeback - Structure | 44 |  |  |  | day | 2023-11-25 07:00 | 2024-02-29 17:00 | [12 empty] | 0 | 5 | Jo/0TQX6S0q11S0J/xl3nw | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.1 | 41905390 | 41905389 | Mech / P2, Mezz / P3, Sky, 10 |  |  |  |  | day | 2023-11-25 07:00 | 2024-01-09 17:00 | [12 empty] | 0 | 6 | Zug2Qf6bBkeblEjULcqfdw | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.2 | 41905391 | 41905389 | Lvl 11-13 | 29 |  |  |  | day | 2023-11-27 07:00 | 2024-01-15 17:00 | [12 empty] | 1 | 6 | jIg/igtVDE2pnaW5Byp2PA | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.3 | 41905392 | 41905389 | Lvl 12 |  |  |  |  | day | [14 empty] | 2 | 6 | rbk9p66p002u6tc+a/GbCA | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.4 | 41905393 | 41905389 | Lvl 13 | 3 |  |  |  | day | [14 empty] | 3 | 6 | GcpgQPV4wk+xOgFbu2+Cmw | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.5 | 41905394 | 41905389 | Lvl 14-16 | 17 |  |  |  | day | 2023-11-28 07:00 | 2024-01-19 17:00 | [12 empty] | 4 | 6 | 6EUxrbwoCE28nF0WBIlpew | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.6 | 41905395 | 41905389 | Lvl 15 | 36 |  |  |  | day | [14 empty] | 5 | 6 | ZDwrrmC/aUeDpuVdjH6k/A | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.7 | 41905396 | 41905389 | Lvl 16 | 24 |  |  |  | day | [14 empty] | 6 | 6 | xiceJjffk0O4dLJ6vrSmPw | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.8 | 41905397 | 41905389 | Lvl 17-19 | 47 |  |  |  | day | 2023-11-29 07:00 | 2024-01-25 17:00 | [12 empty] | 7 | 6 | PiQ3VXCKlEqHhwwnSOSXBA | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.9 | 41905398 | 41905389 | Lvl 18 | 0 |  |  |  | day | [14 empty] | 8 | 6 | dhW5HGB3GEi/2pIlTEq1Lg | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.10 | 41905399 | 41905389 | Lvl 19 | 45 |  |  |  | day | [14 empty] | 9 | 6 | 59fnjcp1UkSRcEOMzZg3ZQ | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.11 | 41905400 | 41905389 | Lvl 20-22 | 14 |  |  |  | day | 2023-11-30 07:00 | 2024-01-31 17:00 | [12 empty] | 10 | 6 | B2sKhOu+pkS7pflW3vGIFA | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.12 | 41905401 | 41905389 | Lvl 21 | 8 |  |  |  | day | [14 empty] | 11 | 6 | KkOf8fmwsUeSIiZZ6HgpBw | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.13 | 41905402 | 41905389 | Lvl 22 |  |  |  |  | day | [14 empty] | 12 | 6 | iljEj6gg+02oTU6Yu95iFQ | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.14 | 41905403 | 41905389 | Lvl 23-25 |  |  |  |  | day | 2023-12-01 07:00 | 2024-02-06 17:00 | [12 empty] | 13 | 6 | BAgh+UY9nkiAiPIMeWL8vA | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.15 | 41905404 | 41905389 | Lvl 24 | 23 |  |  |  | day | [14 empty] | 14 | 6 | DoM5hVHArEC4FZG83c8g2A | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.16 | 41905405 | 41905389 | Lvl 25 | 3 |  |  |  | day | [14 empty] | 15 | 6 | pvgF5sCuYkOwCy47jXJkCA | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.17 | 41905406 | 41905389 | Lvl 26-28 | 11 |  |  |  | day | 2023-12-01 07:00 | 2024-02-12 17:00 | [12 empty] | 16 | 6 | e3vQRF4v40iMvqvvOC0tIA | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.18 | 41905407 | 41905389 | Lvl 27 | 36 |  |  |  | day | [14 empty] | 17 | 6 | If6B9y8dBU2U2gvwAUwJDA | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.19 | 41905408 | 41905389 | Lvl 28 | 36 |  |  |  | day | [14 empty] | 18 | 6 | GM5/goUXU06qyzjg60vBng | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.20 | 41905409 | 41905389 | Lvl 29-31 |  |  |  |  | day | 2023-12-01 07:00 | 2024-02-16 17:00 | [12 empty] | 19 | 6 | 2o9cVzaUQUWmbw0IOGUwRg | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.21 | 41905410 | 41905389 | Lvl 30 |  |  |  |  | day | [14 empty] | 20 | 6 | u1pGFCJpJkmgT/1bWNbvGg | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.22 | 41905411 | 41905389 | Lvl 31 | 38 |  |  |  | day | [14 empty] | 21 | 6 | FCt48Il6VEOukgggyoZsnw | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.23 | 41905412 | 41905389 | Lvl 32-34 | 45 |  |  |  | day | 2023-12-01 07:00 | 2024-02-23 17:00 | [12 empty] | 22 | 6 | Tqww71R37kWpiijUlUOtTA | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.24 | 41905413 | 41905389 | Lvl 33 | 23 |  |  |  | day | [14 empty] | 23 | 6 | ugXQBtAbBkmWD3IS+H5b4w | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.25 | 41905414 | 41905389 | Lvl 34 |  |  |  |  | day | [14 empty] | 24 | 6 | fRexYyhBlEOpSIt7I+XgWA | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.26 | 41905415 | 41905389 | Lvl 35-36 | 12 |  |  |  | day | 2023-12-03 07:00 | 2024-02-29 17:00 | [12 empty] | 25 | 6 | CgBxR87m+EytuzpZ5MDEsg | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.1.27 | 41905416 | 41905389 | Lvl 36 | 33 |  |  |  | day | [14 empty] | 26 | 6 | tsIFlqVI3kysYEBqmoAJhA | Jo/0TQX6S0q11S0J/xl3nw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.2 | 41905450 | 41905448 | TC#1 - Comeback - Riser - Mech/P2 - Level 36 |  |  |  |  | day | 2024-01-22 07:00 | 2024-06-26 17:00 | [12 empty] | 1 | 5 | ou3PovjQJU6OKNyHLlH+Ew | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.2.1 | 41905451 | 41905450 | P2-10 | 6 |  |  |  | day | 2024-01-22 07:00 | 2024-03-04 17:00 | [12 empty] | 0 | 6 | JpZH/ORoEEafAN9lErw9RA | ou3PovjQJU6OKNyHLlH+Ew | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.2.2 | 41905452 | 41905450 | 2024-11-13 | 3 |  |  |  | day | 2024-02-05 07:00 | 2024-03-18 17:00 | [12 empty] | 1 | 6 | VF41VYNRz0CwSo97TRROFA | ou3PovjQJU6OKNyHLlH+Ew | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.2.3 | 41905453 | 41905450 | 14-16 | 7 |  |  |  | day | 2024-02-20 07:00 | 2024-04-01 17:00 | [12 empty] | 2 | 6 | d5hAd45toUaBC72tss1A0Q | ou3PovjQJU6OKNyHLlH+Ew | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.2.4 | 41905454 | 41905450 | 17-19 | 19 |  |  |  | day | 2024-03-05 07:00 | 2024-04-16 17:00 | [12 empty] | 3 | 6 | wPPoDJOm60mxypakjl4YUQ | ou3PovjQJU6OKNyHLlH+Ew | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.2.5 | 41905455 | 41905450 | 20-22 | 28 |  |  |  | day | 2024-03-19 07:00 | 2024-04-30 17:00 | [12 empty] | 4 | 6 | /ZB7HGQIME+OCBVGf1hLVA | ou3PovjQJU6OKNyHLlH+Ew | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.2.6 | 41905456 | 41905450 | 23-25 | 44 |  |  |  | day | 2024-04-02 07:00 | 2024-05-14 17:00 | [12 empty] | 5 | 6 | HLAdmTxym0WpCIQJj5RqqQ | ou3PovjQJU6OKNyHLlH+Ew | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.2.7 | 41905791 | 41905450 | 26-28 | 45 |  |  |  | day | 2024-04-17 07:00 | 2024-05-29 17:00 | [12 empty] | 6 | 6 | 9DIuaJzOPEm4HnuRjtWgyQ | ou3PovjQJU6OKNyHLlH+Ew | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.2.8 | 41905792 | 41905450 | 29-31 | 9 |  |  |  | day | 2024-05-01 07:00 | 2024-06-12 17:00 | [12 empty] | 7 | 6 | uu/rQ1x5V0W2MJj203M1yA | ou3PovjQJU6OKNyHLlH+Ew | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.2.9 | 41905793 | 41905450 | 32-34 | 42 |  |  |  | day | 2024-05-15 07:00 | 2024-06-26 17:00 | [12 empty] | 8 | 6 | gdz3CTiOdEmLu+Cz+pFy6w | ou3PovjQJU6OKNyHLlH+Ew | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.3 | 41905449 | 41905448 | TC#1 - Comeback - Level 10 - Mech-190 Elec-191 |  |  |  |  | day | 2024-03-05 07:00 | 2024-04-01 17:00 | [12 empty] | 2 | 5 | oJSvF5EWw0ekbuTMAgAizg | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.4 | 41905457 | 41905448 | TC#1 - Comeback - Level 11 - Mech-190 Elec-191 | 25 |  |  |  | day | 2024-03-19 07:00 | 2024-04-16 17:00 | [12 empty] | 3 | 5 | IZNjK1+b+EqSLlgm2GmzrA | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.5 | 41905458 | 41905448 | TC#1 - Comeback - Level 12 - Mech-190 Elec-191 | 40 |  |  |  | day | 2024-03-26 07:00 | 2024-04-23 17:00 | [12 empty] | 4 | 5 | ES++8q2SqkOzWZSDuyRSwA | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.6 | 41905459 | 41905448 | TC#1 - Comeback - Level 13 - Mech-190 Elec-191 | 48 |  |  |  | day | 2024-04-02 07:00 | 2024-04-30 17:00 | [12 empty] | 5 | 5 | 4sxW5O1HoEKQclzm8W28RQ | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.7 | 41905770 | 41905448 | TC#1 - Comeback - Level 14 - Mech-190 Elec-191 | 2 |  |  |  | day | 2024-04-09 07:00 | 2024-05-07 17:00 | [12 empty] | 6 | 5 | BAyuel49zky4iXaONpZ3Zg | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.8 | 41905771 | 41905448 | TC#1 - Comeback - Level 15 - Mech-190 Elec-191 | 5 |  |  |  | day | 2024-04-17 07:00 | 2024-05-14 17:00 | [12 empty] | 7 | 5 | BtDLw/jrwkyTtwfbMIzBfg | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.9 | 41905772 | 41905448 | TC#1 - Comeback - Level 16 - Mech-190 Elec-191 | 4 |  |  |  | day | 2024-04-24 07:00 | 2024-05-21 17:00 | [12 empty] | 8 | 5 | rwynlLari0aK+7zwGfKkRA | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.10 | 41905773 | 41905448 | TC#1 - Comeback - Level 17 - Mech-190 Elec-191 | 4 |  |  |  | day | 2024-05-01 07:00 | 2024-05-29 17:00 | [12 empty] | 9 | 5 | B6hjKGAVWk2SzvKkcZskWQ | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.11 | 41905774 | 41905448 | TC#1 - Comeback - Level 18 - Mech-190 Elec-191 | 46 |  |  |  | day | 2024-05-08 07:00 | 2024-06-05 17:00 | [12 empty] | 10 | 5 | Edu16CohB0mW0DSr37ufqg | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.12 | 41905775 | 41905448 | TC#1 - Comeback - Level 19 - Mech-190 Elec-191 |  |  |  |  | day | 2024-05-15 07:00 | 2024-06-12 17:00 | [12 empty] | 11 | 5 | AZqRSaEsAkukZ8s5uLxn7Q | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.13 | 41905776 | 41905448 | TC#1 - Comeback - Level 20 - Mech-190 Elec-191 | 48 |  |  |  | day | 2024-05-22 07:00 | 2024-06-19 17:00 | [12 empty] | 12 | 5 | DZcG45dH40e8XeumQx24ow | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.14 | 41905777 | 41905448 | TC#1 - Comeback - Level 21 - Mech-190 Elec-191 | 8 |  |  |  | day | 2024-05-30 07:00 | 2024-06-26 17:00 | [12 empty] | 13 | 5 | kUoUTao2+UezRMUsJivD9A | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.15 | 41905778 | 41905448 | TC#1 - Comeback - Level 22 - Mech-190 Elec-191 |  |  |  |  | day | 2024-06-06 07:00 | 2024-07-03 17:00 | [12 empty] | 14 | 5 | EpQcx5HA8Uy0dog5JEK7kw | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.16 | 41905779 | 41905448 | TC#1 - Comeback - Level 23 - Mech-190 Elec-191 |  |  |  |  | day | 2024-06-13 07:00 | 2024-07-11 17:00 | [12 empty] | 15 | 5 | iuJ/alJGoUqHlFc53ualvw | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.17 | 41905780 | 41905448 | TC#1 - Comeback - Level 24 - Mech-190 Elec-191 | 48 |  |  |  | day | 2024-06-20 07:00 | 2024-07-18 17:00 | [12 empty] | 16 | 5 | EO+5Dx/CGUe6CWgh0zL0ZQ | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.18 | 41905781 | 41905448 | TC#1 - Comeback - Level 25 - Mech-190 Elec-191 |  |  |  |  | day | 2024-06-27 07:00 | 2024-07-25 17:00 | [12 empty] | 17 | 5 | aE5PNCExo0OqQ5FlkoBarw | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.19 | 41905782 | 41905448 | TC#1 - Comeback - Level 26 - Mech-190 Elec-191 | 34 |  |  |  | day | 2024-07-05 07:00 | 2024-08-01 17:00 | [12 empty] | 18 | 5 | 0ajbAWHYhEeqHuwUEh8Ueg | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.20 | 41905783 | 41905448 | TC#1 - Comeback - Level 27 - Mech-190 Elec-191 | 49 |  |  |  | day | 2024-07-12 07:00 | 2024-08-08 17:00 | [12 empty] | 19 | 5 | xuHO0tyh8EyuSRV0fnHmIg | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.21 | 41905784 | 41905448 | TC#1 - Comeback - Level 28 - Mech-190 Elec-191 | 17 |  |  |  | day | 2024-07-19 07:00 | 2024-08-15 17:00 | [12 empty] | 20 | 5 | wBD0ihjaDESh44CVTOCDyg | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.22 | 41905785 | 41905448 | TC#1 - Comeback - Level 29 - Mech-190 Elec-191 |  |  |  |  | day | 2024-07-26 07:00 | 2024-08-22 17:00 | [12 empty] | 21 | 5 | zjTwFvWJp0S500njN1700A | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.23 | 41905786 | 41905448 | TC#1 - Comeback - Level 30 - Mech-190 Elec-191 | 23 |  |  |  | day | 2024-08-02 07:00 | 2024-08-29 17:00 | [12 empty] | 22 | 5 | 7KFfmz3e5keY7AD+rZi+Vw | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.24 | 41905787 | 41905448 | TC#1 - Comeback - Level 31 - Mech-190 Elec-191 |  |  |  |  | day | 2024-08-09 07:00 | 2024-09-06 17:00 | [12 empty] | 23 | 5 | Noi4ry0W7EqVy69ZetJfbw | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.25 | 41905788 | 41905448 | TC#1 - Comeback - Level 32 - Mech-190 Elec-191 | 31 |  |  |  | day | 2024-08-16 07:00 | 2024-09-13 17:00 | [12 empty] | 24 | 5 | kXub/Iuuw0S00VjYwGSZug | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.26 | 41905789 | 41905448 | TC#1 - Comeback - Level 33 - Mech-190 Elec-191 |  |  |  |  | day | 2024-08-23 07:00 | 2024-09-20 17:00 | [12 empty] | 25 | 5 | eYWTBUxvVU6PdQcvNqLgWg | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.12.27 | 41905790 | 41905448 | TC#1 - Comeback - Level 34 - Mech-190 Elec-191 | 37 |  |  |  | day | 2024-08-30 07:00 | 2024-09-27 17:00 | [12 empty] | 26 | 5 | pQb++PoYtkC1tX6rHDfjew | RG/2Zj7DdEKtDB4eFSqbWg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13 | 41905608 | 41904236 | Tower - Residential |  |  |  |  | day | 2023-12-26 07:00 | 2025-05-01 17:00 | [12 empty] | 12 | 4 | jYO7/2WAnky6Fktzlg2pzw | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1 | 41905610 | 41905608 | Level 36 - Residential Amenities | 46 |  |  |  | day | 2023-12-26 07:00 | 2025-01-09 17:00 | [12 empty] | 0 | 5 | gM/3buT9UkSUQ7saaW0Iqw | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.1 | 41906829 | 41905610 | Interior Summary & Milestones | 24 |  |  |  | day | 2023-12-26 07:00 | 2024-12-19 17:00 | [12 empty] | 0 | 6 | buqIr1IfnUyeoiDBqV4Qug | gM/3buT9UkSUQ7saaW0Iqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.2 | 43728976 | 41905610 | Roofing, Pool, Exterior Amenties | 8 |  |  |  | day | 2024-04-25 07:00 | 2024-05-31 17:00 | [12 empty] | 1 | 6 | dEBEJaT4KkeKDYnK5hgkmA | gM/3buT9UkSUQ7saaW0Iqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.2.1 | 43728977 | 43728976 | Pool | 3 |  |  |  | day | 2024-04-25 07:00 | 2024-05-28 17:00 | [12 empty] | 0 | 7 | MIxfGeinUUaN3S6lxxTgSg | dEBEJaT4KkeKDYnK5hgkmA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.2.2 | 43728978 | 43728976 | Crawl Space |  |  |  |  | day | 2024-05-17 07:00 | 2024-05-31 17:00 | [12 empty] | 1 | 7 | GC29CnTy5EivefE5amgdgg | dEBEJaT4KkeKDYnK5hgkmA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.3 | 41906830 | 41905610 | Roughs | 36 |  |  |  | day | 2024-04-25 07:00 | 2024-06-13 17:00 | [12 empty] | 2 | 6 | p6wRfHihVUy2OsGugQ4EGg | gM/3buT9UkSUQ7saaW0Iqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.3.1 | 41906831 | 41906830 | Facade - Curtainwall |  |  |  |  | day | [14 empty] | 0 | 7 | Fy5U51N5AEWOEG+j6zCJFA | p6wRfHihVUy2OsGugQ4EGg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.3.2 | 41906832 | 41906830 | Layout, Risers & Toptrack |  |  |  |  | day | 2024-04-25 07:00 | 2024-05-09 17:00 | [12 empty] | 1 | 7 | ZzWzhUH+cU2xwl89TY/Fcg | p6wRfHihVUy2OsGugQ4EGg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.3.3 | 41906833 | 41906830 | OH Rough | 40 |  |  |  | day | 2024-05-02 07:00 | 2024-05-21 17:00 | [12 empty] | 2 | 7 | ULQTw9kgRU+BDLqDfRnTGg | p6wRfHihVUy2OsGugQ4EGg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.3.4 | 41906834 | 41906830 | Heat Pumps | 2 |  |  |  | day | [14 empty] | 3 | 7 | r9JwLD2qjkG4iYLlo1WREQ | p6wRfHihVUy2OsGugQ4EGg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.3.5 | 41906835 | 41906830 | Framing | 27 |  |  |  | day | 2024-05-10 07:00 | 2024-06-11 17:00 | [12 empty] | 4 | 7 | TvjMdd1HkkKktsoANndNIw | p6wRfHihVUy2OsGugQ4EGg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.3.6 | 41906836 | 41906830 | In-Wall Rough | 28 |  |  |  | day | 2024-05-24 07:00 | 2024-06-12 17:00 | [12 empty] | 5 | 7 | E734jp3AcE68KGg8Ifi1fA | p6wRfHihVUy2OsGugQ4EGg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.3.7 | 41906837 | 41906830 | Inspections | 8 |  |  |  | day | 2024-06-10 07:00 | 2024-06-13 17:00 | [12 empty] | 6 | 7 | Vw4LKDTOJUm70Klmhc8ATQ | p6wRfHihVUy2OsGugQ4EGg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.4 | 41906838 | 41905610 | Unit Finishes |  |  |  |  | day | 2024-06-14 07:00 | 2024-12-19 17:00 | [12 empty] | 3 | 6 | rDv180GySUaYV6SUlkGhPA | gM/3buT9UkSUQ7saaW0Iqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.4.1 | 41906839 | 41906838 | Drywall |  |  |  |  | day | 2024-06-14 07:00 | 2024-07-17 17:00 | [12 empty] | 0 | 7 | Rg1vUhrUHEy6rc43T0rFPA | rDv180GySUaYV6SUlkGhPA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.4.2 | 41906840 | 41906838 | Bathroom Waterproofing | 33 |  |  |  | day | 2024-06-17 07:00 | 2024-07-18 17:00 | [12 empty] | 1 | 7 | yHCpVw0hxUSfFTgCNgMuvw | rDv180GySUaYV6SUlkGhPA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.4.3 | 41906841 | 41906838 | Paint | 11 |  |  |  | day | 2024-07-18 07:00 | 2024-08-01 17:00 | [12 empty] | 2 | 7 | wFFjh4QNVUGR2Fq/4Cs7RA | rDv180GySUaYV6SUlkGhPA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.4.4 | 41906842 | 41906838 | Tile | 41 |  |  |  | day | 2024-08-02 07:00 | 2024-08-28 17:00 | [12 empty] | 3 | 7 | K0n8y61zrkiXbjNkiFpuSA | rDv180GySUaYV6SUlkGhPA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.4.5 | 41906843 | 41906838 | Wood Flooring | 8 |  |  |  | day | 2024-08-29 07:00 | 2024-09-12 17:00 | [12 empty] | 4 | 7 | uWTbsuwJZ0ek7XHjLqrulA | rDv180GySUaYV6SUlkGhPA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.4.6 | 41906844 | 41906838 | Casework |  |  |  |  | day | 2024-09-13 07:00 | 2024-10-17 17:00 | [12 empty] | 5 | 7 | IJtteIVnRU6+to5VI1/nLg | rDv180GySUaYV6SUlkGhPA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.4.7 | 41906845 | 41906838 | MEP Finishes | 39 |  |  |  | day | 2024-10-10 07:00 | 2024-11-04 17:00 | [12 empty] | 6 | 7 | zNgeXWvugUGjr8Hj8yuH9Q | rDv180GySUaYV6SUlkGhPA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.4.8 | 41906846 | 41906838 | Doors & Trim |  |  |  |  | day | 2024-09-27 07:00 | 2024-11-05 17:00 | [12 empty] | 7 | 7 | 3S2lOSj4UE+ScBAVtude+w | rDv180GySUaYV6SUlkGhPA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.4.9 | 41906847 | 41906838 | Finish Paint | 4 |  |  |  | day | 2024-10-30 07:00 | 2024-11-05 17:00 | [12 empty] | 8 | 7 | z2bnRaZkOEudRqzZbIU5Zw | rDv180GySUaYV6SUlkGhPA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.4.10 | 41906848 | 41906838 | Worklist/Punchlist | 10 |  |  |  | day | 2024-11-06 07:00 | 2024-12-19 17:00 | [12 empty] | 9 | 7 | ESVK9rppV0Wm5FlDBJJZ/w | rDv180GySUaYV6SUlkGhPA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.5 | 41906849 | 41905610 | Corridors Finishes |  |  |  |  | day | 2024-06-28 07:00 | 2025-01-09 17:00 | [12 empty] | 4 | 6 | rwFCtF1bqEy0oUBICnMQzQ | gM/3buT9UkSUQ7saaW0Iqw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.5.1 | 41906850 | 41906849 | Drywall |  |  |  |  | day | 2024-06-28 07:00 | 2024-07-12 17:00 | [12 empty] | 0 | 7 | CIWnU47MrUWwlV6UXaA6IQ | rwFCtF1bqEy0oUBICnMQzQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.5.2 | 41906851 | 41906849 | Finishes | 14 |  |  |  | day | 2024-07-25 07:00 | 2024-11-27 17:00 | [12 empty] | 1 | 7 | YonCcgIKJECSjxobhVuHSA | rwFCtF1bqEy0oUBICnMQzQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.5.3 | 41906852 | 41906849 | Elevator Vestibule - SE2 | 37 |  |  |  | day | 2024-07-08 07:00 | 2024-07-29 17:00 | [12 empty] | 2 | 7 | yrrbUN+KcE6djRwX9GQZYg | rwFCtF1bqEy0oUBICnMQzQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.5.4 | 41906853 | 41906849 | Elevator Vestibule - PE01,02,03 | 7 |  |  |  | day | 2024-07-10 07:00 | 2024-08-21 17:00 | [12 empty] | 3 | 7 | 0xNRtr9n9Ua4fwAIBfx9UA | rwFCtF1bqEy0oUBICnMQzQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.1.5.5 | 41906854 | 41906849 | Worklist/Punchlist |  |  |  |  | day | 2024-11-29 07:00 | 2025-01-09 17:00 | [12 empty] | 4 | 7 | BdtXdPDtcEuDN2N6FUz1vA | rwFCtF1bqEy0oUBICnMQzQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2 | 41905609 | 41905608 | Level 37 - Residential Units | 47 |  |  |  | day | 2024-01-24 07:00 | 2025-01-17 17:00 | [12 empty] | 1 | 5 | eKwSp1Rkq0uHCXnN78vXNQ | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.1 | 41906257 | 41905609 | Interior Summary & Milestones | 25 |  |  |  | day | 2024-01-24 07:00 | 2024-12-30 17:00 | [12 empty] | 0 | 6 | b85KHqMD1UKub2p+4qoJMA | eKwSp1Rkq0uHCXnN78vXNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.2 | 41906234 | 41905609 | Roughs | 17 |  |  |  | day | 2024-05-03 07:00 | 2024-06-21 17:00 | [12 empty] | 1 | 6 | xWwU4263bUSQIgvIpHkETg | eKwSp1Rkq0uHCXnN78vXNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.2.1 | 41906235 | 41906234 | Facade - Curtainwall | 5 |  |  |  | day | [14 empty] | 0 | 7 | nj3pAXd3eUi8h0j4A/qYMw | xWwU4263bUSQIgvIpHkETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.2.2 | 41906236 | 41906234 | Layout, Risers & Toptrack | 36 |  |  |  | day | 2024-05-03 07:00 | 2024-05-17 17:00 | [12 empty] | 1 | 7 | m+A5PXOLgU6aJ7Ml70QiVw | xWwU4263bUSQIgvIpHkETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.2.3 | 41906237 | 41906234 | OH Rough | 47 |  |  |  | day | 2024-05-10 07:00 | 2024-05-30 17:00 | [12 empty] | 2 | 7 | sT+gqSKJ+Uar+ZcGoUs8Mw | xWwU4263bUSQIgvIpHkETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.2.4 | 41906238 | 41906234 | Heat Pumps |  |  |  |  | day | [14 empty] | 3 | 7 | jS4rzDBRmEKKZTfNS2aV6g | xWwU4263bUSQIgvIpHkETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.2.5 | 41906239 | 41906234 | Framing |  |  |  |  | day | 2024-05-20 07:00 | 2024-06-19 17:00 | [12 empty] | 4 | 7 | c3qahUjsr0mNt9QHDrwnrw | xWwU4263bUSQIgvIpHkETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.2.6 | 41906240 | 41906234 | In-Wall Rough | 4 |  |  |  | day | 2024-06-04 07:00 | 2024-06-20 17:00 | [12 empty] | 5 | 7 | Br/Czka4o0S94TFSlt+knw | xWwU4263bUSQIgvIpHkETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.2.7 | 41906241 | 41906234 | Inspections | 12 |  |  |  | day | 2024-06-18 07:00 | 2024-06-21 17:00 | [12 empty] | 6 | 7 | rX1L0TOOgkuIKDk8K0LTFA | xWwU4263bUSQIgvIpHkETg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.3 | 41906242 | 41905609 | Unit Finishes | 16 |  |  |  | day | 2024-06-24 07:00 | 2024-12-30 17:00 | [12 empty] | 2 | 6 | PG3FUS/6t0y2ePUiOsJQUQ | eKwSp1Rkq0uHCXnN78vXNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.3.1 | 41906243 | 41906242 | Drywall |  |  |  |  | day | 2024-06-24 07:00 | 2024-07-25 17:00 | [12 empty] | 0 | 7 | fJSdWC9KME6LuIl13qFngA | PG3FUS/6t0y2ePUiOsJQUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.3.2 | 41906244 | 41906242 | Bathroom Waterproofing | 39 |  |  |  | day | 2024-06-25 07:00 | 2024-07-26 17:00 | [12 empty] | 1 | 7 | w8tiHOZw50idsMQ7Ebgqtg | PG3FUS/6t0y2ePUiOsJQUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.3.3 | 41906245 | 41906242 | Paint | 44 |  |  |  | day | 2024-07-26 07:00 | 2024-08-09 17:00 | [12 empty] | 2 | 7 | UKK1P2+6y0mR75MRXp7v7A | PG3FUS/6t0y2ePUiOsJQUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.3.4 | 41906246 | 41906242 | Tile | 31 |  |  |  | day | 2024-08-12 07:00 | 2024-09-06 17:00 | [12 empty] | 3 | 7 | HL8KLaYnMkWr/3l4+Lz+Cg | PG3FUS/6t0y2ePUiOsJQUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.3.5 | 41906259 | 41906242 | Wood Flooring |  |  |  |  | day | 2024-09-09 07:00 | 2024-09-20 17:00 | [12 empty] | 4 | 7 | yqYxDJrRaU63to8rhCdwig | PG3FUS/6t0y2ePUiOsJQUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.3.6 | 41906247 | 41906242 | Casework | 2 |  |  |  | day | 2024-09-23 07:00 | 2024-10-25 17:00 | [12 empty] | 5 | 7 | F1BHy+Sz0USgXtFGiK0FWQ | PG3FUS/6t0y2ePUiOsJQUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.3.7 | 41906248 | 41906242 | MEP Finishes | 39 |  |  |  | day | 2024-10-21 07:00 | 2024-11-13 17:00 | [12 empty] | 6 | 7 | y2Gb9PWWmEG7/qs7EN18Eg | PG3FUS/6t0y2ePUiOsJQUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.3.8 | 41906249 | 41906242 | Doors & Trim | 33 |  |  |  | day | 2024-10-07 07:00 | 2024-11-14 17:00 | [12 empty] | 7 | 7 | Q/9nrb25BUqc1Kf5rNMtBg | PG3FUS/6t0y2ePUiOsJQUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.3.9 | 41906250 | 41906242 | Finish Paint |  |  |  |  | day | 2024-11-07 07:00 | 2024-11-14 17:00 | [12 empty] | 8 | 7 | QVnJEeBwk0qzU/OCciRbwQ | PG3FUS/6t0y2ePUiOsJQUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.3.10 | 41906251 | 41906242 | Worklist/Punchlist |  |  |  |  | day | 2024-11-15 07:00 | 2024-12-30 17:00 | [12 empty] | 9 | 7 | 810aKAaN9UaTL4gXEtEEmA | PG3FUS/6t0y2ePUiOsJQUQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.4 | 41906252 | 41905609 | Corridors Finishes | 12 |  |  |  | day | 2024-07-09 07:00 | 2025-01-17 17:00 | [12 empty] | 3 | 6 | vejXNGO8OkCJx6eutpZbDw | eKwSp1Rkq0uHCXnN78vXNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.4.1 | 41906253 | 41906252 | Drywall |  |  |  |  | day | 2024-07-09 07:00 | 2024-07-22 17:00 | [12 empty] | 0 | 7 | 49aENn/VzUKy8RUgK9RWog | vejXNGO8OkCJx6eutpZbDw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.4.2 | 41906254 | 41906252 | Finishes |  |  |  |  | day | 2024-08-02 07:00 | 2024-12-06 17:00 | [12 empty] | 1 | 7 | Kvc4yRQNBkOUKPNT9XZnIw | vejXNGO8OkCJx6eutpZbDw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.4.3 | 41906255 | 41906252 | Elevator Vestibule - SE2 | 5 |  |  |  | day | 2024-07-16 07:00 | 2024-08-06 17:00 | [12 empty] | 2 | 7 | Ina6oGfcYEeOMGl71lAwGw | vejXNGO8OkCJx6eutpZbDw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.4.4 | 41906258 | 41906252 | Elevator Vestibule - PE01,02,03 | 23 |  |  |  | day | 2024-07-18 07:00 | 2024-08-29 17:00 | [12 empty] | 3 | 7 | NwZxkRtArEi3PUkda5yu8A | vejXNGO8OkCJx6eutpZbDw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.2.4.5 | 41906256 | 41906252 | Worklist/Punchlist | 18 |  |  |  | day | 2024-12-09 07:00 | 2025-01-17 17:00 | [12 empty] | 4 | 7 | ayIDL+HKC0iBcLd0q8QxAA | vejXNGO8OkCJx6eutpZbDw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3 | 41905611 | 41905608 | Level 38 - Residential Units |  |  |  |  | day | 2024-02-01 07:00 | 2025-01-27 17:00 | [12 empty] | 2 | 5 | 9v+1is5dXEK9bPUOA/NSJA | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.1 | 41906260 | 41905611 | Interior Summary & Milestones | 39 |  |  |  | day | 2024-02-01 07:00 | 2025-01-08 17:00 | [12 empty] | 0 | 6 | OdYVJyISsECjmT4BgUopIw | 9v+1is5dXEK9bPUOA/NSJA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.2 | 41906261 | 41905611 | Roughs | 27 |  |  |  | day | 2024-05-13 07:00 | 2024-07-01 17:00 | [12 empty] | 1 | 6 | gYT/w8S5nkeClc/UDANaRA | 9v+1is5dXEK9bPUOA/NSJA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.2.1 | 41906262 | 41906261 | Facade - Curtainwall | 32 |  |  |  | day | [14 empty] | 0 | 7 | Ck1W4if7OUy9W8u/Zo1mvA | gYT/w8S5nkeClc/UDANaRA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.2.2 | 41906263 | 41906261 | Layout, Risers & Toptrack |  |  |  |  | day | 2024-05-13 07:00 | 2024-05-28 17:00 | [12 empty] | 1 | 7 | 5CIJVrIajEa6bF/02xHBCA | gYT/w8S5nkeClc/UDANaRA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.2.3 | 41906264 | 41906261 | OH Rough |  |  |  |  | day | 2024-05-20 07:00 | 2024-06-07 17:00 | [12 empty] | 2 | 7 |  | gYT/w8S5nkeClc/UDANaRA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.2.4 | 41906265 | 41906261 | Heat Pumps | 12 |  |  |  | day | [14 empty] | 3 | 7 | Zx8Bbd1aC0a6RTC2UVuWHA | gYT/w8S5nkeClc/UDANaRA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.2.5 | 41906266 | 41906261 | Framing | 42 |  |  |  | day | 2024-05-29 07:00 | 2024-06-27 17:00 | [12 empty] | 4 | 7 | 0ykgRP8ulkijknxGmjsYRQ | gYT/w8S5nkeClc/UDANaRA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.2.6 | 41906267 | 41906261 | In-Wall Rough |  |  |  |  | day | 2024-06-12 07:00 | 2024-06-28 17:00 | [12 empty] | 5 | 7 | Cb7EXpMGcEqKS2jh/9wtXg | gYT/w8S5nkeClc/UDANaRA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.2.7 | 41906268 | 41906261 | Inspections | 24 |  |  |  | day | 2024-06-26 07:00 | 2024-07-01 17:00 | [12 empty] | 6 | 7 | rxxngyrnD0mMDRqdjZum0g | gYT/w8S5nkeClc/UDANaRA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.3 | 41906269 | 41905611 | Unit Finishes | 41 |  |  |  | day | 2024-07-02 07:00 | 2025-01-08 17:00 | [12 empty] | 2 | 6 | c6H6R9yf00SXc+D0dT/HOA | 9v+1is5dXEK9bPUOA/NSJA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.3.1 | 41906270 | 41906269 | Drywall |  |  |  |  | day | 2024-07-02 07:00 | 2024-08-02 17:00 | [12 empty] | 0 | 7 | EvVlhV4aiUahnDwcPdvPhg | c6H6R9yf00SXc+D0dT/HOA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.3.2 | 41906271 | 41906269 | Bathroom Waterproofing | 26 |  |  |  | day | 2024-07-03 07:00 | 2024-08-05 17:00 | [12 empty] | 1 | 7 | FW6tF1ORx06qd9gpcEyNwQ | c6H6R9yf00SXc+D0dT/HOA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.3.3 | 41906272 | 41906269 | Paint |  |  |  |  | day | 2024-08-05 07:00 | 2024-08-19 17:00 | [12 empty] | 2 | 7 | cW6KgeFcskGKNy+CbPpmwQ | c6H6R9yf00SXc+D0dT/HOA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.3.4 | 41906273 | 41906269 | Tile | 6 |  |  |  | day | 2024-08-20 07:00 | 2024-09-16 17:00 | [12 empty] | 3 | 7 | 6Xyuz4CfnE+CyGzK26xx3g | c6H6R9yf00SXc+D0dT/HOA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.3.5 | 41906274 | 41906269 | Wood Flooring | 4 |  |  |  | day | 2024-09-17 07:00 | 2024-09-30 17:00 | [12 empty] | 4 | 7 | WK+jMCLNkUq68pnaRjHOGQ | c6H6R9yf00SXc+D0dT/HOA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.3.6 | 41906275 | 41906269 | Casework | 42 |  |  |  | day | 2024-10-01 07:00 | 2024-11-04 17:00 | [12 empty] | 5 | 7 | v7FiahTpw0uKXRPYztpCcA | c6H6R9yf00SXc+D0dT/HOA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.3.7 | 41906276 | 41906269 | MEP Finishes | 44 |  |  |  | day | 2024-10-29 07:00 | 2024-11-21 17:00 | [12 empty] | 6 | 7 | FkcktmH3mUSnNWTWy1geEQ | c6H6R9yf00SXc+D0dT/HOA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.3.8 | 41906277 | 41906269 | Doors & Trim | 30 |  |  |  | day | 2024-10-16 07:00 | 2024-11-22 17:00 | [12 empty] | 7 | 7 | rxl4YDAlhk+nZ42xdmfMJQ | c6H6R9yf00SXc+D0dT/HOA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.3.9 | 41906278 | 41906269 | Finish Paint | 22 |  |  |  | day | 2024-11-18 07:00 | 2024-11-22 17:00 | [12 empty] | 8 | 7 | SmhgvzUAYEW9kRr+Xl2n0g | c6H6R9yf00SXc+D0dT/HOA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.3.10 | 41906279 | 41906269 | Worklist/Punchlist | 41 |  |  |  | day | 2024-11-25 07:00 | 2025-01-08 17:00 | [12 empty] | 9 | 7 | W6Wgmca/P0Ktu2IK2ZUrQQ | c6H6R9yf00SXc+D0dT/HOA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.4 | 41906280 | 41905611 | Corridors Finishes | 9 |  |  |  | day | 2024-07-17 07:00 | 2025-01-27 17:00 | [12 empty] | 3 | 6 | CJ4vnF+upkqxPGeV2AakbQ | 9v+1is5dXEK9bPUOA/NSJA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.4.1 | 41906281 | 41906280 | Drywall | 31 |  |  |  | day | 2024-07-17 07:00 | 2024-07-30 17:00 | [12 empty] | 0 | 7 | ccrZe6u2Mkm3GZc37q/gvw | CJ4vnF+upkqxPGeV2AakbQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.4.2 | 41906282 | 41906280 | Finishes |  |  |  |  | day | 2024-08-12 07:00 | 2024-12-16 17:00 | [12 empty] | 1 | 7 | wqJQs4Y2S06wGh6TJbzJ/w | CJ4vnF+upkqxPGeV2AakbQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.4.3 | 41906283 | 41906280 | Elevator Vestibule - SE2 | 29 |  |  |  | day | 2024-07-24 07:00 | 2024-08-14 17:00 | [12 empty] | 2 | 7 | vqGxa4Xk20a95b3Ggsjz4A | CJ4vnF+upkqxPGeV2AakbQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.4.4 | 41906284 | 41906280 | Elevator Vestibule - PE01,02,03 |  |  |  |  | day | 2024-07-26 07:00 | 2024-09-09 17:00 | [12 empty] | 3 | 7 | HiF5CTT7GEy/K1bVC5UkLg | CJ4vnF+upkqxPGeV2AakbQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.3.4.5 | 41906285 | 41906280 | Worklist/Punchlist | 30 |  |  |  | day | 2024-12-17 07:00 | 2025-01-27 17:00 | [12 empty] | 4 | 7 | QAV9T2zttk24sn5DKqrjtw | CJ4vnF+upkqxPGeV2AakbQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4 | 41905612 | 41905608 | Level 39 - Residential Units | 17 |  |  |  | day | 2024-02-09 07:00 | 2025-02-04 17:00 | [12 empty] | 3 | 5 | j2mc9PnyWk+blBx4waoJ+w | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.1 | 41906286 | 41905612 | Interior Summary & Milestones | 35 |  |  |  | day | 2024-02-09 07:00 | 2025-01-16 17:00 | [12 empty] | 0 | 6 | lJJxK/r5VEO/5HPqUVNk8Q | j2mc9PnyWk+blBx4waoJ+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.2 | 41906287 | 41905612 | Roughs | 1 |  |  |  | day | 2024-05-21 07:00 | 2024-07-10 17:00 | [12 empty] | 1 | 6 | QqDwYwmLf0ya4nth9+yA5g | j2mc9PnyWk+blBx4waoJ+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.2.1 | 41906288 | 41906287 | Facade - Curtainwall | 13 |  |  |  | day | [14 empty] | 0 | 7 | QJAmXBc9pEu88yCmhMUQgw | QqDwYwmLf0ya4nth9+yA5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.2.2 | 41906289 | 41906287 | Layout, Risers & Toptrack |  |  |  |  | day | 2024-05-21 07:00 | 2024-06-05 17:00 | [12 empty] | 1 | 7 | QFsw79iErE6Iy9oeTJQufg | QqDwYwmLf0ya4nth9+yA5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.2.3 | 41906290 | 41906287 | OH Rough |  |  |  |  | day | 2024-05-29 07:00 | 2024-06-17 17:00 | [12 empty] | 2 | 7 | Ms2gAR9ryUuZh7DRfC1hHg | QqDwYwmLf0ya4nth9+yA5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.2.4 | 41906291 | 41906287 | Heat Pumps | 11 |  |  |  | day | [14 empty] | 3 | 7 | kjgsF6z5lkONcYJXxJDZfQ | QqDwYwmLf0ya4nth9+yA5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.2.5 | 41906292 | 41906287 | Framing |  |  |  |  | day | 2024-06-06 07:00 | 2024-07-08 17:00 | [12 empty] | 4 | 7 | 1As4UlNKxEG8IybLI8IIHg | QqDwYwmLf0ya4nth9+yA5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.2.6 | 41906293 | 41906287 | In-Wall Rough | 1 |  |  |  | day | 2024-06-20 07:00 | 2024-07-09 17:00 | [12 empty] | 5 | 7 | 9csCh9ZPVE+5RdR4Z0cvEA | QqDwYwmLf0ya4nth9+yA5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.2.7 | 41906294 | 41906287 | Inspections | 31 |  |  |  | day | 2024-07-05 07:00 | 2024-07-10 17:00 | [12 empty] | 6 | 7 | kdAK6YzW9U+wMM/4bcRsfA | QqDwYwmLf0ya4nth9+yA5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.3 | 41906295 | 41905612 | Unit Finishes | 12 |  |  |  | day | 2024-07-11 07:00 | 2025-01-16 17:00 | [12 empty] | 2 | 6 | yja2+mdUh0WOi04zutnVnA | j2mc9PnyWk+blBx4waoJ+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.3.1 | 41906296 | 41906295 | Drywall | 45 |  |  |  | day | 2024-07-11 07:00 | 2024-08-12 17:00 | [12 empty] | 0 | 7 | qOPsGlsEyU222P4adQZQSQ | yja2+mdUh0WOi04zutnVnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.3.2 | 41906297 | 41906295 | Bathroom Waterproofing | 26 |  |  |  | day | 2024-07-12 07:00 | 2024-08-13 17:00 | [12 empty] | 1 | 7 | VhksqJBuU0CMwHROlJ3/Lw | yja2+mdUh0WOi04zutnVnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.3.3 | 41906298 | 41906295 | Paint | 48 |  |  |  | day | 2024-08-13 07:00 | 2024-08-27 17:00 | [12 empty] | 2 | 7 | widR+tWJyE2MYlp0PFCNWw | yja2+mdUh0WOi04zutnVnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.3.4 | 41906299 | 41906295 | Tile | 40 |  |  |  | day | 2024-08-28 07:00 | 2024-09-24 17:00 | [12 empty] | 3 | 7 | xTymx+OfSEyjCUk4u1Xp0g | yja2+mdUh0WOi04zutnVnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.3.5 | 41906300 | 41906295 | Wood Flooring | 16 |  |  |  | day | 2024-09-25 07:00 | 2024-10-08 17:00 | [12 empty] | 4 | 7 | NsPnTwrmN0G5LBTU32T5gA | yja2+mdUh0WOi04zutnVnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.3.6 | 41906301 | 41906295 | Casework | 39 |  |  |  | day | 2024-10-09 07:00 | 2024-11-13 17:00 | [12 empty] | 5 | 7 | qbldP+k1Tkiu4Gl7ve6czA | yja2+mdUh0WOi04zutnVnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.3.7 | 41906302 | 41906295 | MEP Finishes | 30 |  |  |  | day | 2024-11-06 07:00 | 2024-12-02 17:00 | [12 empty] | 6 | 7 | yUs1+mQ3kk6q+VGiLZ7hfg | yja2+mdUh0WOi04zutnVnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.3.8 | 41906303 | 41906295 | Doors & Trim | 33 |  |  |  | day | 2024-10-24 07:00 | 2024-12-03 17:00 | [12 empty] | 7 | 7 | /uAXDokWS0q1EyhaGsupSA | yja2+mdUh0WOi04zutnVnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.3.9 | 41906304 | 41906295 | Finish Paint | 23 |  |  |  | day | 2024-11-26 07:00 | 2024-12-03 17:00 | [12 empty] | 8 | 7 | LcKZDZJEl0moVig1nRzpCA | yja2+mdUh0WOi04zutnVnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.3.10 | 41906305 | 41906295 | Worklist/Punchlist |  |  |  |  | day | 2024-12-04 07:00 | 2025-01-16 17:00 | [12 empty] | 9 | 7 | fAkbPkXvgkiGYDKaZLZq+g | yja2+mdUh0WOi04zutnVnA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.4 | 41906306 | 41905612 | Corridors Finishes |  |  |  |  | day | 2024-07-25 07:00 | 2025-02-04 17:00 | [12 empty] | 3 | 6 | UGFaqkKgtUKCFPLx6qG0Kg | j2mc9PnyWk+blBx4waoJ+w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.4.1 | 41906307 | 41906306 | Drywall | 47 |  |  |  | day | 2024-07-25 07:00 | 2024-08-07 17:00 | [12 empty] | 0 | 7 | rd471KQaEUChOfGnpo5WZg | UGFaqkKgtUKCFPLx6qG0Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.4.2 | 41906308 | 41906306 | Finishes | 5 |  |  |  | day | 2024-08-20 07:00 | 2024-12-24 17:00 | [12 empty] | 1 | 7 | IMN0gUtPKEuXOl/t/5nUcg | UGFaqkKgtUKCFPLx6qG0Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.4.3 | 41906309 | 41906306 | Elevator Vestibule - SE2 | 18 |  |  |  | day | 2024-08-01 07:00 | 2024-08-22 17:00 | [12 empty] | 2 | 7 | qCABsIWFY0S24tVctKT+tA | UGFaqkKgtUKCFPLx6qG0Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.4.4 | 41906310 | 41906306 | Elevator Vestibule - PE01,02,03 | 29 |  |  |  | day | 2024-08-05 07:00 | 2024-09-17 17:00 | [12 empty] | 3 | 7 | Y0PzI2CUQUWjCxOcgTS1xA | UGFaqkKgtUKCFPLx6qG0Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.4.4.5 | 41906311 | 41906306 | Worklist/Punchlist | 6 |  |  |  | day | 2024-12-26 07:00 | 2025-02-04 17:00 | [12 empty] | 4 | 7 | GTJtk6ItVk+SfLax5wE4LA | UGFaqkKgtUKCFPLx6qG0Kg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5 | 41905613 | 41905608 | Level 40 - Residential Units |  |  |  |  | day | 2024-02-16 07:00 | 2025-02-12 17:00 | [12 empty] | 4 | 5 | CRtIUmaLE0mkRjepHv3E9g | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.1 | 41906312 | 41905613 | Interior Summary & Milestones | 40 |  |  |  | day | 2024-02-16 07:00 | 2025-01-24 17:00 | [12 empty] | 0 | 6 | qIGBHyFcQUKlqvtqq2N5lg | CRtIUmaLE0mkRjepHv3E9g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.2 | 41906313 | 41905613 | Roughs | 31 |  |  |  | day | 2024-05-30 07:00 | 2024-07-18 17:00 | [12 empty] | 1 | 6 | kRWNHD5yyE+kfsL528x/Xw | CRtIUmaLE0mkRjepHv3E9g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.2.1 | 41906314 | 41906313 | Facade - Curtainwall | 33 |  |  |  | day | [14 empty] | 0 | 7 | rvbfrRANBUqMBeRKK1WFEA | kRWNHD5yyE+kfsL528x/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.2.2 | 41906315 | 41906313 | Layout, Risers & Toptrack |  |  |  |  | day | 2024-05-30 07:00 | 2024-06-13 17:00 | [12 empty] | 1 | 7 | 7/EgfjbnukCkjJqeh7sgNg | kRWNHD5yyE+kfsL528x/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.2.3 | 41906316 | 41906313 | OH Rough | 14 |  |  |  | day | 2024-06-06 07:00 | 2024-06-25 17:00 | [12 empty] | 2 | 7 | 5YjpL3c/90Gywr97nm7OPQ | kRWNHD5yyE+kfsL528x/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.2.4 | 41906317 | 41906313 | Heat Pumps | 29 |  |  |  | day | [14 empty] | 3 | 7 | oag3BMG/u0ydUEQ8vwwwHA | kRWNHD5yyE+kfsL528x/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.2.5 | 41906318 | 41906313 | Framing | 36 |  |  |  | day | 2024-06-14 07:00 | 2024-07-16 17:00 | [12 empty] | 4 | 7 |  | kRWNHD5yyE+kfsL528x/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.2.6 | 41906319 | 41906313 | In-Wall Rough | 28 |  |  |  | day | 2024-06-28 07:00 | 2024-07-17 17:00 | [12 empty] | 5 | 7 | PwZC+AKYd0Gc7IbAEKdAlA | kRWNHD5yyE+kfsL528x/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.2.7 | 41906320 | 41906313 | Inspections | 21 |  |  |  | day | 2024-07-15 07:00 | 2024-07-18 17:00 | [12 empty] | 6 | 7 | 82CzYNyavkq6tXM+w1C6cg | kRWNHD5yyE+kfsL528x/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.3 | 41906321 | 41905613 | Unit Finishes |  |  |  |  | day | 2024-07-19 07:00 | 2025-01-24 17:00 | [12 empty] | 2 | 6 | 3wwqebUhTkWtWt7SFPuIhQ | CRtIUmaLE0mkRjepHv3E9g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.3.1 | 41906322 | 41906321 | Drywall | 19 |  |  |  | day | 2024-07-19 07:00 | 2024-08-20 17:00 | [12 empty] | 0 | 7 |  | 3wwqebUhTkWtWt7SFPuIhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.3.2 | 41906323 | 41906321 | Bathroom Waterproofing |  |  |  |  | day | 2024-07-22 07:00 | 2024-08-21 17:00 | [12 empty] | 1 | 7 | qq2rhw6cp0qC5CQHTxO8UA | 3wwqebUhTkWtWt7SFPuIhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.3.3 | 41906324 | 41906321 | Paint | 35 |  |  |  | day | 2024-08-21 07:00 | 2024-09-05 17:00 | [12 empty] | 2 | 7 | 2RhHILRamkSkLAMK2A9e+w | 3wwqebUhTkWtWt7SFPuIhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.3.4 | 41906325 | 41906321 | Tile |  |  |  |  | day | 2024-09-06 07:00 | 2024-10-02 17:00 | [12 empty] | 3 | 7 | XoXZ+0pV6U+6GVyScbZ1rA | 3wwqebUhTkWtWt7SFPuIhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.3.5 | 41906326 | 41906321 | Wood Flooring |  |  |  |  | day | 2024-10-03 07:00 | 2024-10-17 17:00 | [12 empty] | 4 | 7 | ryAfVEGK+EOMbXpzfDHsFg | 3wwqebUhTkWtWt7SFPuIhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.3.6 | 41906327 | 41906321 | Casework |  |  |  |  | day | 2024-10-18 07:00 | 2024-11-21 17:00 | [12 empty] | 5 | 7 | K6x9dLBxbkOYHxdy9iPiJg | 3wwqebUhTkWtWt7SFPuIhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.3.7 | 41906328 | 41906321 | MEP Finishes |  |  |  |  | day | 2024-11-15 07:00 | 2024-12-10 17:00 | [12 empty] | 6 | 7 | pjv27PU5ZEG7gjCgAFLJhw | 3wwqebUhTkWtWt7SFPuIhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.3.8 | 41906329 | 41906321 | Doors & Trim | 11 |  |  |  | day | 2024-11-01 07:00 | 2024-12-11 17:00 | [12 empty] | 7 | 7 | HHuvOF1j/kGTAK4qQN5ABQ | 3wwqebUhTkWtWt7SFPuIhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.3.9 | 41906330 | 41906321 | Finish Paint | 21 |  |  |  | day | 2024-12-05 07:00 | 2024-12-11 17:00 | [12 empty] | 8 | 7 | p2gyoG6baEWv8EJy0qUk6w | 3wwqebUhTkWtWt7SFPuIhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.3.10 | 41906331 | 41906321 | Worklist/Punchlist | 16 |  |  |  | day | 2024-12-12 07:00 | 2025-01-24 17:00 | [12 empty] | 9 | 7 | zChJLSJ470aIoACTCvDq3A | 3wwqebUhTkWtWt7SFPuIhQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.4 | 41906332 | 41905613 | Corridors Finishes | 9 |  |  |  | day | 2024-08-02 07:00 | 2025-02-12 17:00 | [12 empty] | 3 | 6 | H2IVcugc90O4Tt8cGLluTw | CRtIUmaLE0mkRjepHv3E9g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.4.1 | 41906333 | 41906332 | Drywall | 0 |  |  |  | day | 2024-08-02 07:00 | 2024-08-15 17:00 | [12 empty] | 0 | 7 | kMgj/Np/OEus8s+AG42tBA | H2IVcugc90O4Tt8cGLluTw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.4.2 | 41906334 | 41906332 | Finishes |  |  |  |  | day | 2024-08-28 07:00 | 2025-01-03 17:00 | [12 empty] | 1 | 7 | 5TcKolWgw0KALagWCAyJMA | H2IVcugc90O4Tt8cGLluTw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.4.3 | 41906335 | 41906332 | Elevator Vestibule - SE2 |  |  |  |  | day | 2024-08-09 07:00 | 2024-08-30 17:00 | [12 empty] | 2 | 7 | 8WVRQEitAUeXbpS0SSX7mg | H2IVcugc90O4Tt8cGLluTw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.4.4 | 41906336 | 41906332 | Elevator Vestibule - PE01,02,03 |  |  |  |  | day | 2024-08-13 07:00 | 2024-09-25 17:00 | [12 empty] | 3 | 7 | KPAPdB1OGE2RTs2d16Nq3Q | H2IVcugc90O4Tt8cGLluTw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.5.4.5 | 41906337 | 41906332 | Worklist/Punchlist | 49 |  |  |  | day | 2025-01-06 07:00 | 2025-02-12 17:00 | [12 empty] | 4 | 7 | sO16HkySgkmQDQpwusXtxQ | H2IVcugc90O4Tt8cGLluTw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6 | 41905614 | 41905608 | Level 41 - Residential Units |  |  |  |  | day | 2024-02-26 07:00 | 2025-02-20 17:00 | [12 empty] | 5 | 5 | tSQrURbmCUKHWYVOJ/8wQQ | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.1 | 41906338 | 41905614 | Interior Summary & Milestones | 46 |  |  |  | day | 2024-02-26 07:00 | 2025-01-31 17:00 | [12 empty] | 0 | 6 | SiFlP42ji0ak1gJ0olO01A | tSQrURbmCUKHWYVOJ/8wQQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.2 | 41906339 | 41905614 | Roughs | 28 |  |  |  | day | 2024-06-06 07:00 | 2024-07-25 17:00 | [12 empty] | 1 | 6 | V1vy4B4nWEOdBPMRk6AIlA | tSQrURbmCUKHWYVOJ/8wQQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.2.1 | 41906340 | 41906339 | Facade - Curtainwall | 11 |  |  |  | day | [14 empty] | 0 | 7 | Pj/wfQVZF0iYO/pFEyR+Zg | V1vy4B4nWEOdBPMRk6AIlA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.2.2 | 41906341 | 41906339 | Layout, Risers & Toptrack | 35 |  |  |  | day | 2024-06-06 07:00 | 2024-06-20 17:00 | [12 empty] | 1 | 7 | EV99gowrJkmDUVsnZNloKA | V1vy4B4nWEOdBPMRk6AIlA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.2.3 | 41906342 | 41906339 | OH Rough | 34 |  |  |  | day | 2024-06-13 07:00 | 2024-07-02 17:00 | [12 empty] | 2 | 7 | /nh0/FQ/O0m9hgQypyHrNg | V1vy4B4nWEOdBPMRk6AIlA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.2.4 | 41906343 | 41906339 | Heat Pumps |  |  |  |  | day | [14 empty] | 3 | 7 | wNzk+mkvbUmVOAdBzHV7Ww | V1vy4B4nWEOdBPMRk6AIlA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.2.5 | 41906344 | 41906339 | Framing |  |  |  |  | day | 2024-06-21 07:00 | 2024-07-23 17:00 | [12 empty] | 4 | 7 | xUP95U+RdUCdHGv7ijbDwg | V1vy4B4nWEOdBPMRk6AIlA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.2.6 | 41906345 | 41906339 | In-Wall Rough | 28 |  |  |  | day | 2024-07-08 07:00 | 2024-07-24 17:00 | [12 empty] | 5 | 7 | ArJT/M1Ez0m9CdCBbm67Tw | V1vy4B4nWEOdBPMRk6AIlA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.2.7 | 41906346 | 41906339 | Inspections |  |  |  |  | day | 2024-07-22 07:00 | 2024-07-25 17:00 | [12 empty] | 6 | 7 | r6tl1lCn4UqVIAx74PavXw | V1vy4B4nWEOdBPMRk6AIlA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.3 | 41906347 | 41905614 | Unit Finishes |  |  |  |  | day | 2024-07-26 07:00 | 2025-01-31 17:00 | [12 empty] | 2 | 6 | IUxnO0lycE+d1h0J0OC/Xw | tSQrURbmCUKHWYVOJ/8wQQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.3.1 | 41906348 | 41906347 | Drywall | 5 |  |  |  | day | 2024-07-26 07:00 | 2024-08-27 17:00 | [12 empty] | 0 | 7 | GAd3Va1lEU2BpZLqten0gg | IUxnO0lycE+d1h0J0OC/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.3.2 | 41906349 | 41906347 | Bathroom Waterproofing | 46 |  |  |  | day | 2024-07-29 07:00 | 2024-08-28 17:00 | [12 empty] | 1 | 7 |  | IUxnO0lycE+d1h0J0OC/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.3.3 | 41906350 | 41906347 | Paint | 14 |  |  |  | day | 2024-08-28 07:00 | 2024-09-12 17:00 | [12 empty] | 2 | 7 | xph8e34P4Uq4RU1trXKIUQ | IUxnO0lycE+d1h0J0OC/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.3.4 | 41906351 | 41906347 | Tile |  |  |  |  | day | 2024-09-13 07:00 | 2024-10-09 17:00 | [12 empty] | 3 | 7 | rZhJCivRWU+uzrhcgiiY9A | IUxnO0lycE+d1h0J0OC/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.3.5 | 41906352 | 41906347 | Wood Flooring | 10 |  |  |  | day | 2024-10-10 07:00 | 2024-10-24 17:00 | [12 empty] | 4 | 7 | zzC95MedQkmuQuD31ny3GQ | IUxnO0lycE+d1h0J0OC/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.3.6 | 41906353 | 41906347 | Casework |  |  |  |  | day | 2024-10-25 07:00 | 2024-11-29 17:00 | [12 empty] | 5 | 7 | 09aCVKWZ8kW27IEvv2q6zw | IUxnO0lycE+d1h0J0OC/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.3.7 | 41906354 | 41906347 | MEP Finishes |  |  |  |  | day | 2024-11-22 07:00 | 2024-12-17 17:00 | [12 empty] | 6 | 7 | EeebM4/83UqVhAB7WoomGw | IUxnO0lycE+d1h0J0OC/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.3.8 | 41906355 | 41906347 | Doors & Trim |  |  |  |  | day | 2024-11-08 07:00 | 2024-12-18 17:00 | [12 empty] | 7 | 7 | k2ywSZoO2U2zFQWydMI8eQ | IUxnO0lycE+d1h0J0OC/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.3.9 | 41906356 | 41906347 | Finish Paint | 45 |  |  |  | day | 2024-12-12 07:00 | 2024-12-18 17:00 | [12 empty] | 8 | 7 | rf0LUH8hj02MEbQjeECmIQ | IUxnO0lycE+d1h0J0OC/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.3.10 | 41906357 | 41906347 | Worklist/Punchlist | 33 |  |  |  | day | 2024-12-19 07:00 | 2025-01-31 17:00 | [12 empty] | 9 | 7 | lbp5RahlS06a/z5tTSLXGA | IUxnO0lycE+d1h0J0OC/Xw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.4 | 41906358 | 41905614 | Corridors Finishes | 28 |  |  |  | day | 2024-08-09 07:00 | 2025-02-20 17:00 | [12 empty] | 3 | 6 | qbZfYrZ7SUy09UNvcrIA0Q | tSQrURbmCUKHWYVOJ/8wQQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.4.1 | 41906359 | 41906358 | Drywall | 3 |  |  |  | day | 2024-08-09 07:00 | 2024-08-22 17:00 | [12 empty] | 0 | 7 | klhsCeRmykmBGy/VFN6tNg | qbZfYrZ7SUy09UNvcrIA0Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.4.2 | 41906360 | 41906358 | Finishes | 16 |  |  |  | day | 2024-09-05 07:00 | 2025-01-10 17:00 | [12 empty] | 1 | 7 | chBwICUOW0qPt7JOy4EOVQ | qbZfYrZ7SUy09UNvcrIA0Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.4.3 | 41906361 | 41906358 | Elevator Vestibule - SE2 | 34 |  |  |  | day | 2024-08-16 07:00 | 2024-09-09 17:00 | [12 empty] | 2 | 7 | HGlCArv6nkuttq6ysxL8uA | qbZfYrZ7SUy09UNvcrIA0Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.4.4 | 41906362 | 41906358 | Elevator Vestibule - PE01,02,03 | 12 |  |  |  | day | 2024-08-20 07:00 | 2024-10-02 17:00 | [12 empty] | 3 | 7 | vc6SSuTB3U6qBH1Pct2FuQ | qbZfYrZ7SUy09UNvcrIA0Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.6.4.5 | 41906363 | 41906358 | Worklist/Punchlist | 40 |  |  |  | day | 2025-01-13 07:00 | 2025-02-20 17:00 | [12 empty] | 4 | 7 | DaldJIHkPkaneuYHdFWk2w | qbZfYrZ7SUy09UNvcrIA0Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7 | 41905615 | 41905608 | Level 42 - Residential Units | 38 |  |  |  | day | 2024-03-04 07:00 | 2025-02-27 17:00 | [12 empty] | 6 | 5 | k+W/do8BNUOcQi0hb1tq3w | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.1 | 41906364 | 41905615 | Interior Summary & Milestones | 14 |  |  |  | day | 2024-03-04 07:00 | 2025-02-07 17:00 | [12 empty] | 0 | 6 | ojbEit8jBkiymwT198zyjA | k+W/do8BNUOcQi0hb1tq3w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.2 | 41906365 | 41905615 | Roughs |  |  |  |  | day | 2024-06-13 07:00 | 2024-08-01 17:00 | [12 empty] | 1 | 6 | jcHYsfvG8UubvWFe1r3Dpg | k+W/do8BNUOcQi0hb1tq3w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.2.1 | 41906366 | 41906365 | Facade - Curtainwall | 28 |  |  |  | day | [14 empty] | 0 | 7 | 3NIjeITlOEuiyo6j6BzafQ | jcHYsfvG8UubvWFe1r3Dpg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.2.2 | 41906367 | 41906365 | Layout, Risers & Toptrack | 10 |  |  |  | day | 2024-06-13 07:00 | 2024-06-27 17:00 | [12 empty] | 1 | 7 | 7S2X2QxHI0O4udMP5w7o/w | jcHYsfvG8UubvWFe1r3Dpg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.2.3 | 41906368 | 41906365 | OH Rough | 31 |  |  |  | day | 2024-06-20 07:00 | 2024-07-10 17:00 | [12 empty] | 2 | 7 | O2xWvlBC7EqkxvSybYDptQ | jcHYsfvG8UubvWFe1r3Dpg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.2.4 | 41906369 | 41906365 | Heat Pumps | 1 |  |  |  | day | [14 empty] | 3 | 7 | u+EF2Yxsl0CvwZGoLQp05Q | jcHYsfvG8UubvWFe1r3Dpg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.2.5 | 41906370 | 41906365 | Framing | 46 |  |  |  | day | 2024-06-28 07:00 | 2024-07-30 17:00 | [12 empty] | 4 | 7 | G7zJG9ZXcEy218kqwQO7sA | jcHYsfvG8UubvWFe1r3Dpg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.2.6 | 41906371 | 41906365 | In-Wall Rough |  |  |  |  | day | 2024-07-15 07:00 | 2024-07-31 17:00 | [12 empty] | 5 | 7 | +vkANAOaXUa/y+7lD/9nYw | jcHYsfvG8UubvWFe1r3Dpg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.2.7 | 41906372 | 41906365 | Inspections | 19 |  |  |  | day | 2024-07-29 07:00 | 2024-08-01 17:00 | [12 empty] | 6 | 7 | EHFZ0BYclUiZp9xxKx+W7g | jcHYsfvG8UubvWFe1r3Dpg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.3 | 41906373 | 41905615 | Unit Finishes |  |  |  |  | day | 2024-08-02 07:00 | 2025-02-07 17:00 | [12 empty] | 2 | 6 | H8lanjTLnE6g+WT0w8ffAw | k+W/do8BNUOcQi0hb1tq3w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.3.1 | 41906374 | 41906373 | Drywall | 10 |  |  |  | day | 2024-08-02 07:00 | 2024-09-04 17:00 | [12 empty] | 0 | 7 | 1fNf1Qmx002yGa+dHZXtdg | H8lanjTLnE6g+WT0w8ffAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.3.2 | 41906375 | 41906373 | Bathroom Waterproofing | 26 |  |  |  | day | 2024-08-05 07:00 | 2024-09-05 17:00 | [12 empty] | 1 | 7 | yah5WQE/40OnatrXMxLZ1A | H8lanjTLnE6g+WT0w8ffAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.3.3 | 41906376 | 41906373 | Paint | 2 |  |  |  | day | 2024-09-05 07:00 | 2024-09-19 17:00 | [12 empty] | 2 | 7 | /7L/s/Qaj0SJo09zxv1ZTQ | H8lanjTLnE6g+WT0w8ffAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.3.4 | 41906377 | 41906373 | Tile | 16 |  |  |  | day | 2024-09-20 07:00 | 2024-10-17 17:00 | [12 empty] | 3 | 7 | lZdb6fWE4UyMazov7sDUGg | H8lanjTLnE6g+WT0w8ffAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.3.5 | 41906378 | 41906373 | Wood Flooring | 43 |  |  |  | day | 2024-10-18 07:00 | 2024-10-31 17:00 | [12 empty] | 4 | 7 | uv76UmqBfEqePC3myrOGmA | H8lanjTLnE6g+WT0w8ffAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.3.6 | 41906379 | 41906373 | Casework |  |  |  |  | day | 2024-11-01 07:00 | 2024-12-06 17:00 | [12 empty] | 5 | 7 | A8DiMRdqaE2slEpQjIEs/w | H8lanjTLnE6g+WT0w8ffAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.3.7 | 41906380 | 41906373 | MEP Finishes | 28 |  |  |  | day | 2024-12-02 07:00 | 2024-12-24 17:00 | [12 empty] | 6 | 7 | AOyS1KleqEmLbcWqEycczw | H8lanjTLnE6g+WT0w8ffAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.3.8 | 41906381 | 41906373 | Doors & Trim |  |  |  |  | day | 2024-11-18 07:00 | 2024-12-26 17:00 | [12 empty] | 7 | 7 | YhpTMgEilka4OyVZFx/SwQ | H8lanjTLnE6g+WT0w8ffAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.3.9 | 41906382 | 41906373 | Finish Paint | 46 |  |  |  | day | 2024-12-19 07:00 | 2024-12-26 17:00 | [12 empty] | 8 | 7 | y2k2SETHMEWmBpZ732p41Q | H8lanjTLnE6g+WT0w8ffAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.3.10 | 41906383 | 41906373 | Worklist/Punchlist | 15 |  |  |  | day | 2024-12-27 07:00 | 2025-02-07 17:00 | [12 empty] | 9 | 7 | r/Fd5fkf30i51V4RVeIr4A | H8lanjTLnE6g+WT0w8ffAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.4 | 41906384 | 41905615 | Corridors Finishes | 36 |  |  |  | day | 2024-08-16 07:00 | 2025-02-27 17:00 | [12 empty] | 3 | 6 | cZDlihkJwk+JgUx1g0d4bg | k+W/do8BNUOcQi0hb1tq3w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.4.1 | 41906385 | 41906384 | Drywall | 19 |  |  |  | day | 2024-08-16 07:00 | 2024-08-29 17:00 | [12 empty] | 0 | 7 | h+Xu8PCrYUKOda2H6Lp30Q | cZDlihkJwk+JgUx1g0d4bg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.4.2 | 41906386 | 41906384 | Finishes | 5 |  |  |  | day | 2024-09-12 07:00 | 2025-01-17 17:00 | [12 empty] | 1 | 7 | sgHOgPVQF0uCSrw5ETtq/g | cZDlihkJwk+JgUx1g0d4bg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.4.3 | 41906387 | 41906384 | Elevator Vestibule - SE2 | 18 |  |  |  | day | 2024-08-23 07:00 | 2024-09-16 17:00 | [12 empty] | 2 | 7 | 4IlScI2FK0m6iyrgFAGR2g | cZDlihkJwk+JgUx1g0d4bg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.4.4 | 41906388 | 41906384 | Elevator Vestibule - PE01,02,03 | 4 |  |  |  | day | 2024-08-27 07:00 | 2024-10-09 17:00 | [12 empty] | 3 | 7 | 2FCZKvppa0KeotKFb/R+2w | cZDlihkJwk+JgUx1g0d4bg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.7.4.5 | 41906389 | 41906384 | Worklist/Punchlist | 2 |  |  |  | day | 2025-01-20 07:00 | 2025-02-27 17:00 | [12 empty] | 4 | 7 | Wer7rCVctkGL0CX7jTOBbw | cZDlihkJwk+JgUx1g0d4bg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8 | 41905616 | 41905608 | Level 43 - Residential Units |  |  |  |  | day | 2024-03-11 07:00 | 2025-03-06 17:00 | [12 empty] | 7 | 5 | wfh+QMKk2Uee2KArkuIVXA | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.1 | 41906390 | 41905616 | Interior Summary & Milestones | 37 |  |  |  | day | 2024-03-11 07:00 | 2025-02-14 17:00 | [12 empty] | 0 | 6 | SjnqKVm9AEiq3rPbclV+Mw | wfh+QMKk2Uee2KArkuIVXA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.2 | 41906391 | 41905616 | Roughs |  |  |  |  | day | 2024-06-20 07:00 | 2024-08-08 17:00 | [12 empty] | 1 | 6 | lo4cObysq0GJWPAZDN66cA | wfh+QMKk2Uee2KArkuIVXA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.2.1 | 41906392 | 41906391 | Facade - Curtainwall | 33 |  |  |  | day | [14 empty] | 0 | 7 | j5Z1GseUykmPG1d4W1Ss2Q | lo4cObysq0GJWPAZDN66cA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.2.2 | 41906393 | 41906391 | Layout, Risers & Toptrack | 34 |  |  |  | day | 2024-06-20 07:00 | 2024-07-05 17:00 | [12 empty] | 1 | 7 | c5XuqNt8m0OEalcGFFc9wg | lo4cObysq0GJWPAZDN66cA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.2.3 | 41906394 | 41906391 | OH Rough | 48 |  |  |  | day | 2024-06-27 07:00 | 2024-07-17 17:00 | [12 empty] | 2 | 7 | ZuSlYWFyL0y2US1kjpQK9Q | lo4cObysq0GJWPAZDN66cA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.2.4 | 41906395 | 41906391 | Heat Pumps |  |  |  |  | day | [14 empty] | 3 | 7 | 6zdgnwCL40m8v98u/qBwPg | lo4cObysq0GJWPAZDN66cA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.2.5 | 41906396 | 41906391 | Framing | 23 |  |  |  | day | 2024-07-08 07:00 | 2024-08-06 17:00 | [12 empty] | 4 | 7 | 0dCFyK8BQEKi3HtCTuaxFQ | lo4cObysq0GJWPAZDN66cA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.2.6 | 41906397 | 41906391 | In-Wall Rough |  |  |  |  | day | 2024-07-22 07:00 | 2024-08-07 17:00 | [12 empty] | 5 | 7 | T5LNph0k/UaVfI2gDMVE9A | lo4cObysq0GJWPAZDN66cA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.2.7 | 41906398 | 41906391 | Inspections |  |  |  |  | day | 2024-08-05 07:00 | 2024-08-08 17:00 | [12 empty] | 6 | 7 | jZ6M4FPV2kuOjETSZl3v5w | lo4cObysq0GJWPAZDN66cA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.3 | 41906399 | 41905616 | Unit Finishes | 14 |  |  |  | day | 2024-08-09 07:00 | 2025-02-14 17:00 | [12 empty] | 2 | 6 | xF5z4ISooEyiG60Dhyu81A | wfh+QMKk2Uee2KArkuIVXA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.3.1 | 41906400 | 41906399 | Drywall | 43 |  |  |  | day | 2024-08-09 07:00 | 2024-09-11 17:00 | [12 empty] | 0 | 7 | OcUulIkjpkeEAvOHv8i9ug | xF5z4ISooEyiG60Dhyu81A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.3.2 | 41906401 | 41906399 | Bathroom Waterproofing | 15 |  |  |  | day | 2024-08-12 07:00 | 2024-09-12 17:00 | [12 empty] | 1 | 7 | RvphrnSxwUOuTPG5zef8Ug | xF5z4ISooEyiG60Dhyu81A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.3.3 | 41906402 | 41906399 | Paint |  |  |  |  | day | 2024-09-12 07:00 | 2024-09-26 17:00 | [12 empty] | 2 | 7 | /tEpXs41nUSz8q6pyZMYHw | xF5z4ISooEyiG60Dhyu81A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.3.4 | 41906403 | 41906399 | Tile | 7 |  |  |  | day | 2024-09-27 07:00 | 2024-10-24 17:00 | [12 empty] | 3 | 7 | 2E/uFZYnmkylWT9OwDojcg | xF5z4ISooEyiG60Dhyu81A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.3.5 | 41906404 | 41906399 | Wood Flooring | 45 |  |  |  | day | 2024-10-25 07:00 | 2024-11-07 17:00 | [12 empty] | 4 | 7 | oSWwBAvg2UOwVLGDuCC8nQ | xF5z4ISooEyiG60Dhyu81A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.3.6 | 41906405 | 41906399 | Casework | 24 |  |  |  | day | 2024-11-08 07:00 | 2024-12-13 17:00 | [12 empty] | 5 | 7 | v3dJvmXNREqDcs0Nn3QMCg | xF5z4ISooEyiG60Dhyu81A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.3.7 | 41906406 | 41906399 | MEP Finishes | 16 |  |  |  | day | 2024-12-09 07:00 | 2025-01-02 17:00 | [12 empty] | 6 | 7 | sQzTRYJiHkKq5H8e3eeZnw | xF5z4ISooEyiG60Dhyu81A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.3.8 | 41906407 | 41906399 | Doors & Trim | 28 |  |  |  | day | 2024-11-25 07:00 | 2025-01-03 17:00 | [12 empty] | 7 | 7 | G5r+gghmKkONdilLY39j/Q | xF5z4ISooEyiG60Dhyu81A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.3.9 | 41906408 | 41906399 | Finish Paint |  |  |  |  | day | 2024-12-27 07:00 | 2025-01-03 17:00 | [12 empty] | 8 | 7 | kVAEmSHnh02lT1GM1ditCg | xF5z4ISooEyiG60Dhyu81A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.3.10 | 41906409 | 41906399 | Worklist/Punchlist | 14 |  |  |  | day | 2025-01-06 07:00 | 2025-02-14 17:00 | [12 empty] | 9 | 7 | BSSBQBTN8km45JDecSfQIw | xF5z4ISooEyiG60Dhyu81A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.4 | 41906410 | 41905616 | Corridors Finishes | 26 |  |  |  | day | 2024-08-23 07:00 | 2025-03-06 17:00 | [12 empty] | 3 | 6 | lXauyWFUu0K3SIeKt0elTw | wfh+QMKk2Uee2KArkuIVXA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.4.1 | 41906411 | 41906410 | Drywall | 45 |  |  |  | day | 2024-08-23 07:00 | 2024-09-06 17:00 | [12 empty] | 0 | 7 | dtBQcOwZekSFCf4rzPQGDA | lXauyWFUu0K3SIeKt0elTw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.4.2 | 41906412 | 41906410 | Finishes |  |  |  |  | day | 2024-09-19 07:00 | 2025-01-24 17:00 | [12 empty] | 1 | 7 | bX3q4sVGxUuD6w9QwKAdrQ | lXauyWFUu0K3SIeKt0elTw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.4.3 | 41906413 | 41906410 | Elevator Vestibule - SE2 |  |  |  |  | day | 2024-08-30 07:00 | 2024-09-23 17:00 | [12 empty] | 2 | 7 | 9+ZBUWcyP0iJDbgKgsrlTg | lXauyWFUu0K3SIeKt0elTw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.4.4 | 41906414 | 41906410 | Elevator Vestibule - PE01,02,03 |  |  |  |  | day | 2024-09-04 07:00 | 2024-10-17 17:00 | [12 empty] | 3 | 7 | XZKz8DRU3EKysctPTOwKQQ | lXauyWFUu0K3SIeKt0elTw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.8.4.5 | 41906415 | 41906410 | Worklist/Punchlist | 28 |  |  |  | day | 2025-01-27 07:00 | 2025-03-06 17:00 | [12 empty] | 4 | 7 | Xed1A+hqXUSh9qWDFY5i2g | lXauyWFUu0K3SIeKt0elTw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9 | 41905617 | 41905608 | Level 44 - Residential Units | 43 |  |  |  | day | 2024-03-18 07:00 | 2025-03-13 17:00 | [12 empty] | 8 | 5 | s8BXbJ1rs02uqUAOzbk/aw | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.1 | 41906416 | 41905617 | Interior Summary & Milestones | 23 |  |  |  | day | 2024-03-18 07:00 | 2025-02-24 17:00 | [12 empty] | 0 | 6 | jhnq4xSFHE6cDpzxnqOlkg | s8BXbJ1rs02uqUAOzbk/aw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.2 | 41906417 | 41905617 | Roughs | 2 |  |  |  | day | 2024-06-27 07:00 | 2024-08-15 17:00 | [12 empty] | 1 | 6 | fY6mmslgYUiBgZ35aYL29Q | s8BXbJ1rs02uqUAOzbk/aw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.2.1 | 41906418 | 41906417 | Facade - Curtainwall |  |  |  |  | day | [14 empty] | 0 | 7 | 9DymdB8i7UqCvQZdQQ8KDA | fY6mmslgYUiBgZ35aYL29Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.2.2 | 41906419 | 41906417 | Layout, Risers & Toptrack | 45 |  |  |  | day | 2024-06-27 07:00 | 2024-07-12 17:00 | [12 empty] | 1 | 7 | bps7QozEw0GWied1ztQb6A | fY6mmslgYUiBgZ35aYL29Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.2.3 | 41906420 | 41906417 | OH Rough | 14 |  |  |  | day | 2024-07-05 07:00 | 2024-07-24 17:00 | [12 empty] | 2 | 7 | ilBaH6GNdUSOpK1bPbsTqg | fY6mmslgYUiBgZ35aYL29Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.2.4 | 41906421 | 41906417 | Heat Pumps |  |  |  |  | day | [14 empty] | 3 | 7 | grTY9alsdEmeefL8VI59lw | fY6mmslgYUiBgZ35aYL29Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.2.5 | 41906422 | 41906417 | Framing | 29 |  |  |  | day | 2024-07-15 07:00 | 2024-08-13 17:00 | [12 empty] | 4 | 7 | E/SSXY+ac0ap7dnDL94ENg | fY6mmslgYUiBgZ35aYL29Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.2.6 | 41906423 | 41906417 | In-Wall Rough | 13 |  |  |  | day | 2024-07-29 07:00 | 2024-08-14 17:00 | [12 empty] | 5 | 7 | PEEZcdUE7kie7GE2lgBCEw | fY6mmslgYUiBgZ35aYL29Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.2.7 | 41906424 | 41906417 | Inspections | 6 |  |  |  | day | 2024-08-12 07:00 | 2024-08-15 17:00 | [12 empty] | 6 | 7 | aNhFWrOs0EiiVOHL6sjM7Q | fY6mmslgYUiBgZ35aYL29Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.3 | 41906425 | 41905617 | Unit Finishes | 16 |  |  |  | day | 2024-08-16 07:00 | 2025-02-24 17:00 | [12 empty] | 2 | 6 | yqz8PjfJk0CGzPHlhgsS3Q | s8BXbJ1rs02uqUAOzbk/aw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.3.1 | 41906426 | 41906425 | Drywall | 43 |  |  |  | day | 2024-08-16 07:00 | 2024-09-18 17:00 | [12 empty] | 0 | 7 | mhTx7hqjQUCX30Bab4KrOw | yqz8PjfJk0CGzPHlhgsS3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.3.2 | 41906427 | 41906425 | Bathroom Waterproofing |  |  |  |  | day | 2024-08-19 07:00 | 2024-09-19 17:00 | [12 empty] | 1 | 7 | Begxy0xlckSkrLvKxhe9zw | yqz8PjfJk0CGzPHlhgsS3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.3.3 | 41906428 | 41906425 | Paint | 35 |  |  |  | day | 2024-09-19 07:00 | 2024-10-03 17:00 | [12 empty] | 2 | 7 | HjzsrshDs0+OWLZvTpYMzw | yqz8PjfJk0CGzPHlhgsS3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.3.4 | 41906429 | 41906425 | Tile | 8 |  |  |  | day | 2024-10-04 07:00 | 2024-10-31 17:00 | [12 empty] | 3 | 7 | VPlia2BAf0qdGqobWl+fkA | yqz8PjfJk0CGzPHlhgsS3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.3.5 | 41906430 | 41906425 | Wood Flooring |  |  |  |  | day | 2024-11-01 07:00 | 2024-11-15 17:00 | [12 empty] | 4 | 7 | 9t9QLebWoEWO15VhDsbzGQ | yqz8PjfJk0CGzPHlhgsS3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.3.6 | 41906431 | 41906425 | Casework | 47 |  |  |  | day | 2024-11-18 07:00 | 2024-12-20 17:00 | [12 empty] | 5 | 7 | e6KBmF02rEuHPMVkbYVmaA | yqz8PjfJk0CGzPHlhgsS3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.3.7 | 41906432 | 41906425 | MEP Finishes | 21 |  |  |  | day | 2024-12-16 07:00 | 2025-01-09 17:00 | [12 empty] | 6 | 7 | kCcArCjGgESLwQthYEbWLw | yqz8PjfJk0CGzPHlhgsS3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.3.8 | 41906433 | 41906425 | Doors & Trim |  |  |  |  | day | 2024-12-03 07:00 | 2025-01-10 17:00 | [12 empty] | 7 | 7 | YP6EYkgGMU2N52qleHSX3Q | yqz8PjfJk0CGzPHlhgsS3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.3.9 | 41906434 | 41906425 | Finish Paint | 23 |  |  |  | day | 2025-01-06 07:00 | 2025-01-10 17:00 | [12 empty] | 8 | 7 | iWVCRlrCykmrlB2tedvgrw | yqz8PjfJk0CGzPHlhgsS3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.3.10 | 41906435 | 41906425 | Worklist/Punchlist | 7 |  |  |  | day | 2025-01-13 07:00 | 2025-02-24 17:00 | [12 empty] | 9 | 7 | ygFYfFI2w0Wt/Dp/Q4Gljg | yqz8PjfJk0CGzPHlhgsS3Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.4 | 41906436 | 41905617 | Corridors Finishes | 10 |  |  |  | day | 2024-08-30 07:00 | 2025-03-13 17:00 | [12 empty] | 3 | 6 | V1GtWPcqW0mbuZvTkyQmOQ | s8BXbJ1rs02uqUAOzbk/aw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.4.1 | 41906437 | 41906436 | Drywall | 12 |  |  |  | day | 2024-08-30 07:00 | 2024-09-13 17:00 | [12 empty] | 0 | 7 | bb3sUzmGFkiepRA+cvuOFA | V1GtWPcqW0mbuZvTkyQmOQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.4.2 | 41906438 | 41906436 | Finishes | 16 |  |  |  | day | 2024-09-26 07:00 | 2025-01-31 17:00 | [12 empty] | 1 | 7 | hjDUJ/it/Em5xGn0bFSiOQ | V1GtWPcqW0mbuZvTkyQmOQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.4.3 | 41906439 | 41906436 | Elevator Vestibule - SE2 | 7 |  |  |  | day | 2024-09-09 07:00 | 2024-09-30 17:00 | [12 empty] | 2 | 7 | b+r0sKQXzEOYEwKVA5ceQw | V1GtWPcqW0mbuZvTkyQmOQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.4.4 | 41906440 | 41906436 | Elevator Vestibule - PE01,02,03 | 20 |  |  |  | day | 2024-09-11 07:00 | 2024-10-24 17:00 | [12 empty] | 3 | 7 | ZCjqDzu3XkW+JBi9GoXdhA | V1GtWPcqW0mbuZvTkyQmOQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.9.4.5 | 41906441 | 41906436 | Worklist/Punchlist | 17 |  |  |  | day | 2025-02-03 07:00 | 2025-03-13 17:00 | [12 empty] | 4 | 7 | YbGFdfJssUaEJd693Tyc1A | V1GtWPcqW0mbuZvTkyQmOQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10 | 41905618 | 41905608 | Level 45 - Residential Units | 29 |  |  |  | day | 2024-03-25 07:00 | 2025-03-20 17:00 | [12 empty] | 9 | 5 | H4qXlnXnb0GX3B9gKi4+Iw | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.1 | 41906442 | 41905618 | Interior Summary & Milestones |  |  |  |  | day | 2024-03-25 07:00 | 2025-03-03 17:00 | [12 empty] | 0 | 6 | m1OP/yqV3UucHTG8QxaMQw | H4qXlnXnb0GX3B9gKi4+Iw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.2 | 41906443 | 41905618 | Roughs | 45 |  |  |  | day | 2024-07-05 07:00 | 2024-08-22 17:00 | [12 empty] | 1 | 6 | EQ8ArE0StUueK/PSEizRnQ | H4qXlnXnb0GX3B9gKi4+Iw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.2.1 | 41906444 | 41906443 | Facade - Curtainwall | 46 |  |  |  | day | [14 empty] | 0 | 7 | uD96NsV0l0O6Areyxg8AFA | EQ8ArE0StUueK/PSEizRnQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.2.2 | 41906445 | 41906443 | Layout, Risers & Toptrack | 30 |  |  |  | day | 2024-07-05 07:00 | 2024-07-19 17:00 | [12 empty] | 1 | 7 | y/yLhgARz0eWQf4/HkogLA | EQ8ArE0StUueK/PSEizRnQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.2.3 | 41906446 | 41906443 | OH Rough |  |  |  |  | day | 2024-07-12 07:00 | 2024-07-31 17:00 | [12 empty] | 2 | 7 | A3tyeolWZkq4k6p362W2bw | EQ8ArE0StUueK/PSEizRnQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.2.4 | 41906447 | 41906443 | Heat Pumps | 31 |  |  |  | day | [14 empty] | 3 | 7 | YDEdQktikkKraALK3+WR+Q | EQ8ArE0StUueK/PSEizRnQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.2.5 | 41906448 | 41906443 | Framing |  |  |  |  | day | 2024-07-22 07:00 | 2024-08-20 17:00 | [12 empty] | 4 | 7 | uy3FT7VHXUWjUzU6eq6RcA | EQ8ArE0StUueK/PSEizRnQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.2.6 | 41906449 | 41906443 | In-Wall Rough | 44 |  |  |  | day | 2024-08-05 07:00 | 2024-08-21 17:00 | [12 empty] | 5 | 7 | soLV57byu0Srakua1g/UIQ | EQ8ArE0StUueK/PSEizRnQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.2.7 | 41906450 | 41906443 | Inspections | 24 |  |  |  | day | 2024-08-19 07:00 | 2024-08-22 17:00 | [12 empty] | 6 | 7 | pec80v/TqkOguggxZZJrHA | EQ8ArE0StUueK/PSEizRnQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.3 | 41906451 | 41905618 | Unit Finishes | 32 |  |  |  | day | 2024-08-23 07:00 | 2025-03-03 17:00 | [12 empty] | 2 | 6 | O1mIb4pN4Uqrwq1ad7TKSA | H4qXlnXnb0GX3B9gKi4+Iw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.3.1 | 41906452 | 41906451 | Drywall | 37 |  |  |  | day | 2024-08-23 07:00 | 2024-09-25 17:00 | [12 empty] | 0 | 7 | ke/2Xs0OAUG6ioPg9l96Fw | O1mIb4pN4Uqrwq1ad7TKSA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.3.2 | 41906453 | 41906451 | Bathroom Waterproofing | 40 |  |  |  | day | 2024-08-26 07:00 | 2024-09-26 17:00 | [12 empty] | 1 | 7 | 7tcmohelvke3Tmp52Yxebg | O1mIb4pN4Uqrwq1ad7TKSA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.3.3 | 41906454 | 41906451 | Paint | 7 |  |  |  | day | 2024-09-26 07:00 | 2024-10-10 17:00 | [12 empty] | 2 | 7 | PVF3nbAy9EKCPae8CZ75eQ | O1mIb4pN4Uqrwq1ad7TKSA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.3.4 | 41906455 | 41906451 | Tile | 10 |  |  |  | day | 2024-10-11 07:00 | 2024-11-07 17:00 | [12 empty] | 3 | 7 | ew8ibLNwQEyNxnWJDSXBiA | O1mIb4pN4Uqrwq1ad7TKSA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.3.5 | 41906456 | 41906451 | Wood Flooring |  |  |  |  | day | 2024-11-08 07:00 | 2024-11-22 17:00 | [12 empty] | 4 | 7 | qwhuDI54VUi3Y1GPTa9Hzw | O1mIb4pN4Uqrwq1ad7TKSA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.3.6 | 41906457 | 41906451 | Casework | 23 |  |  |  | day | 2024-11-25 07:00 | 2024-12-30 17:00 | [12 empty] | 5 | 7 | DpIb0W1TMUyUThbyFsYADg | O1mIb4pN4Uqrwq1ad7TKSA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.3.7 | 41906458 | 41906451 | MEP Finishes | 40 |  |  |  | day | 2024-12-23 07:00 | 2025-01-16 17:00 | [12 empty] | 6 | 7 | 9NbVgFXh70eS6kOk7hhnHA | O1mIb4pN4Uqrwq1ad7TKSA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.3.8 | 41906459 | 41906451 | Doors & Trim | 16 |  |  |  | day | 2024-12-10 07:00 | 2025-01-17 17:00 | [12 empty] | 7 | 7 | GNpoU0pA9ESWaQUyosa93Q | O1mIb4pN4Uqrwq1ad7TKSA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.3.9 | 41906460 | 41906451 | Finish Paint | 11 |  |  |  | day | 2025-01-13 07:00 | 2025-01-17 17:00 | [12 empty] | 8 | 7 | y0umv564S0uwvTUz0JppNw | O1mIb4pN4Uqrwq1ad7TKSA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.3.10 | 41906461 | 41906451 | Worklist/Punchlist |  |  |  |  | day | 2025-01-20 07:00 | 2025-03-03 17:00 | [12 empty] | 9 | 7 | EpLuZaRAtkS5y9TN5HYhJQ | O1mIb4pN4Uqrwq1ad7TKSA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.4 | 41906462 | 41905618 | Corridors Finishes |  |  |  |  | day | 2024-09-09 07:00 | 2025-03-20 17:00 | [12 empty] | 3 | 6 | VWiM078Ix06vp0MhXv/qYA | H4qXlnXnb0GX3B9gKi4+Iw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.4.1 | 41906463 | 41906462 | Drywall | 14 |  |  |  | day | 2024-09-09 07:00 | 2024-09-20 17:00 | [12 empty] | 0 | 7 | 3Pzh3LXQdU+7gOkFW0K+Bg | VWiM078Ix06vp0MhXv/qYA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.4.2 | 41906464 | 41906462 | Finishes | 15 |  |  |  | day | 2024-10-03 07:00 | 2025-02-07 17:00 | [12 empty] | 1 | 7 | iSl71g2OlUC3yQcqoX3FQA | VWiM078Ix06vp0MhXv/qYA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.4.3 | 41906465 | 41906462 | Elevator Vestibule - SE2 | 21 |  |  |  | day | 2024-09-16 07:00 | 2024-10-07 17:00 | [12 empty] | 2 | 7 | PVNUbWtPXEmaFJlWgJxKHQ | VWiM078Ix06vp0MhXv/qYA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.4.4 | 41906466 | 41906462 | Elevator Vestibule - PE01,02,03 | 27 |  |  |  | day | 2024-09-18 07:00 | 2024-10-31 17:00 | [12 empty] | 3 | 7 | yEt5bJyyMUWDqIHnhklhJw | VWiM078Ix06vp0MhXv/qYA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.10.4.5 | 41906467 | 41906462 | Worklist/Punchlist | 19 |  |  |  | day | 2025-02-10 07:00 | 2025-03-20 17:00 | [12 empty] | 4 | 7 | LawPaBoYW0S/nNBymR30GQ | VWiM078Ix06vp0MhXv/qYA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11 | 41905619 | 41905608 | Level 46 - Residential Units | 32 |  |  |  | day | 2024-04-01 07:00 | 2025-03-27 17:00 | [12 empty] | 10 | 5 | /8BnQPDGD0yPsawwZp59eA | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.1 | 41906468 | 41905619 | Interior Summary & Milestones |  |  |  |  | day | 2024-04-01 07:00 | 2025-03-10 17:00 | [12 empty] | 0 | 6 | upTq3i3DL0C+AdX9erU3bw | /8BnQPDGD0yPsawwZp59eA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.2 | 41906469 | 41905619 | Roughs | 39 |  |  |  | day | 2024-07-12 07:00 | 2024-08-29 17:00 | [12 empty] | 1 | 6 | bSBN/l+2d0GFQQVmmMo5OQ | /8BnQPDGD0yPsawwZp59eA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.2.1 | 41906470 | 41906469 | Facade - Curtainwall | 31 |  |  |  | day | [14 empty] | 0 | 7 | krxndAtGFUe23/TkeX2slw | bSBN/l+2d0GFQQVmmMo5OQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.2.2 | 41906471 | 41906469 | Layout, Risers & Toptrack | 49 |  |  |  | day | 2024-07-12 07:00 | 2024-07-26 17:00 | [12 empty] | 1 | 7 | 7z77udEVTUmNf/LN2mCOIg | bSBN/l+2d0GFQQVmmMo5OQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.2.3 | 41906472 | 41906469 | OH Rough |  |  |  |  | day | 2024-07-19 07:00 | 2024-08-07 17:00 | [12 empty] | 2 | 7 | IqBfa54Yc0esk0VUI0Mwpg | bSBN/l+2d0GFQQVmmMo5OQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.2.4 | 41906473 | 41906469 | Heat Pumps | 1 |  |  |  | day | [14 empty] | 3 | 7 | gi8Qy/XpD0CyveRpxFL4RQ | bSBN/l+2d0GFQQVmmMo5OQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.2.5 | 41906474 | 41906469 | Framing | 32 |  |  |  | day | 2024-07-29 07:00 | 2024-08-27 17:00 | [12 empty] | 4 | 7 | B3XlboRip0GgrKs+7p9zDg | bSBN/l+2d0GFQQVmmMo5OQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.2.6 | 41906475 | 41906469 | In-Wall Rough | 32 |  |  |  | day | 2024-08-12 07:00 | 2024-08-28 17:00 | [12 empty] | 5 | 7 | jst7b1KVrUWxwY7fAcRhjA | bSBN/l+2d0GFQQVmmMo5OQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.2.7 | 41906476 | 41906469 | Inspections | 40 |  |  |  | day | 2024-08-26 07:00 | 2024-08-29 17:00 | [12 empty] | 6 | 7 | GUZaP8OxZEe/YWhgVQpk+g | bSBN/l+2d0GFQQVmmMo5OQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.3 | 41906477 | 41905619 | Unit Finishes | 12 |  |  |  | day | 2024-08-30 07:00 | 2025-03-10 17:00 | [12 empty] | 2 | 6 | LFGVdh8Trk2JIsVTlHVN7Q | /8BnQPDGD0yPsawwZp59eA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.3.1 | 41906478 | 41906477 | Drywall |  |  |  |  | day | 2024-08-30 07:00 | 2024-10-02 17:00 | [12 empty] | 0 | 7 | TYpEU7NSh0O3cihuZWBjJQ | LFGVdh8Trk2JIsVTlHVN7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.3.2 | 41906479 | 41906477 | Bathroom Waterproofing | 32 |  |  |  | day | 2024-09-03 07:00 | 2024-10-03 17:00 | [12 empty] | 1 | 7 | R4NYNIM4ME2euXUpQyXS/Q | LFGVdh8Trk2JIsVTlHVN7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.3.3 | 41906480 | 41906477 | Paint | 12 |  |  |  | day | 2024-10-03 07:00 | 2024-10-18 17:00 | [12 empty] | 2 | 7 | hqK8ZOn8WEaVpiSypPK4SQ | LFGVdh8Trk2JIsVTlHVN7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.3.4 | 41906481 | 41906477 | Tile | 25 |  |  |  | day | 2024-10-21 07:00 | 2024-11-15 17:00 | [12 empty] | 3 | 7 | SoCOjEqITUqudOBJ809l2A | LFGVdh8Trk2JIsVTlHVN7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.3.5 | 41906482 | 41906477 | Wood Flooring |  |  |  |  | day | 2024-11-18 07:00 | 2024-12-02 17:00 | [12 empty] | 4 | 7 | OlgYC2Nn1UOw28Cs5W6HjQ | LFGVdh8Trk2JIsVTlHVN7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.3.6 | 41906483 | 41906477 | Casework |  |  |  |  | day | 2024-12-03 07:00 | 2025-01-07 17:00 | [12 empty] | 5 | 7 | LczZRGEZMEmHLGwWhzUCig | LFGVdh8Trk2JIsVTlHVN7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.3.7 | 41906484 | 41906477 | MEP Finishes |  |  |  |  | day | 2024-12-31 07:00 | 2025-01-23 17:00 | [12 empty] | 6 | 7 | F8epE4R6jEqraXEataWpnw | LFGVdh8Trk2JIsVTlHVN7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.3.8 | 41906485 | 41906477 | Doors & Trim | 37 |  |  |  | day | 2024-12-17 07:00 | 2025-01-24 17:00 | [12 empty] | 7 | 7 | Yw5qJ+9TC0qJvJjKAts/0g | LFGVdh8Trk2JIsVTlHVN7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.3.9 | 41906486 | 41906477 | Finish Paint |  |  |  |  | day | 2025-01-20 07:00 | 2025-01-24 17:00 | [12 empty] | 8 | 7 | kqt+olYX/U6Xlyl08lkaNw | LFGVdh8Trk2JIsVTlHVN7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.3.10 | 41906487 | 41906477 | Worklist/Punchlist | 25 |  |  |  | day | 2025-01-27 07:00 | 2025-03-10 17:00 | [12 empty] | 9 | 7 | VPgppJ6ig0Gg5iGp8JShAQ | LFGVdh8Trk2JIsVTlHVN7Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.4 | 41906488 | 41905619 | Corridors Finishes | 45 |  |  |  | day | 2024-09-16 07:00 | 2025-03-27 17:00 | [12 empty] | 3 | 6 | LmkdpCLp9kOnsvL7kg3/kQ | /8BnQPDGD0yPsawwZp59eA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.4.1 | 41906489 | 41906488 | Drywall | 49 |  |  |  | day | 2024-09-16 07:00 | 2024-09-27 17:00 | [12 empty] | 0 | 7 | abvtgiTMNEuW25UbPkVa4g | LmkdpCLp9kOnsvL7kg3/kQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.4.2 | 41906490 | 41906488 | Finishes |  |  |  |  | day | 2024-10-10 07:00 | 2025-02-14 17:00 | [12 empty] | 1 | 7 | VYif5qmWWU6hYuc1CRTUPA | LmkdpCLp9kOnsvL7kg3/kQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.4.3 | 41906491 | 41906488 | Elevator Vestibule - SE2 | 33 |  |  |  | day | 2024-09-23 07:00 | 2024-10-15 17:00 | [12 empty] | 2 | 7 | jM23ua9k20SWYzSL+5FvmQ | LmkdpCLp9kOnsvL7kg3/kQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.4.4 | 41906492 | 41906488 | Elevator Vestibule - PE01,02,03 |  |  |  |  | day | 2024-09-25 07:00 | 2024-11-07 17:00 | [12 empty] | 3 | 7 | H6Fga9k3tEeRW9idJ8yeEg | LmkdpCLp9kOnsvL7kg3/kQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.11.4.5 | 41906493 | 41906488 | Worklist/Punchlist | 43 |  |  |  | day | 2025-02-18 07:00 | 2025-03-27 17:00 | [12 empty] | 4 | 7 |  | LmkdpCLp9kOnsvL7kg3/kQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12 | 41905620 | 41905608 | Level 47 - Residential Units |  |  |  |  | day | 2024-04-09 07:00 | 2025-04-03 17:00 | [12 empty] | 11 | 5 | HUD7iDK2VkiUyzgPJQ/EMQ | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.1 | 41906494 | 41905620 | Interior Summary & Milestones | 39 |  |  |  | day | 2024-04-09 07:00 | 2025-03-17 17:00 | [12 empty] | 0 | 6 | LninfDMmcEe1NPE+0x1TAg | HUD7iDK2VkiUyzgPJQ/EMQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.2 | 41906495 | 41905620 | Roughs | 10 |  |  |  | day | 2024-07-19 07:00 | 2024-09-06 17:00 | [12 empty] | 1 | 6 | cmBRHE8mD0OUTfGXoQ8wPQ | HUD7iDK2VkiUyzgPJQ/EMQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.2.1 | 41906496 | 41906495 | Facade - Curtainwall | 2 |  |  |  | day | [14 empty] | 0 | 7 | nKlzWoenJESZj3uHFftSUQ | cmBRHE8mD0OUTfGXoQ8wPQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.2.2 | 41906497 | 41906495 | Layout, Risers & Toptrack | 5 |  |  |  | day | 2024-07-19 07:00 | 2024-08-02 17:00 | [12 empty] | 1 | 7 | FAfwNmE05EmFj+9Cu85qRg | cmBRHE8mD0OUTfGXoQ8wPQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.2.3 | 41906498 | 41906495 | OH Rough | 8 |  |  |  | day | 2024-07-26 07:00 | 2024-08-14 17:00 | [12 empty] | 2 | 7 | 380aho/4QUuxD6OtazmRVw | cmBRHE8mD0OUTfGXoQ8wPQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.2.4 | 41906499 | 41906495 | Heat Pumps | 5 |  |  |  | day | [14 empty] | 3 | 7 | X9Q8nRX/vkWTPr2Feqgf/A | cmBRHE8mD0OUTfGXoQ8wPQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.2.5 | 41906500 | 41906495 | Framing | 8 |  |  |  | day | 2024-08-05 07:00 | 2024-09-04 17:00 | [12 empty] | 4 | 7 | rEjNR9ssCUaEzJsVduLkmA | cmBRHE8mD0OUTfGXoQ8wPQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.2.6 | 41906501 | 41906495 | In-Wall Rough | 38 |  |  |  | day | 2024-08-19 07:00 | 2024-09-05 17:00 | [12 empty] | 5 | 7 | HZzVAmojbkSLPwLDou+lqA | cmBRHE8mD0OUTfGXoQ8wPQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.2.7 | 41906502 | 41906495 | Inspections |  |  |  |  | day | 2024-09-03 07:00 | 2024-09-06 17:00 | [12 empty] | 6 | 7 | 0Nn8JXrd3E2xp7WuoeyZRQ | cmBRHE8mD0OUTfGXoQ8wPQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.3 | 41906503 | 41905620 | Unit Finishes | 31 |  |  |  | day | 2024-09-09 07:00 | 2025-03-17 17:00 | [12 empty] | 2 | 6 | Pl4UIRDBXU+qPgM+E62KoA | HUD7iDK2VkiUyzgPJQ/EMQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.3.1 | 41906504 | 41906503 | Drywall | 40 |  |  |  | day | 2024-09-09 07:00 | 2024-10-09 17:00 | [12 empty] | 0 | 7 | lzm6VyRnz06bV6TsQWZ5CA | Pl4UIRDBXU+qPgM+E62KoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.3.2 | 41906505 | 41906503 | Bathroom Waterproofing | 49 |  |  |  | day | 2024-09-10 07:00 | 2024-10-10 17:00 | [12 empty] | 1 | 7 | 6sVpIoeiQUef6DZXlwM4sw | Pl4UIRDBXU+qPgM+E62KoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.3.3 | 41906506 | 41906503 | Paint | 11 |  |  |  | day | 2024-10-10 07:00 | 2024-10-25 17:00 | [12 empty] | 2 | 7 | AtidlDb6dkOnR0imO+Xbgg | Pl4UIRDBXU+qPgM+E62KoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.3.4 | 41906507 | 41906503 | Tile |  |  |  |  | day | 2024-10-28 07:00 | 2024-11-22 17:00 | [12 empty] | 3 | 7 | dWgNcQvLZEqRzzfc8vakjA | Pl4UIRDBXU+qPgM+E62KoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.3.5 | 41906508 | 41906503 | Wood Flooring | 7 |  |  |  | day | 2024-11-25 07:00 | 2024-12-09 17:00 | [12 empty] | 4 | 7 | vNAW1zQDNUSiKiLbMWM0vw | Pl4UIRDBXU+qPgM+E62KoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.3.6 | 41906509 | 41906503 | Casework |  |  |  |  | day | 2024-12-10 07:00 | 2025-01-14 17:00 | [12 empty] | 5 | 7 | 5WtF01t00ku9+1opJWfBwg | Pl4UIRDBXU+qPgM+E62KoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.3.7 | 41906510 | 41906503 | MEP Finishes |  |  |  |  | day | 2025-01-08 07:00 | 2025-01-30 17:00 | [12 empty] | 6 | 7 |  | Pl4UIRDBXU+qPgM+E62KoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.3.8 | 41906511 | 41906503 | Doors & Trim | 19 |  |  |  | day | 2024-12-24 07:00 | 2025-01-31 17:00 | [12 empty] | 7 | 7 | qzqSrw2Cj0qNTcmomfLHFg | Pl4UIRDBXU+qPgM+E62KoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.3.9 | 41906512 | 41906503 | Finish Paint | 46 |  |  |  | day | 2025-01-27 07:00 | 2025-01-31 17:00 | [12 empty] | 8 | 7 | TWxy9Ol7uUGLrlrAhhnWxQ | Pl4UIRDBXU+qPgM+E62KoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.3.10 | 41906513 | 41906503 | Worklist/Punchlist |  |  |  |  | day | 2025-02-03 07:00 | 2025-03-17 17:00 | [12 empty] | 9 | 7 | xff1dwcOu0WLJjce79ke7w | Pl4UIRDBXU+qPgM+E62KoA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.4 | 41906514 | 41905620 | Corridors Finishes | 10 |  |  |  | day | 2024-09-23 07:00 | 2025-04-03 17:00 | [12 empty] | 3 | 6 | MP4bMiL/YEKZD+G3Ld7szg | HUD7iDK2VkiUyzgPJQ/EMQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.4.1 | 41906515 | 41906514 | Drywall |  |  |  |  | day | 2024-09-23 07:00 | 2024-10-04 17:00 | [12 empty] | 0 | 7 | qAsIg3w5AEOumfXo0dcBMg | MP4bMiL/YEKZD+G3Ld7szg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.4.2 | 41906516 | 41906514 | Finishes | 15 |  |  |  | day | 2024-10-18 07:00 | 2025-02-24 17:00 | [12 empty] | 1 | 7 | ctrO7S4JxEW20tbyk3yZSQ | MP4bMiL/YEKZD+G3Ld7szg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.4.3 | 41906517 | 41906514 | Elevator Vestibule - SE2 | 3 |  |  |  | day | 2024-09-30 07:00 | 2024-10-22 17:00 | [12 empty] | 2 | 7 | sFq3myErLkWLAYK3FqiOZQ | MP4bMiL/YEKZD+G3Ld7szg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.4.4 | 41906518 | 41906514 | Elevator Vestibule - PE01,02,03 | 5 |  |  |  | day | 2024-10-02 07:00 | 2024-11-15 17:00 | [12 empty] | 3 | 7 | 4wNvX26p1Eijc7+ZmLguGw | MP4bMiL/YEKZD+G3Ld7szg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.12.4.5 | 41906519 | 41906514 | Worklist/Punchlist | 21 |  |  |  | day | 2025-02-25 07:00 | 2025-04-03 17:00 | [12 empty] | 4 | 7 | l6kn1GHAHkmRLWMWxQhYzg | MP4bMiL/YEKZD+G3Ld7szg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13 | 41905621 | 41905608 | Level 48 - Residential Units | 25 |  |  |  | day | 2024-04-18 07:00 | 2025-04-10 17:00 | [12 empty] | 12 | 5 | LU1cTt6W5UG+Hg5AEq7OQw | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.1 | 41906520 | 41905621 | Interior Summary & Milestones | 2 |  |  |  | day | 2024-04-18 07:00 | 2025-03-24 17:00 | [12 empty] | 0 | 6 | 3yYjsPplmUqKGEbqHHfV9w | LU1cTt6W5UG+Hg5AEq7OQw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.2 | 41906521 | 41905621 | Roughs | 40 |  |  |  | day | 2024-07-26 07:00 | 2024-09-13 17:00 | [12 empty] | 1 | 6 | T9YQNKd/HUifuL+y+WPZHw | LU1cTt6W5UG+Hg5AEq7OQw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.2.1 | 41906522 | 41906521 | Facade - Curtainwall | 41 |  |  |  | day | [14 empty] | 0 | 7 | SULc8Du31EKyVV8AYfR3wQ | T9YQNKd/HUifuL+y+WPZHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.2.2 | 41906523 | 41906521 | Layout, Risers & Toptrack |  |  |  |  | day | 2024-07-26 07:00 | 2024-08-09 17:00 | [12 empty] | 1 | 7 | VIxIpod58Ui9ysH0zDPRgQ | T9YQNKd/HUifuL+y+WPZHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.2.3 | 41906524 | 41906521 | OH Rough |  |  |  |  | day | 2024-08-02 07:00 | 2024-08-21 17:00 | [12 empty] | 2 | 7 | c4Te/MOkokSQotGhuT2d0A | T9YQNKd/HUifuL+y+WPZHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.2.4 | 41906525 | 41906521 | Heat Pumps | 17 |  |  |  | day | [14 empty] | 3 | 7 | EJ4HZ8AT8UuaJiuERr+Omw | T9YQNKd/HUifuL+y+WPZHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.2.5 | 41906526 | 41906521 | Framing | 11 |  |  |  | day | 2024-08-12 07:00 | 2024-09-11 17:00 | [12 empty] | 4 | 7 | 2RSk+7fsOEKkjESUnoKa0w | T9YQNKd/HUifuL+y+WPZHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.2.6 | 41906527 | 41906521 | In-Wall Rough | 22 |  |  |  | day | 2024-08-26 07:00 | 2024-09-12 17:00 | [12 empty] | 5 | 7 | SLJCN/6R+0KXD6DC0nqjSg | T9YQNKd/HUifuL+y+WPZHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.2.7 | 41906528 | 41906521 | Inspections | 11 |  |  |  | day | 2024-09-10 07:00 | 2024-09-13 17:00 | [12 empty] | 6 | 7 | q13sj0IFvE6Lcs6NDPQ8WQ | T9YQNKd/HUifuL+y+WPZHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.3 | 41906529 | 41905621 | Unit Finishes |  |  |  |  | day | 2024-09-16 07:00 | 2025-03-24 17:00 | [12 empty] | 2 | 6 | re5OR1vXnU2OQqyKm/Bi1g | LU1cTt6W5UG+Hg5AEq7OQw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.3.1 | 41906530 | 41906529 | Drywall |  |  |  |  | day | 2024-09-16 07:00 | 2024-10-17 17:00 | [12 empty] | 0 | 7 | yjY8LTrRxUK4YgWS9uNsDg | re5OR1vXnU2OQqyKm/Bi1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.3.2 | 41906531 | 41906529 | Bathroom Waterproofing |  |  |  |  | day | 2024-09-17 07:00 | 2024-10-18 17:00 | [12 empty] | 1 | 7 | FJUUNfbTAkuDpVqJA1S9+Q | re5OR1vXnU2OQqyKm/Bi1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.3.3 | 41906532 | 41906529 | Paint | 18 |  |  |  | day | 2024-10-18 07:00 | 2024-11-01 17:00 | [12 empty] | 2 | 7 | BPYV2gAsUEOvHWz0DpZ8sw | re5OR1vXnU2OQqyKm/Bi1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.3.4 | 41906533 | 41906529 | Tile |  |  |  |  | day | 2024-11-04 07:00 | 2024-12-02 17:00 | [12 empty] | 3 | 7 | Q8rNGsyHUUeMI2Jidxuycg | re5OR1vXnU2OQqyKm/Bi1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.3.5 | 41906534 | 41906529 | Wood Flooring |  |  |  |  | day | 2024-12-03 07:00 | 2024-12-16 17:00 | [12 empty] | 4 | 7 | 47lEluvOfEqMP7xro5oqzg | re5OR1vXnU2OQqyKm/Bi1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.3.6 | 41906535 | 41906529 | Casework | 44 |  |  |  | day | 2024-12-17 07:00 | 2025-01-21 17:00 | [12 empty] | 5 | 7 | bN7Z17ihBUirXKhNhKh5UA | re5OR1vXnU2OQqyKm/Bi1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.3.7 | 41906536 | 41906529 | MEP Finishes | 7 |  |  |  | day | 2025-01-15 07:00 | 2025-02-06 17:00 | [12 empty] | 6 | 7 | opAUo9pHXkWt4+Hl6kK33Q | re5OR1vXnU2OQqyKm/Bi1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.3.8 | 41906537 | 41906529 | Doors & Trim | 28 |  |  |  | day | 2025-01-02 07:00 | 2025-02-07 17:00 | [12 empty] | 7 | 7 | nN8LsmcMuESpELu2cUv+7A | re5OR1vXnU2OQqyKm/Bi1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.3.9 | 41906538 | 41906529 | Finish Paint | 31 |  |  |  | day | 2025-02-03 07:00 | 2025-02-07 17:00 | [12 empty] | 8 | 7 | pu0p13+mREuVH638ldHTwg | re5OR1vXnU2OQqyKm/Bi1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.3.10 | 41906539 | 41906529 | Worklist/Punchlist |  |  |  |  | day | 2025-02-10 07:00 | 2025-03-24 17:00 | [12 empty] | 9 | 7 | r9MZYOVhGES1cNnCWo7nEA | re5OR1vXnU2OQqyKm/Bi1g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.4 | 41906540 | 41905621 | Corridors Finishes | 17 |  |  |  | day | 2024-09-30 07:00 | 2025-04-10 17:00 | [12 empty] | 3 | 6 | T05iNbi2ikqo/b/XbpFKZg | LU1cTt6W5UG+Hg5AEq7OQw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.4.1 | 41906541 | 41906540 | Drywall | 5 |  |  |  | day | 2024-09-30 07:00 | 2024-10-11 17:00 | [12 empty] | 0 | 7 | V+2wzd2WYE6lxlSVL47zDw | T05iNbi2ikqo/b/XbpFKZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.4.2 | 41906542 | 41906540 | Finishes |  |  |  |  | day | 2024-10-25 07:00 | 2025-03-03 17:00 | [12 empty] | 1 | 7 | XYT2VOI1o0OU+6uhp4tdkA | T05iNbi2ikqo/b/XbpFKZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.4.3 | 41906543 | 41906540 | Elevator Vestibule - SE2 | 18 |  |  |  | day | 2024-10-07 07:00 | 2024-10-29 17:00 | [12 empty] | 2 | 7 | bTO6Z2yY+UmsEFG9uF4Xqg | T05iNbi2ikqo/b/XbpFKZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.4.4 | 41906544 | 41906540 | Elevator Vestibule - PE01,02,03 | 21 |  |  |  | day | 2024-10-09 07:00 | 2024-11-22 17:00 | [12 empty] | 3 | 7 | pV3NBDmnNkOKO/2EnvsDoA | T05iNbi2ikqo/b/XbpFKZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.13.4.5 | 41906545 | 41906540 | Worklist/Punchlist |  |  |  |  | day | 2025-03-04 07:00 | 2025-04-10 17:00 | [12 empty] | 4 | 7 | c2jLgeDKXES1RV08y2hO0Q | T05iNbi2ikqo/b/XbpFKZg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14 | 41905622 | 41905608 | Level 49 - Residential Units | 31 |  |  |  | day | 2024-04-26 07:00 | 2025-04-17 17:00 | [12 empty] | 13 | 5 | 2Gs8Ph5z+0up/wLziAUuQw | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.1 | 41906546 | 41905622 | Interior Summary & Milestones |  |  |  |  | day | 2024-04-26 07:00 | 2025-03-31 17:00 | [12 empty] | 0 | 6 | mGgaTq1pp0an89a10GdySw | 2Gs8Ph5z+0up/wLziAUuQw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.2 | 41906547 | 41905622 | Roughs |  |  |  |  | day | 2024-08-02 07:00 | 2024-09-20 17:00 | [12 empty] | 1 | 6 | /xHl4CX+nkOMBZkbOx1XHw | 2Gs8Ph5z+0up/wLziAUuQw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.2.1 | 41906548 | 41906547 | Facade - Curtainwall | 27 |  |  |  | day | [14 empty] | 0 | 7 | e7LFrq11HEGL7zCsnMDbtw | /xHl4CX+nkOMBZkbOx1XHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.2.2 | 41906549 | 41906547 | Layout, Risers & Toptrack | 9 |  |  |  | day | 2024-08-02 07:00 | 2024-08-16 17:00 | [12 empty] | 1 | 7 | 1lFFmKVvp0uYhvPAUyycMA | /xHl4CX+nkOMBZkbOx1XHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.2.3 | 41906550 | 41906547 | OH Rough | 34 |  |  |  | day | 2024-08-09 07:00 | 2024-08-28 17:00 | [12 empty] | 2 | 7 | 3ADVHRd3XEi6o0miW6+LfA | /xHl4CX+nkOMBZkbOx1XHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.2.4 | 41906551 | 41906547 | Heat Pumps | 28 |  |  |  | day | [14 empty] | 3 | 7 | aqBNkQOPoUuToa954z7jbA | /xHl4CX+nkOMBZkbOx1XHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.2.5 | 41906552 | 41906547 | Framing | 14 |  |  |  | day | 2024-08-19 07:00 | 2024-09-18 17:00 | [12 empty] | 4 | 7 | JaHeek2nTUa1k3d1zixNHw | /xHl4CX+nkOMBZkbOx1XHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.2.6 | 41906553 | 41906547 | In-Wall Rough | 32 |  |  |  | day | 2024-09-03 07:00 | 2024-09-19 17:00 | [12 empty] | 5 | 7 | v8jfpL81b0CrvQLKsOnXOw | /xHl4CX+nkOMBZkbOx1XHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.2.7 | 41906554 | 41906547 | Inspections | 6 |  |  |  | day | 2024-09-17 07:00 | 2024-09-20 17:00 | [12 empty] | 6 | 7 | bo/klGLaekK0jN5mQlN7zQ | /xHl4CX+nkOMBZkbOx1XHw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.3 | 41906555 | 41905622 | Unit Finishes |  |  |  |  | day | 2024-09-23 07:00 | 2025-03-31 17:00 | [12 empty] | 2 | 6 | AJUozI98N0W2X5kJd+D7sQ | 2Gs8Ph5z+0up/wLziAUuQw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.3.1 | 41906556 | 41906555 | Drywall | 48 |  |  |  | day | 2024-09-23 07:00 | 2024-10-24 17:00 | [12 empty] | 0 | 7 | sFbu89xt/EuOoXnavzTG3A | AJUozI98N0W2X5kJd+D7sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.3.2 | 41906557 | 41906555 | Bathroom Waterproofing |  |  |  |  | day | 2024-09-24 07:00 | 2024-10-25 17:00 | [12 empty] | 1 | 7 | /Bkycuq1XU62+yWXAwxiYQ | AJUozI98N0W2X5kJd+D7sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.3.3 | 41906558 | 41906555 | Paint |  |  |  |  | day | 2024-10-25 07:00 | 2024-11-08 17:00 | [12 empty] | 2 | 7 | 0O9lOPc7rUyfbkxt5rg6yg | AJUozI98N0W2X5kJd+D7sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.3.4 | 41906559 | 41906555 | Tile | 30 |  |  |  | day | 2024-11-12 07:00 | 2024-12-09 17:00 | [12 empty] | 3 | 7 | wuVXs1EWQk6+DgOgSQsmIg | AJUozI98N0W2X5kJd+D7sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.3.5 | 41906560 | 41906555 | Wood Flooring |  |  |  |  | day | 2024-12-10 07:00 | 2024-12-23 17:00 | [12 empty] | 4 | 7 | ENVoRwUB10mRpqWgyGLYHQ | AJUozI98N0W2X5kJd+D7sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.3.6 | 41906561 | 41906555 | Casework |  |  |  |  | day | 2024-12-24 07:00 | 2025-01-28 17:00 | [12 empty] | 5 | 7 | XVe4frYw2ECQaMGqH+nOFA | AJUozI98N0W2X5kJd+D7sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.3.7 | 41906562 | 41906555 | MEP Finishes | 36 |  |  |  | day | 2025-01-22 07:00 | 2025-02-13 17:00 | [12 empty] | 6 | 7 | HxHFnHa+LUa7KTujniAtZw | AJUozI98N0W2X5kJd+D7sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.3.8 | 41906563 | 41906555 | Doors & Trim | 3 |  |  |  | day | 2025-01-09 07:00 | 2025-02-14 17:00 | [12 empty] | 7 | 7 | VsPluzXKhUq7Yu/VQ/cTzg | AJUozI98N0W2X5kJd+D7sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.3.9 | 41906564 | 41906555 | Finish Paint |  |  |  |  | day | 2025-02-10 07:00 | 2025-02-14 17:00 | [12 empty] | 8 | 7 | yu1rlYoX9UWajzDrYL2t+w | AJUozI98N0W2X5kJd+D7sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.3.10 | 41906565 | 41906555 | Worklist/Punchlist | 43 |  |  |  | day | 2025-02-18 07:00 | 2025-03-31 17:00 | [12 empty] | 9 | 7 | ss6XzMTpX0mF0avppABPhQ | AJUozI98N0W2X5kJd+D7sQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.4 | 41906566 | 41905622 | Corridors Finishes | 19 |  |  |  | day | 2024-10-07 07:00 | 2025-04-17 17:00 | [12 empty] | 3 | 6 | lSpYdZ/EA0OngtvRa+JBkw | 2Gs8Ph5z+0up/wLziAUuQw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.4.1 | 41906567 | 41906566 | Drywall | 23 |  |  |  | day | 2024-10-07 07:00 | 2024-10-21 17:00 | [12 empty] | 0 | 7 | lijWlLDx1Ea3iX68Ad+wkw | lSpYdZ/EA0OngtvRa+JBkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.4.2 | 41906568 | 41906566 | Finishes |  |  |  |  | day | 2024-11-01 07:00 | 2025-03-10 17:00 | [12 empty] | 1 | 7 | 9PgkAkHrAEqImkFF7tobPw | lSpYdZ/EA0OngtvRa+JBkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.4.3 | 41906569 | 41906566 | Elevator Vestibule - SE2 |  |  |  |  | day | 2024-10-15 07:00 | 2024-11-05 17:00 | [12 empty] | 2 | 7 | o7TPBQtMMkm8BJWc6GXKUA | lSpYdZ/EA0OngtvRa+JBkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.4.4 | 41906570 | 41906566 | Elevator Vestibule - PE01,02,03 | 31 |  |  |  | day | 2024-10-17 07:00 | 2024-12-02 17:00 | [12 empty] | 3 | 7 | nQr0l1zdK0OY4P1+ZznQ+A | lSpYdZ/EA0OngtvRa+JBkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.14.4.5 | 41906571 | 41906566 | Worklist/Punchlist | 40 |  |  |  | day | 2025-03-11 07:00 | 2025-04-17 17:00 | [12 empty] | 4 | 7 | GDtLD230aU2NBt033ChMKA | lSpYdZ/EA0OngtvRa+JBkw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15 | 41905623 | 41905608 | Level 50 - Residential Units |  |  |  |  | day | 2024-05-06 07:00 | 2025-04-25 17:00 | [12 empty] | 14 | 5 | jC0uxlzW10CT7KbOq+c+KQ | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.1 | 41906572 | 41905623 | Interior Summary & Milestones | 33 |  |  |  | day | 2024-05-06 07:00 | 2025-04-07 17:00 | [12 empty] | 0 | 6 | F0zIpqyVgUa8JEHqj39Cvw | jC0uxlzW10CT7KbOq+c+KQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.2 | 41906573 | 41905623 | Roughs |  |  |  |  | day | 2024-08-09 07:00 | 2024-09-27 17:00 | [12 empty] | 1 | 6 | 7ns+xWWO8EWHqSwKxSeSdw | jC0uxlzW10CT7KbOq+c+KQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.2.1 | 41906574 | 41906573 | Facade - Curtainwall | 1 |  |  |  | day | [14 empty] | 0 | 7 | 8bzLlzGaZEOmlWeVjA8hMA | 7ns+xWWO8EWHqSwKxSeSdw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.2.2 | 41906575 | 41906573 | Layout, Risers & Toptrack | 14 |  |  |  | day | 2024-08-09 07:00 | 2024-08-23 17:00 | [12 empty] | 1 | 7 | RE1geILChkie0E1IlxafeQ | 7ns+xWWO8EWHqSwKxSeSdw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.2.3 | 41906576 | 41906573 | OH Rough | 33 |  |  |  | day | 2024-08-16 07:00 | 2024-09-05 17:00 | [12 empty] | 2 | 7 | 0jsbdqNI50ydxoh182T52A | 7ns+xWWO8EWHqSwKxSeSdw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.2.4 | 41906577 | 41906573 | Heat Pumps |  |  |  |  | day | [14 empty] | 3 | 7 | OrYm9dFuP0GlcKEqs8PiyA | 7ns+xWWO8EWHqSwKxSeSdw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.2.5 | 41906578 | 41906573 | Framing |  |  |  |  | day | 2024-08-26 07:00 | 2024-09-25 17:00 | [12 empty] | 4 | 7 | NycV6H7ZoEC622aMztdI4Q | 7ns+xWWO8EWHqSwKxSeSdw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.2.6 | 41906579 | 41906573 | In-Wall Rough |  |  |  |  | day | 2024-09-10 07:00 | 2024-09-26 17:00 | [12 empty] | 5 | 7 | boiX0SW6MEGbaV4W/aNJCg | 7ns+xWWO8EWHqSwKxSeSdw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.2.7 | 41906580 | 41906573 | Inspections | 41 |  |  |  | day | 2024-09-24 07:00 | 2024-09-27 17:00 | [12 empty] | 6 | 7 | fsT/w5foEkiRG/GObCO0uw | 7ns+xWWO8EWHqSwKxSeSdw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.3 | 41906581 | 41905623 | Unit Finishes | 11 |  |  |  | day | 2024-09-30 07:00 | 2025-04-07 17:00 | [12 empty] | 2 | 6 | ap6U3vFXDEe11VAiXG/L5g | jC0uxlzW10CT7KbOq+c+KQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.3.1 | 41906582 | 41906581 | Drywall | 2 |  |  |  | day | 2024-09-30 07:00 | 2024-10-31 17:00 | [12 empty] | 0 | 7 | milHS0wzx0CPZ/buoHvFzw | ap6U3vFXDEe11VAiXG/L5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.3.2 | 41906583 | 41906581 | Bathroom Waterproofing |  |  |  |  | day | 2024-10-01 07:00 | 2024-11-01 17:00 | [12 empty] | 1 | 7 | OkLSHJ0ZvkiFDrjUA1g5nQ | ap6U3vFXDEe11VAiXG/L5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.3.3 | 41906584 | 41906581 | Paint | 17 |  |  |  | day | 2024-11-01 07:00 | 2024-11-18 17:00 | [12 empty] | 2 | 7 | hGMLQMItAECfuU6S8qp3fw | ap6U3vFXDEe11VAiXG/L5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.3.4 | 41906585 | 41906581 | Tile | 39 |  |  |  | day | 2024-11-19 07:00 | 2024-12-16 17:00 | [12 empty] | 3 | 7 | vbSOMsXGZ0SiHJgW/T9Y5Q | ap6U3vFXDEe11VAiXG/L5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.3.5 | 41906586 | 41906581 | Wood Flooring |  |  |  |  | day | 2024-12-17 07:00 | 2024-12-31 17:00 | [12 empty] | 4 | 7 | TQYx8S5n7Eq8T1G04Zd9rg | ap6U3vFXDEe11VAiXG/L5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.3.6 | 41906587 | 41906581 | Casework | 14 |  |  |  | day | 2025-01-02 07:00 | 2025-02-04 17:00 | [12 empty] | 5 | 7 | TsiQ/jhPmkSUJ0JKOF3cqA | ap6U3vFXDEe11VAiXG/L5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.3.7 | 41906588 | 41906581 | MEP Finishes | 32 |  |  |  | day | 2025-01-29 07:00 | 2025-02-21 17:00 | [12 empty] | 6 | 7 | DgBPcFBzK0ihVo8isB/sPg | ap6U3vFXDEe11VAiXG/L5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.3.8 | 41906589 | 41906581 | Doors & Trim | 34 |  |  |  | day | 2025-01-16 07:00 | 2025-02-24 17:00 | [12 empty] | 7 | 7 | tx4ZdUC4tUqhf2aEObFq1g | ap6U3vFXDEe11VAiXG/L5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.3.9 | 41906590 | 41906581 | Finish Paint | 25 |  |  |  | day | 2025-02-18 07:00 | 2025-02-24 17:00 | [12 empty] | 8 | 7 | K+ykIcqjgUOB07bJclvktQ | ap6U3vFXDEe11VAiXG/L5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.3.10 | 41906591 | 41906581 | Worklist/Punchlist | 7 |  |  |  | day | 2025-02-25 07:00 | 2025-04-07 17:00 | [12 empty] | 9 | 7 | JsKpmMQXGkix1a/Q/Rnnyg | ap6U3vFXDEe11VAiXG/L5g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.4 | 41906592 | 41905623 | Corridors Finishes | 35 |  |  |  | day | 2024-10-15 07:00 | 2025-04-25 17:00 | [12 empty] | 3 | 6 | XwEWIh4YUE+fZ+G56tlR1A | jC0uxlzW10CT7KbOq+c+KQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.4.1 | 41906593 | 41906592 | Drywall | 47 |  |  |  | day | 2024-10-15 07:00 | 2024-10-28 17:00 | [12 empty] | 0 | 7 | jxCmOndDXEWYYwq5bgpUdA | XwEWIh4YUE+fZ+G56tlR1A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.4.2 | 41906594 | 41906592 | Finishes |  |  |  |  | day | 2024-11-08 07:00 | 2025-03-17 17:00 | [12 empty] | 1 | 7 | 1bnnno2xaEaD5iotEuseeA | XwEWIh4YUE+fZ+G56tlR1A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.4.3 | 41906595 | 41906592 | Elevator Vestibule - SE2 | 22 |  |  |  | day | 2024-10-22 07:00 | 2024-11-13 17:00 | [12 empty] | 2 | 7 | 8tAubAyc6U+T5IH7kfjFFQ | XwEWIh4YUE+fZ+G56tlR1A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.4.4 | 41906596 | 41906592 | Elevator Vestibule - PE01,02,03 |  |  |  |  | day | 2024-10-24 07:00 | 2024-12-09 17:00 | [12 empty] | 3 | 7 | /diKTprrwEyAG//n+5Xucw | XwEWIh4YUE+fZ+G56tlR1A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.15.4.5 | 41906597 | 41906592 | Worklist/Punchlist |  |  |  |  | day | 2025-03-18 07:00 | 2025-04-25 17:00 | [12 empty] | 4 | 7 | Oel4xqMwVU6aTNwK+hA4hw | XwEWIh4YUE+fZ+G56tlR1A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16 | 41905624 | 41905608 | Level 51 - Residential Units | 13 |  |  |  | day | 2024-05-14 07:00 | 2025-05-01 17:00 | [12 empty] | 15 | 5 | AkEebUTxIUaB2Nk8UkqTVg | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.1 | 41906598 | 41905624 | Interior Summary & Milestones | 13 |  |  |  | day | 2024-05-14 07:00 | 2025-04-14 17:00 | [12 empty] | 0 | 6 | btU/0Y2vxEuVj8UPM8/IXQ | AkEebUTxIUaB2Nk8UkqTVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.2 | 41906599 | 41905624 | Roughs | 1 |  |  |  | day | 2024-08-16 07:00 | 2024-10-04 17:00 | [12 empty] | 1 | 6 | AWh/xiTEfEWwzJq1UNHc8g | AkEebUTxIUaB2Nk8UkqTVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.2.1 | 41906600 | 41906599 | Facade - Curtainwall | 36 |  |  |  | day | [14 empty] | 0 | 7 | u2iXyXDpR02gjxHo25qp9g | AWh/xiTEfEWwzJq1UNHc8g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.2.2 | 41906601 | 41906599 | Layout, Risers & Toptrack | 4 |  |  |  | day | 2024-08-16 07:00 | 2024-08-30 17:00 | [12 empty] | 1 | 7 | y8liWSQHBU+1HPx5Oc3p7Q | AWh/xiTEfEWwzJq1UNHc8g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.2.3 | 41906602 | 41906599 | OH Rough |  |  |  |  | day | 2024-08-23 07:00 | 2024-09-12 17:00 | [12 empty] | 2 | 7 | VYV9M06MSU29hrQa1EQk4g | AWh/xiTEfEWwzJq1UNHc8g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.2.4 | 41906603 | 41906599 | Heat Pumps |  |  |  |  | day | [14 empty] | 3 | 7 | Vqv+b11DE0qoHIfjWN+Riw | AWh/xiTEfEWwzJq1UNHc8g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.2.5 | 41906604 | 41906599 | Framing |  |  |  |  | day | 2024-09-03 07:00 | 2024-10-02 17:00 | [12 empty] | 4 | 7 | WsjAe0oTl0CTOJzmLswBFQ | AWh/xiTEfEWwzJq1UNHc8g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.2.6 | 41906605 | 41906599 | In-Wall Rough | 46 |  |  |  | day | 2024-09-17 07:00 | 2024-10-03 17:00 | [12 empty] | 5 | 7 | nWWPJWKkVki5MY4y0pt5dQ | AWh/xiTEfEWwzJq1UNHc8g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.2.7 | 41906606 | 41906599 | Inspections | 13 |  |  |  | day | 2024-10-01 07:00 | 2024-10-04 17:00 | [12 empty] | 6 | 7 | nGqeyVQ0gkKCUz5dzeHBjA | AWh/xiTEfEWwzJq1UNHc8g | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.3 | 41906607 | 41905624 | Unit Finishes | 38 |  |  |  | day | 2024-10-07 07:00 | 2025-04-14 17:00 | [12 empty] | 2 | 6 | 39aKhetrjE+R+3xnL3nl9Q | AkEebUTxIUaB2Nk8UkqTVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.3.1 | 41906608 | 41906607 | Drywall |  |  |  |  | day | 2024-10-07 07:00 | 2024-11-07 17:00 | [12 empty] | 0 | 7 | eFdVOY7+OkKkdEXHnfMvMQ | 39aKhetrjE+R+3xnL3nl9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.3.2 | 41906609 | 41906607 | Bathroom Waterproofing | 19 |  |  |  | day | 2024-10-08 07:00 | 2024-11-08 17:00 | [12 empty] | 1 | 7 | rzCV6DJfW0S3ZZyVp4GL3A | 39aKhetrjE+R+3xnL3nl9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.3.3 | 41906610 | 41906607 | Paint |  |  |  |  | day | 2024-11-08 07:00 | 2024-11-25 17:00 | [12 empty] | 2 | 7 | uFFEV38qz0qugAfyiZHbAQ | 39aKhetrjE+R+3xnL3nl9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.3.4 | 41906611 | 41906607 | Tile | 38 |  |  |  | day | 2024-11-26 07:00 | 2024-12-23 17:00 | [12 empty] | 3 | 7 | 7jJ/SEQ080SmiEPTsqCi2w | 39aKhetrjE+R+3xnL3nl9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.3.5 | 41906612 | 41906607 | Wood Flooring | 5 |  |  |  | day | 2024-12-24 07:00 | 2025-01-08 17:00 | [12 empty] | 4 | 7 | 5jHJdeyJAECoXfqG3HVZSw | 39aKhetrjE+R+3xnL3nl9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.3.6 | 41906613 | 41906607 | Casework | 16 |  |  |  | day | 2025-01-09 07:00 | 2025-02-11 17:00 | [12 empty] | 5 | 7 | gDwUovClmE+3tP0na9TexA | 39aKhetrjE+R+3xnL3nl9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.3.7 | 41906614 | 41906607 | MEP Finishes | 24 |  |  |  | day | 2025-02-05 07:00 | 2025-02-28 17:00 | [12 empty] | 6 | 7 | mX0FOoX5sU64n3nntSeGtw | 39aKhetrjE+R+3xnL3nl9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.3.8 | 41906615 | 41906607 | Doors & Trim |  |  |  |  | day | 2025-01-23 07:00 | 2025-03-03 17:00 | [12 empty] | 7 | 7 | CRlcBbXn20OvCgWEdXCE+Q | 39aKhetrjE+R+3xnL3nl9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.3.9 | 41906616 | 41906607 | Finish Paint | 1 |  |  |  | day | 2025-02-25 07:00 | 2025-03-03 17:00 | [12 empty] | 8 | 7 | usZxlkV8g0a/g2YJfwLC/Q | 39aKhetrjE+R+3xnL3nl9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.3.10 | 41906617 | 41906607 | Worklist/Punchlist | 34 |  |  |  | day | 2025-03-04 07:00 | 2025-04-14 17:00 | [12 empty] | 9 | 7 | yOcfJ0DDmUGxRD53DFWn+Q | 39aKhetrjE+R+3xnL3nl9Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.4 | 41906618 | 41905624 | Corridors Finishes | 36 |  |  |  | day | 2024-10-22 07:00 | 2025-05-01 17:00 | [12 empty] | 3 | 6 | SM/GdB42A025+XidOfLFCg | AkEebUTxIUaB2Nk8UkqTVg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.4.1 | 41906619 | 41906618 | Drywall |  |  |  |  | day | 2024-10-22 07:00 | 2024-11-04 17:00 | [12 empty] | 0 | 7 | Mqqv1T/1dEiMLwYgwjO2pg | SM/GdB42A025+XidOfLFCg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.4.2 | 41906620 | 41906618 | Finishes | 0 |  |  |  | day | 2024-11-18 07:00 | 2025-03-24 17:00 | [12 empty] | 1 | 7 | a257Jvuzokufzk1N7VcyEA | SM/GdB42A025+XidOfLFCg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.4.3 | 41906621 | 41906618 | Elevator Vestibule - SE2 | 39 |  |  |  | day | 2024-10-29 07:00 | 2024-11-20 17:00 | [12 empty] | 2 | 7 | Ho1Gh3K5V0ityoZlPqPelg | SM/GdB42A025+XidOfLFCg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.4.4 | 41906622 | 41906618 | Elevator Vestibule - PE01,02,03 |  |  |  |  | day | 2024-10-31 07:00 | 2024-12-16 17:00 | [12 empty] | 3 | 7 | Ee2Pmz9AjU6Nt9nqPbXgzA | SM/GdB42A025+XidOfLFCg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.16.4.5 | 41906623 | 41906618 | Worklist/Punchlist | 35 |  |  |  | day | 2025-03-25 07:00 | 2025-05-01 17:00 | [12 empty] | 4 | 7 | X65WE7sVjEu1y2ncPe4FsQ | SM/GdB42A025+XidOfLFCg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.13.17 | 41905625 | 41905608 | Level 52 - Lower Penthouse | 44 |  |  |  | day | [14 empty] | 16 | 5 | t50Q2KDOj0eLoZOHCkVX6A | jYO7/2WAnky6Fktzlg2pzw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14 | 41904256 | 41904236 | TOWER EQUIPMENT | 22 |  |  |  | day | 2023-10-24 07:00 | 2024-12-03 17:00 | [12 empty] | 13 | 4 | kBUiuWZkRE6ihZJFVHh8hw | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.1 | 41906201 | 41904256 | All Elevator Summaries | 46 |  |  |  | day | 2024-01-08 07:00 | 2024-12-03 17:00 | [12 empty] | 0 | 5 | IHQIfqCfMEal96G7cpHyaQ | kBUiuWZkRE6ihZJFVHh8hw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.2 | 43171927 | 41904256 | PE25 (Level 09-10) | 30 |  |  |  | day | 2024-04-10 07:00 | 2024-05-22 17:00 | [12 empty] | 1 | 5 | Zfa3QA/TPECeW9/wVT+rSA | kBUiuWZkRE6ihZJFVHh8hw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.3 | 41905729 | 41904256 | Elevator - Crash Decks | 10 |  |  |  | day | 2023-10-24 07:00 | 2024-04-23 17:00 | [12 empty] | 2 | 5 | ZLVgAt8HgkC2oQQxRlU0Lg | kBUiuWZkRE6ihZJFVHh8hw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.3.1 | 41905739 | 41905729 | Level 20 |  |  |  |  | day | 2023-10-24 07:00 | 2023-12-26 17:00 | [12 empty] | 0 | 6 | FjZut0MeD02fH+D1rF9sJg | ZLVgAt8HgkC2oQQxRlU0Lg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.3.2 | 41906163 | 41905729 | Level 36 (SE-02) | 2 |  |  |  | day | 2023-12-08 07:00 | 2024-04-23 17:00 | [12 empty] | 1 | 6 | 4+AeWJUdtEC2klhwtNkang | ZLVgAt8HgkC2oQQxRlU0Lg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4 | 41905730 | 41904256 | 1st Group (PE-04,05,06) (PE-07,08,09) (PE-13,14,15)(SE-02,SE-03) |  |  |  |  | day | 2023-12-26 07:00 | 2024-12-03 17:00 | [12 empty] | 3 | 5 | Q7pqa8EUM0SVYoXYJk8CWA | kBUiuWZkRE6ihZJFVHh8hw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.1 | 41905752 | 41905730 | 1st Group Summary | 15 |  |  |  | day | 2024-01-08 07:00 | 2024-12-03 17:00 | [12 empty] | 0 | 6 | 858vAHdYWkmUJSkaGSefuA | Q7pqa8EUM0SVYoXYJk8CWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.2 | 41905745 | 41905730 | OFFICE MID RISE PASSENGER (PE-13,14,15) | 9 |  |  |  | day | 2023-12-26 07:00 | 2024-08-09 17:00 | [12 empty] | 1 | 6 | UEigfL1+bU2xfhbdwaXlaQ | Q7pqa8EUM0SVYoXYJk8CWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.2.1 | 41905746 | 41905745 | Shaft Scope | 28 |  |  |  | day | 2023-12-26 07:00 | 2024-06-17 17:00 | [12 empty] | 0 | 7 | 2yxAbo7+n0+ydHXYIl26ag | UEigfL1+bU2xfhbdwaXlaQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.2.1.1 | 41905747 | 41905746 | Level P3 - Elevator Pit Work |  |  |  |  | day | 2023-12-26 07:00 | 2024-01-19 17:00 | [12 empty] | 0 | 8 | f09ZiKIWd0yHs+wvx87asw | 2yxAbo7+n0+ydHXYIl26ag | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.2.1.2 | 41905748 | 41905746 | Level 09 to18 | 11 |  |  |  | day | 2024-01-08 07:00 | 2024-03-13 17:00 | [12 empty] | 1 | 8 | AsZU/OugykWyiDcavbZ34A | 2yxAbo7+n0+ydHXYIl26ag | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.2.1.3 | 41905749 | 41905746 | Level 19 to 25 | 29 |  |  |  | day | 2024-04-24 07:00 | 2024-05-20 17:00 | [12 empty] | 2 | 8 | QYxSRzMEhkK6fiwrIj+6WA | 2yxAbo7+n0+ydHXYIl26ag | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.2.1.4 | 41905751 | 41905746 | Level 26 to 35 | 40 |  |  |  | day | 2024-05-09 07:00 | 2024-06-17 17:00 | [12 empty] | 3 | 8 | 3gdCje9kdkGb6JDOKgR4Gg | 2yxAbo7+n0+ydHXYIl26ag | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.2.2 | 41905750 | 41905745 | PE13-15 - Level 35 - EMR Activities | 0 |  |  |  | day | 2024-05-10 07:00 | 2024-08-09 17:00 | [12 empty] | 1 | 7 | 8HbnLzu90UO6IS6ulbahZg | UEigfL1+bU2xfhbdwaXlaQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.3 | 41906185 | 41905730 | HIGH RISE PASSENGER (PE-01,02,03) (TC-1 CONSTRAINT) |  |  |  |  | day | 2024-04-02 07:00 | 2024-12-03 17:00 | [12 empty] | 2 | 6 | JGW84Kwa8UWgFTmjhYrv8Q | Q7pqa8EUM0SVYoXYJk8CWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.3.1 | 41906186 | 41906185 | Shaft Scope | 19 |  |  |  | day | 2024-04-02 07:00 | 2024-09-10 17:00 | [12 empty] | 0 | 7 | W7j8v5G55E6vmhP5vH3Oug | JGW84Kwa8UWgFTmjhYrv8Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.3.1.1 | 41906187 | 41906186 | Level P3 - Elevator Pit Work | 7 |  |  |  | day | 2024-04-02 07:00 | 2024-04-16 17:00 | [12 empty] | 0 | 8 | ro4UlMc40EGKwGOg4fglbQ | W7j8v5G55E6vmhP5vH3Oug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.3.1.2 | 41906188 | 41906186 | Level 09 to18 | 42 |  |  |  | day | 2024-04-02 07:00 | 2024-05-31 17:00 | [12 empty] | 1 | 8 | mz6YypIxrUaZAVj98FGu+A | W7j8v5G55E6vmhP5vH3Oug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.3.1.3 | 41906189 | 41906186 | Level 19 to 25 |  |  |  |  | day | 2024-05-17 07:00 | 2024-06-03 17:00 | [12 empty] | 2 | 8 | aAdlasIcAUCd6P3gKeztsw | W7j8v5G55E6vmhP5vH3Oug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.3.1.4 | 41906190 | 41906186 | Level 26 to 35 | 0 |  |  |  | day | 2024-06-04 07:00 | 2024-06-27 17:00 | [12 empty] | 3 | 8 | MqqeOVPEa0KkpJz1lrxE+A | W7j8v5G55E6vmhP5vH3Oug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.3.1.5 | 41906191 | 41906186 | Level 36 to 52 | 19 |  |  |  | day | 2024-06-28 07:00 | 2024-09-10 17:00 | [12 empty] | 4 | 8 | AnFpcNVCZU6gP7TO3Yk4jA | W7j8v5G55E6vmhP5vH3Oug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.3.2 | 41906192 | 41906185 | PE01-13 - Level 52 - EMR Activities | 27 |  |  |  | day | 2024-07-11 07:00 | 2024-12-03 17:00 | [12 empty] | 1 | 7 |  | JGW84Kwa8UWgFTmjhYrv8Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.4 | 41906173 | 41905730 | MID RISE SERVICE (SE-01) (TC-1 CONSTRAINT) | 42 |  |  |  | day | 2024-04-02 07:00 | 2024-09-19 17:00 | [12 empty] | 3 | 6 | 12xWFEJM7UiTGFcXdCsO6A | Q7pqa8EUM0SVYoXYJk8CWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.4.1 | 41906174 | 41906173 | Shaft Scope | 36 |  |  |  | day | 2024-04-02 07:00 | 2024-07-11 17:00 | [12 empty] | 0 | 7 | qiBvQB/+GkK4smNKucUDSQ | 12xWFEJM7UiTGFcXdCsO6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.4.1.1 | 41906175 | 41906174 | Level P3 - Elevator Pit Work | 46 |  |  |  | day | 2024-04-02 07:00 | 2024-04-16 17:00 | [12 empty] | 0 | 8 | gwoMsP2V5kSFhtDyjzN7vA | qiBvQB/+GkK4smNKucUDSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.4.1.2 | 41906176 | 41906174 | Level 09 to18 | 36 |  |  |  | day | 2024-04-02 07:00 | 2024-05-31 17:00 | [12 empty] | 1 | 8 | 2mVug/o7UkSJN7iSSeMmhw | qiBvQB/+GkK4smNKucUDSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.4.1.3 | 41906177 | 41906174 | Level 19 to 25 | 11 |  |  |  | day | 2024-05-17 07:00 | 2024-06-13 17:00 | [12 empty] | 2 | 8 | CRJLRz1Ek0uvWkAmrAI+xg | qiBvQB/+GkK4smNKucUDSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.4.1.4 | 41906178 | 41906174 | Level 26 to 35 | 36 |  |  |  | day | 2024-06-04 07:00 | 2024-07-11 17:00 | [12 empty] | 3 | 8 | t/cMmSxcz02l4otp2ypwXg | qiBvQB/+GkK4smNKucUDSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.4.1.5 | 41906179 | 41906174 | Level 36 to 52 | 48 |  |  |  | day | [14 empty] | 4 | 8 | fzdmdJD5j0O3iCL3/HEiPQ | qiBvQB/+GkK4smNKucUDSQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.4.2 | 41906180 | 41906173 | SE01 - Level 35 - EMR Activities | 48 |  |  |  | day | 2024-05-29 07:00 | 2024-09-19 17:00 | [12 empty] | 1 | 7 | AKB7WVwsJkaWnAkjbVEqsQ | 12xWFEJM7UiTGFcXdCsO6A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.5 | 41906164 | 41905730 | MID RISE SERVICE (SE-03) | 43 |  |  |  | day | 2023-12-26 07:00 | 2024-08-15 17:00 | [12 empty] | 4 | 6 | 7t+h4641wkmhLdvvvmc0ug | Q7pqa8EUM0SVYoXYJk8CWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.5.1 | 41906165 | 41906164 | Shaft Scope | 27 |  |  |  | day | 2023-12-26 07:00 | 2024-06-18 17:00 | [12 empty] | 0 | 7 | e5C/1yr6t06yzLVha/0QNQ | 7t+h4641wkmhLdvvvmc0ug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.5.1.1 | 41906166 | 41906165 | Level P3 - Elevator Pit Work | 46 |  |  |  | day | 2023-12-26 07:00 | 2024-03-22 17:00 | [12 empty] | 0 | 8 | tBDDuyk0mUyWX5xneIqXGg | e5C/1yr6t06yzLVha/0QNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.5.1.2 | 41906167 | 41906165 | Level 09 to18 |  |  |  |  | day | 2024-03-11 07:00 | 2024-05-08 17:00 | [12 empty] | 1 | 8 | SpQrkeRSx0mRgVrCjll1pA | e5C/1yr6t06yzLVha/0QNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.5.1.3 | 41906168 | 41906165 | Level 19 to 25 | 5 |  |  |  | day | 2024-04-25 07:00 | 2024-05-21 17:00 | [12 empty] | 2 | 8 | YA9aND25/UCNrrwq2bTpyA | e5C/1yr6t06yzLVha/0QNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.5.1.4 | 41906169 | 41906165 | Level 26 to 35 | 43 |  |  |  | day | 2024-05-10 07:00 | 2024-06-18 17:00 | [12 empty] | 3 | 8 | 7STSdFs480GdmbZtAj/Xiw | e5C/1yr6t06yzLVha/0QNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.5.1.5 | 41906170 | 41906165 | Level 36 to 52 | 19 |  |  |  | day | [14 empty] | 4 | 8 | IVRfbe0rVUmi4Z7EYT1T+w | e5C/1yr6t06yzLVha/0QNQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.5.2 | 41906171 | 41906164 | SE03 - Level 35 - EMR Activities | 49 |  |  |  | day | 2024-04-24 07:00 | 2024-08-15 17:00 | [12 empty] | 1 | 7 | vkxGzIr9VE2MJ1gGS6nmbA | 7t+h4641wkmhLdvvvmc0ug | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.6 | 41906193 | 41905730 | OFFICE MID RISE PASSENGER (PE-10,11,12) (TC-1 CONSTRAINT) | 13 |  |  |  | day | 2024-04-02 07:00 | 2024-09-05 17:00 | [12 empty] | 5 | 6 | k9q3YjqfbkindaIylE+7+A | Q7pqa8EUM0SVYoXYJk8CWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.6.1 | 41906194 | 41906193 | Shaft Scope | 1 |  |  |  | day | 2024-04-02 07:00 | 2024-07-11 17:00 | [12 empty] | 0 | 7 | j2dQghT84k+1Q3bjFloDHQ | k9q3YjqfbkindaIylE+7+A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.6.1.1 | 41906195 | 41906194 | Level P3 - Elevator Pit Work | 8 |  |  |  | day | 2024-04-02 07:00 | 2024-04-16 17:00 | [12 empty] | 0 | 8 | NUT/f/Blc0ix5fSz7kM2Uw | j2dQghT84k+1Q3bjFloDHQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.6.1.2 | 41906196 | 41906194 | Level 09 to18 | 36 |  |  |  | day | 2024-04-02 07:00 | 2024-05-31 17:00 | [12 empty] | 1 | 8 | CS22ZJhgbkygO1DaVjhHYg | j2dQghT84k+1Q3bjFloDHQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.6.1.3 | 41906197 | 41906194 | Level 19 to 25 | 19 |  |  |  | day | 2024-05-17 07:00 | 2024-06-13 17:00 | [12 empty] | 2 | 8 | V2SNcNVRCEiUGVsN/Q0Q6w | j2dQghT84k+1Q3bjFloDHQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.6.1.4 | 41906198 | 41906194 | Level 26 to 35 | 25 |  |  |  | day | 2024-06-04 07:00 | 2024-07-11 17:00 | [12 empty] | 3 | 8 | UIaxdAPay0+h6/pp7bnlyA | j2dQghT84k+1Q3bjFloDHQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.6.1.5 | 41906199 | 41906194 | Level 36 to 52 | 28 |  |  |  | day | [14 empty] | 4 | 8 | EdKnX79TC0Kdzsfjn1zJ+g | j2dQghT84k+1Q3bjFloDHQ | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.6.2 | 41906200 | 41906193 | PE10-12 - Level 35 - EMR Activities |  |  |  |  | day | 2024-05-14 07:00 | 2024-09-05 17:00 | [12 empty] | 1 | 7 | /q7ENpGbm0WAMpfYoWNakg | k9q3YjqfbkindaIylE+7+A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.7 | 41906155 | 41905730 | HIGH RISE SERVICE (SE-02) | 34 |  |  |  | day | 2023-12-26 07:00 | 2024-12-03 17:00 | [12 empty] | 6 | 6 | fMtBuqWDA0Ce7rMyZYyI1A | Q7pqa8EUM0SVYoXYJk8CWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.7.1 | 41906156 | 41906155 | Shaft Scope |  |  |  |  | day | 2023-12-26 07:00 | 2024-09-05 17:00 | [12 empty] | 0 | 7 | FMsu8L/hGEOmFy9Suw2Kww | fMtBuqWDA0Ce7rMyZYyI1A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.7.1.1 | 41906157 | 41906156 | Level P3 - Elevator Pit Work | 36 |  |  |  | day | 2023-12-26 07:00 | 2024-04-23 17:00 | [12 empty] | 0 | 8 | 5WMdy8RnrkyigTnOfAJecQ | FMsu8L/hGEOmFy9Suw2Kww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.7.1.2 | 41906158 | 41906156 | Level 09 to18 | 4 |  |  |  | day | 2024-03-11 07:00 | 2024-05-08 17:00 | [12 empty] | 1 | 8 | T56axuG13E+kXxBCZcf2XQ | FMsu8L/hGEOmFy9Suw2Kww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.7.1.3 | 41906159 | 41906156 | Level 19 to 25 |  |  |  |  | day | 2024-04-25 07:00 | 2024-05-21 17:00 | [12 empty] | 2 | 8 | Wh6m90ovpU+CAW8zOhL7pQ | FMsu8L/hGEOmFy9Suw2Kww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.7.1.4 | 41906160 | 41906156 | Level 26 to 35 | 48 |  |  |  | day | 2024-05-10 07:00 | 2024-06-18 17:00 | [12 empty] | 3 | 8 | 5wtGEys8QkiEvyGHbMghYg | FMsu8L/hGEOmFy9Suw2Kww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.7.1.5 | 41906162 | 41906156 | Level 36 to 52 | 13 |  |  |  | day | 2024-07-18 07:00 | 2024-09-05 17:00 | [12 empty] | 4 | 8 | ai9cGQ5FoECOoqBZrb12cA | FMsu8L/hGEOmFy9Suw2Kww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.7.2 | 41906161 | 41906155 | SE02 - Level 52 - EMR Activities | 11 |  |  |  | day | 2024-07-18 07:00 | 2024-12-03 17:00 | [12 empty] | 1 | 7 | O+7KZw5O9kOccm4bZMc+aw | fMtBuqWDA0Ce7rMyZYyI1A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.8 | 41905733 | 41905730 | OFFICE LOW RISE PASSENGER (PE-04,05,06) | 41 |  |  |  | day | 2024-02-05 07:00 | 2024-06-19 17:00 | [12 empty] | 7 | 6 | 0qPbw+Ejf02rv6gEVf+pdA | Q7pqa8EUM0SVYoXYJk8CWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.8.1 | 41905734 | 41905733 | Shaft Scope | 19 |  |  |  | day | 2024-02-05 07:00 | 2024-05-15 17:00 | [12 empty] | 0 | 7 | fl/U+kOk0EexhJMGQbPJtg | 0qPbw+Ejf02rv6gEVf+pdA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.8.1.1 | 41905735 | 41905734 | Level P3 - Elevator Pit Work | 49 |  |  |  | day | 2024-02-05 07:00 | 2024-02-16 17:00 | [12 empty] | 0 | 8 | GPGdUufi80y4rMvA8rmu+w | fl/U+kOk0EexhJMGQbPJtg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.8.1.2 | 41905736 | 41905734 | Level 09 to18 | 23 |  |  |  | day | 2024-02-05 07:00 | 2024-04-10 17:00 | [12 empty] | 1 | 8 | 9I4rvSp/W0eCh3pkO87dnw | fl/U+kOk0EexhJMGQbPJtg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.8.1.3 | 41905737 | 41905734 | Level 19 to 25 | 42 |  |  |  | day | 2024-04-11 07:00 | 2024-05-15 17:00 | [12 empty] | 2 | 8 | w+2PlxQwJUCH8JnAomqQ3A | fl/U+kOk0EexhJMGQbPJtg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.8.2 | 41905738 | 41905733 | Level 25 - EMR Activities | 33 |  |  |  | day | 2024-04-26 07:00 | 2024-06-19 17:00 | [12 empty] | 1 | 7 | kJz9m6vpGkSum2gtOID7xw | 0qPbw+Ejf02rv6gEVf+pdA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.9 | 41905732 | 41905730 | OFFICE LOW RISE PASSENGER (PE-07,08,09) |  |  |  |  | day | 2024-01-08 07:00 | 2024-05-21 17:00 | [12 empty] | 8 | 6 | XmT07XVT3kCDSL2E03Y96Q | Q7pqa8EUM0SVYoXYJk8CWA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.9.1 | 41905740 | 41905732 | Shaft Scope | 49 |  |  |  | day | 2024-01-08 07:00 | 2024-04-17 17:00 | [12 empty] | 0 | 7 | 2wKzQTOBeEWsiLSmvkF/Rw | XmT07XVT3kCDSL2E03Y96Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.9.1.1 | 41905741 | 41905740 | Level P3 - Elevator Pit Work | 28 |  |  |  | day | 2024-01-08 07:00 | 2024-01-19 17:00 | [12 empty] | 0 | 8 | C8RqB4Mvp0GbPpdPWIAAOA | 2wKzQTOBeEWsiLSmvkF/Rw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.9.1.2 | 41905742 | 41905740 | Level 09 to18 | 38 |  |  |  | day | 2024-01-08 07:00 | 2024-03-13 17:00 | [12 empty] | 1 | 8 | XRTs+94tPUemG6QXeW8RiA | 2wKzQTOBeEWsiLSmvkF/Rw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.9.1.3 | 41905743 | 41905740 | Level 19 to 25 |  |  |  |  | day | 2024-03-14 07:00 | 2024-04-17 17:00 | [12 empty] | 2 | 8 | Z9LIWKo4ekmAfBB/XmJ5Tg | 2wKzQTOBeEWsiLSmvkF/Rw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.4.9.2 | 41905744 | 41905732 | Level 25 - EMR Activities | 46 |  |  |  | day | 2024-03-28 07:00 | 2024-05-21 17:00 | [12 empty] | 1 | 7 | uGjG7142nEe9vh3VPz4lAQ | XmT07XVT3kCDSL2E03Y96Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.5 | 41905731 | 41904256 | 2nd Group (Waiting on TC#1 Comeback) (PE-01,02,03) (PE-10,11,12) (SE-01) |  |  |  |  | day | 2024-04-02 07:00 | 2024-12-03 17:00 | [12 empty] | 4 | 5 | AbfB7f0WnUqY0LGP+/SvQw | kBUiuWZkRE6ihZJFVHh8hw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.5.1 | 41906172 | 41905731 | 2nd Group Summary | 49 |  |  |  | day | 2024-04-02 07:00 | 2024-12-03 17:00 | [12 empty] | 0 | 6 | cKYcRUU96ki2i4qUH5FnkQ | AbfB7f0WnUqY0LGP+/SvQw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.6 | 41904487 | 41904256 | Office Elevators (Sky Street- Lvl 34) | 22 |  |  |  | day | [14 empty] | 5 | 5 | tQeYsFw7lU6lMg3AfyuOJA | kBUiuWZkRE6ihZJFVHh8hw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.6.1 | 41904749 | 41904487 | Passenger Elevators | 43 |  |  |  | day | [14 empty] | 0 | 6 | iPqdkDMUckeROxY6bnXb3A | tQeYsFw7lU6lMg3AfyuOJA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.6.1.1 | 41904987 | 41904749 | PE 4-9 (Sky Street through- Lvl 23) |  |  |  |  | day | [14 empty] | 0 | 7 | QCdVc+grg0+HX2WdnpLrlw | iPqdkDMUckeROxY6bnXb3A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.6.1.2 | 41904988 | 41904749 | PE 10-15 (Lvl 23- 34)- No stops Lvl 10 thru Lvl 22 |  |  |  |  | day | [14 empty] | 1 | 7 | p9eoAK55KkKvu+DutPbgQw | iPqdkDMUckeROxY6bnXb3A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.6.2 | 41904750 | 41904487 | Service Elevators | 22 |  |  |  | day | [14 empty] | 1 | 6 | 8QDpuC5C0EKUqNSMK6iYQA | tQeYsFw7lU6lMg3AfyuOJA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.6.2.1 | 41904989 | 41904750 | SE 1 (Garage- Lvl 32) | 44 |  |  |  | day | [14 empty] | 0 | 7 | l/9HPNfz50+cK6v1R7w+Hg | 8QDpuC5C0EKUqNSMK6iYQA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.6.2.2 | 41904990 | 41904750 | SE 3 (Garage- Lvl 34) |  |  |  |  | day | [14 empty] | 1 | 7 | 3VE9fuoXDk+jXyDDA8MQtg | 8QDpuC5C0EKUqNSMK6iYQA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7 | 41904488 | 41904256 | Residential Elevators (Garage- Lvl 51) | 49 |  |  |  | day | [14 empty] | 6 | 5 | EvM/3DC6fUq65kTQSa69Ig | kBUiuWZkRE6ihZJFVHh8hw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1 | 41904751 | 41904488 | Passenger Elevators | 41 |  |  |  | day | [14 empty] | 0 | 6 | GS6eNkbeK0aen21kCtyKog | EvM/3DC6fUq65kTQSa69Ig | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1.1 | 41904991 | 41904751 | PE 1,2,3 (Garage- Lvl 51)- No stops Lvl 12 thru Lvl 34 |  |  |  |  | day | [14 empty] | 0 | 7 | qwVsBUxpyEGwNws9ehbNuA | GS6eNkbeK0aen21kCtyKog | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1.1.1 | 41905417 | 41904991 | PE1 Jump | 49 |  |  |  | day | [14 empty] | 0 | 8 | RhQgcdnbQ0u8odboS7+75A | qwVsBUxpyEGwNws9ehbNuA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1.1.1.1 | 41905422 | 41905417 | Crash Decks | 20 |  |  |  | day | [14 empty] | 0 | 9 | 8MEmJ5yPYEi3jyZ8mAgOyA | RhQgcdnbQ0u8odboS7+75A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1.1.1.1.1 | 41905423 | 41905422 | Level 18 | 0 |  |  |  | day | [14 empty] | 0 | 10 | OOY4Bk6oHU2CBT7B5l3vSA | 8MEmJ5yPYEi3jyZ8mAgOyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1.1.1.1.2 | 41905424 | 41905422 | Level 36 |  |  |  |  | day | [14 empty] | 1 | 10 | Wy5zv7+CgUilFl6pPf2OPg | 8MEmJ5yPYEi3jyZ8mAgOyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1.1.1.1.3 | 41905425 | 41905422 | Level 46 | 28 |  |  |  | day | [14 empty] | 2 | 10 | AhghdgMfJ0aaoHrDJU1UIQ | 8MEmJ5yPYEi3jyZ8mAgOyA | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1.1.1.2 | 41905419 | 41905417 | Jump #1 - Pit Scope / Levels P3-17 (10 Floors)(4 Openings) |  |  |  |  | day | [14 empty] | 1 | 9 | fL8/ervERU2JDFyoxGpvvw | RhQgcdnbQ0u8odboS7+75A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1.1.1.3 | 41905420 | 41905417 | Jump #2 - Levels 18-35 (18 Floors)(1 Opening) |  |  |  |  | day | [14 empty] | 2 | 9 | Q59vWOIPZEa/uzUTFS25fA | RhQgcdnbQ0u8odboS7+75A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1.1.1.4 | 41905421 | 41905417 | Jump #3 - Levels 36-46 (10 Floors)(10 Openings) | 4 |  |  |  | day | [14 empty] | 3 | 9 | POgIQHgi9kumedrg57CPtQ | RhQgcdnbQ0u8odboS7+75A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1.1.1.5 | 41905426 | 41905417 | Jump #2 - Remaining Levels | 46 |  |  |  | day | [14 empty] | 4 | 9 | uaQJGVlcY0uy1wIpGV2CNg | RhQgcdnbQ0u8odboS7+75A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.1.1.1.6 | 41905418 | 41905417 | EMR Scope | 21 |  |  |  | day | [14 empty] | 5 | 9 | ev8p9pDaIEqIHgX7A6Fr4w | RhQgcdnbQ0u8odboS7+75A | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.2 | 41904752 | 41904488 | Service Elevators |  |  |  |  | day | [14 empty] | 1 | 6 | EyQZv7rPvUK7RD+2qZX4ww | EvM/3DC6fUq65kTQSa69Ig | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.2.1 | 41904992 | 41904752 | SE 2 (Garage- Lvl 51) | 33 |  |  |  | day | [14 empty] | 0 | 7 | 7tioJYsXkUOdfSc2KL1W+Q | EyQZv7rPvUK7RD+2qZX4ww | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.2.1.1 | 41905606 | 41904992 | Shaft Scope |  |  |  |  | day | [14 empty] | 0 | 8 | EuuEhkAGe0CMElMaJDw5/A | 7tioJYsXkUOdfSc2KL1W+Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.14.7.2.1.2 | 41905605 | 41904992 | EMR Scope |  |  |  |  | day | [14 empty] | 1 | 8 | MCFkArqsCkmnwvt4ymfvXg | 7tioJYsXkUOdfSc2KL1W+Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.15 | 41904258 | 41904236 | FINAL SITE WORK | 42 |  |  |  | day | 2024-11-04 07:00 | 2025-01-30 17:00 | [12 empty] | 14 | 4 | arNgwc4Bak2JKNZHt1A15w | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.16 | 41904259 | 41904236 | OFFICE TOWER START-UP & COMMISSIONING | 9 |  |  |  | day | 2024-02-07 07:00 | 2025-01-03 17:00 | [12 empty] | 15 | 4 | dzqgPZx6E0mN6FB3cokedQ | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.4.17 | 41904263 | 41904236 | RESIDENTIAL TOWER START-UP & COMMISSIONING |  |  |  |  | day | 2024-10-04 07:00 | 2025-03-07 17:00 | [12 empty] | 16 | 4 | 6Avo0eP19EuJqJUL3ahWrg | MjDx2K8Y4ki27Z8wd1MiAw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.5 | 41904245 | 41905203 | Phased Turnover | 49 |  |  |  | day | 2022-04-27 07:00 | 2025-02-26 17:00 | [12 empty] | 4 | 3 | XqzU0+H70E+JPTzPd3UYsw | iRqoq5YdVEasR9RY3sZSmg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.5.1 | 41904287 | 41904245 | Turnover - Bus Terminal | 17 |  |  |  | day | 2022-04-27 07:00 | 2024-10-21 17:00 | [12 empty] | 0 | 4 | yGWdYEKlpE+dp5gmo9Jc2Q | XqzU0+H70E+JPTzPd3UYsw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.5.1.1 | 41904446 | 41904287 | CMP-13 - Level P1 Modifications (Standard Hours) |  |  |  |  | day | 2022-04-27 07:00 | 2024-04-03 17:00 | [12 empty] | 0 | 5 | 2yyApOI2iEep6bVGmWUA7w | yGWdYEKlpE+dp5gmo9Jc2Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.5.1.2 | 41904445 | 41904287 | CMP-12 - Bus Terminal Expansion (Standard Hours) |  |  |  |  | day | 2024-04-12 07:00 | 2024-10-21 17:00 | [12 empty] | 1 | 5 | cvCu4IKhiUCMpKzLdXDPfA | yGWdYEKlpE+dp5gmo9Jc2Q | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.5.2 | 41904288 | 41904245 | Turnover - Platforms | 7 |  |  |  | day | 2024-11-04 07:00 | 2025-02-26 17:00 | [12 empty] | 1 | 4 | xZDcaQE39kWpFL4kHLB7Eg | XqzU0+H70E+JPTzPd3UYsw | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.5.2.1 | 41904447 | 41904288 | CMP-14 - Platform Restoration | 46 |  |  |  | day | 2024-11-07 07:00 | 2025-02-26 17:00 | [12 empty] | 0 | 5 | BKYJANZIm06HTyTL9qCJLg | xZDcaQE39kWpFL4kHLB7Eg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.6 | 41905595 | 41905203 | Weather Days Used | 39 |  |  |  | day | 2020-11-23 07:00 | 2023-12-18 17:00 | [12 empty] | 5 | 3 | +5wDVKYstUWupN1bsdPZ8w | iRqoq5YdVEasR9RY3sZSmg | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.6.1 | 41905596 | 41905595 | Weather TOC#01 | 48 |  |  |  | day | 2020-11-23 07:00 | 2023-03-14 17:00 | [12 empty] | 0 | 4 | Pa5LTGT6006zBt9H/IQxCQ | +5wDVKYstUWupN1bsdPZ8w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.6.2 | 41905597 | 41905595 | Weather TOC#02-14 | 11 |  |  |  | day | 2021-07-30 07:00 | 2023-12-18 17:00 | [12 empty] | 1 | 4 | 1pTwKd4cJUCmg6Owd86/dA | +5wDVKYstUWupN1bsdPZ8w | 2024-05-10 15:13:41.774122+00
240001 | Test Project | 1.12.7 | 41906798 | 41905203 | AHU A&B - Operational | 26 |  |  |  | day | 2024-07-19 07:00 | 2024-12-31 17:00 | [12 empty] | 6 | 3 | gYC7sncVgE2eR86MrBlb1A | iRqoq5YdVEasR9RY3sZSmg | 2024-05-10 15:13:41.774122+00